MINISTRY OF HEALTH ZANZIBAR

Zanzibar Malaria Strategic Plan V 2024-2029 accelerating to zero local malaria cases

zanzibar malaria elimination programme

November 2023

# CONTENTS

CONTENTS	iii

TABLES	ix

FIGURES	ix

ABREVIATIONS	xi

FOREWORD	xiii

ACKNOWLEDGMENTS	xiv

EXECUTIVE SUMMARY	xvi

CHAPTER ONE: INTRODUCTION	18

BACKGROUND	18

POLICY AND PROGRAMMING ENVIRONMENT FOR MALARIA ELIMINATION	19

The Zanzibar Vision 2050	19

The Health Sector Strategic Plan IV for 2020/21 – 2024/25	19

THE MALARIA STRATEGIC PLAN V	20

Purpose of the Malaria Strategic Plan	20

Process and Steps of Developing the National Malaria Strategic Plan	20

Layout of MSP 2024-2029	21

CHAPTER TWO: COUNTRY PROFILE	22

OVERVIEW AND ADMINISTRATIVE SET UP	22

Geography and Climate	22

Demographic Information	22

Socio-Economic Status	22

HEALTH SYSTEM ANALYSIS AND ORGANIZATION	23

The Public Sector	23

The private sector	24

THE ZANZIBAR MALARIA ELIMINATION PROGRAMME	24

CHAPTER THREE: MALARIA SITUATION ANALYSIS	26

HISTORY OF MALARIA CONTROL IN ZANZIBAR	26

MALARIA VECTORS	27

Vector species	27

Insecticide Resistance	28

MALARIA PARASITES	28

MALARIA TRANSMISSION AND ENDEMICITY	29

Malaria Transmission Risk, Stratification and Mapping	29

Current Malaria Situation In Zanzibar	32

Case Classification	33

Malaria Admissions and Deaths	33

CHAPTER FOUR: PROGRESS MADE IN ACHIEVING 2017/18 - 2022/23 TARGETS	35

OVERALL PROGRESS ON EPIDEMIOLOGICAL INDICATORS AND TARGETS	35

Progress in MSP Morbidity and Mortality Impact Targets	35

Progress towards Entomological Impact	36

Financing of Malaria Activities at Program Level	36

EFFECTIVENESS OF HEALTH SYSTEMS IN DELIVERING HEALTH SERVICES	37

Organization of the health system	37

Malaria Services Rendered by ZAMEP	38

Integrated Malaria Vector Management	38

Malaria Diagnosis and Treatment	40

Procurement supply management	40

Malaria Surveillance and Response	41

Malaria Advocacy	41

Way Forward	42

CHAPTER FIVE: MALARIA STRATEGIC PLAN 2024-2029	45

OUTLINE TO NATIONAL MALARIA STRATEGIC PLAN 2024-2029	45

Purpose of the National Malaria Strategic Plan	45

Process of Developing the Malaria Strategic Plan 2024-2029	45

VISION, MISSION AND GOAL	45

Programme Vision	45

Programme mission	45

Goal	46

GUIDING PRINCIPLES	46

Strategic Focus	47

Strategic Directions for 2024-2029	47

STRATEGY OUTLINE	48

Core Strategic Areas: Strategic and Specific Objectives	48

Supportive Strategic Areas, Strategic and Specific Objectives	49

CORE STRATEGIC AREA 1: INTEGRATED MALARIA VECTOR MANAGEMENT	51

Strategic Objective 1	51

Integrated Malaria Vector management Strategic Approaches/Interventions	51

CORE STRATEGIC AREA 2: MALARIA DIAGNOSIS, TREATMENT AND PREVENTIVE THERAPIES	54

Strategic Objective 2.1:	54

Malaria Diagnosis Strategic Approaches/Interventions	54

Strategic Objective 2.2	56

Treatment and Preventive Therapies Approach/Intervention	56

CORE STRATEGIC AREA 3: MALARIA SURVEILLANCE AND RESPONSE	57

Strategic Objective 3	57

MSR Strategic Approaches/Interventions	57

SUPPORTIVE STRATEGIC AREA 4: MONITORING, EVALUATION, RESEARCH AND LEARNING	60

M&E Objectives	61

SUPPORTIVE STRATEGIC AREA 5: MALARIA LOGISTIC MANAGEMENT SYSTEM	62

Strategic Objective 5	62

MLMS Strategic Approaches/Interventions	62

SUPPORTIVE STRATEGIC AREA 6: SOCIAL BEHAVIOUR CHANGE AND COMMUNITY ENGAGEMENT	63

Strategic Approach 6	63

SBC&CE Strategic Approaches/Interventions	63

SUPPORTIVE STRATEGIC AREA 7: LEADERSHIP, PARTNERSHIP AND RESOURCE MOBILISATION	65

Strategic Objective 7.1	65

Malaria Leadership & Partnership Strategic Approaches/Interventions	65

Strategic Objective 7.2	66

Malaria Financing and Resource Mobilization Strategic Approaches/Interventions:	66

CHAPTER SIX: IMPLEMENTATION FRAMEWORK	68

ACCELERATING TOWARDS MALARIA ELIMINATION: MSP PHASES AND MODALITIES	68

MSP WORKPLAN	69

IMPLEMENTATION ARRANGEMENTS	70

OVERALL PROGRAMME MANAGEMENT	70

The Zanzibar Malaria Elimination Program (ZAMEP)	70

ZAMEP Structure and Functional Technical Units	72

ZAMEP Management	72

Partnership:	74

Technical Thematic Units	74

ROLES AND RESPONSIBILITIES OF DISTRICT HEALTH MANAGEMENT TEAMS, HEALTH FACILITIES AND COMMUNITIES	75

District Management Teams	75

Health Facilities	76

Communities	76

PROGRAM GOVERNANCE	76

Independent National Malaria Elimination Advisory Committee	76

ZAMEP Management Committee (ZAMC)	77

Malaria Technical Working Groups	77

Partnerships and co-ordination	81

National fiscal planning cycle and alignment with malaria programme	81

Cross‐border malaria initiatives	82

MULTISECTORAL ENGAGEMENT	82

MANAGEMENT PROCEDURES	1

Data Management Arrangements	1

Procurement and Supply Management Systems	1

Financial Resources Management And Audits	2

RISK ANALYSIS AND MITIGATION	2

COSTS OF NSP, ANTICIPATED FUNDS AND GAPS	3

CHAPTER SEVEN: MONITORING AND EVALUATION FRAMEWORK	5

COMPREHENSIVE MALARIA STRATEGIC INFORMATION SYSTEM	5

Integrated Malaria Surveillance System	6

Health Management Information System	7

Tracking Implementation Progress	8

Commodity Tracking System	8

Programmatic Monitoring and Evaluation System	9

DATA QUALITY	9

PERFORMANCE FRAMEWORK	10

APPENDIX	11

ANNEX 1: WORKPLAN	12

ANNEX 2: BUDGET	19

ANNEX 3: PERFORMANCE FRAMEWORK	20

ANNEX 5. SWOT ANALYSIS	26

# TABLES

Table 1: API per district per year (Source: MEEDS/IDSR)	30

Table 2: Shehia count by annual level of parasite incidence (per 1000)	31

Table 3: Performance of Impact Indicators	35

Table 4: Trends in Malaria Morbidity 2018/19 To 2021/22	36

Table 5: Epidemic Preparedness Roles by Level	58

Table 6: risk outline and proposed mitigation:	2

# FIGURES

Figure 1: Vector species aggregated by location (upper charts) and disaggregated by year Pemba and Unguja 2010-2021 (bottom charts)	27

Figure 2: Resistance profile by type of insecticide	28

Figure 3: Proportion of parasite species identified in health facilities 2020-2022	29

Figure 4: Malaria foci classification.	30

Figure 5: API per 1,000 population by shehia in Pemba and Unguja 2021 (source MCN)	31

Figure 6: Malaria cases per year, by country and islands 2008-2022 (upper charts) and malaria cases per month by country (middle chart) and island (bottom chart)	32

Figure 7: Case classification by years and week	33

Figure 8: Malaria admissions and deaths 2020-2022	33

Figure 9: Budget and Commitment from all Sources	37

Figure 10: IRS Operation in Zanzibar 2017/18 to 2020/2021	39

Figure 11: Number of tests and ABER by year and location	40

Figure 13: Percentage of women who reported that malaria is the most serious health problem in the community by region 2017	41

Figure 14: MSP phases and reviews	68

Figure 15: the ZAMEP organograms	72

Figure 16: Proportion of NSP costs by strategic area	3

Figure 17: Total and proportion of budget costs by year and strategic area	3

Figure 18: Proportion of NSP costs by partner and funding gap (Year 1- year 4)	4

Figure 19: Total and Proportion of NSP costs by partner and funding gap by year and development partner and the remaining gap	4

Figure 19: Elements of the comprehensive Zanzibar Malaria Elimination Information System	6

Figure 20: Malaria Surveillance and Response Information System	7

Figure 21: Malaria HMIS and Response Information System	7

Figure 22	8

Figure 23	9

# ABREVIATIONS

| ACTs; Artemisinin Combination Therapies. CHVs; Community Health Volunteers. CM; Case Management. CMSIS; Comprehensive Malaria Strategic Information System. CSOs; Civil Society Organizations. DHIS2; Demographic Health Information System 2. DHMT; District Health Management Team. DMO; District Medical Officer. DMSO; District Malaria Surveillance Officer. DPS; Director of preventive services. ELISA; Enzyme-linked Immunosorbent Assay. fDA; Focal Reactive Drug Administration. GF GC7; Global Fund Grant Cycle 7. GFATM; Global Fund to fight AIDS, Tuberculosis and Malaria. GPS; Geographical Positioning System. GTS; Global Technical Strategy (WHO). HCPs; Health Care Providers. HMIS; Health Management Information System. HRH; Human Resources for Health. HSS; Health Systems Strengthening. HSSP; Health Sector Strategic Plan. ICT; Information and Communication Technology. IDSR; Integrated Disease Surveillance and Response. IEC; Information, Education, Communication. IEC; Information Education and Communication. IMCI; Integrated Management of Childhood Illness. IMVM; Integrated Malaria Vector Control. IPC; Interpersonal Communication. IRS; Indoor Residual Spraying. ITN; Insecticidal Treated Net. LLIN; Long Lasting Insecticide Net. LSM; Larval Source Management. MERL; Monitoring, Evaluation, Research and Learning. M&E; Monitoring and Evaluation. MCM; Malaria Case Management. MCN; Malaria Case Notification. MDA; Mass Drug Administration. mDTWG; Malaria diagnosis technical working group. MEED; Malaria Early Epidemic Detection. mMQAQC; Malaria Miscroscopy quality assurance and quality control. MMS; Malaria molecular surveillance. MOH; Ministry of Health. MPR; Malaria Program Review. mRDT; malaria Rapid Diagnostic Test. MSIS; Malaria strategic information system. MSR; Malaria Surveillance and Response. NCD; Non-communicable diseases. NMSP; Malaria Strategic Plan. OPD; Out Patient Department. PHCC; Primary Health Care Center. PHCU; Primary Health Care Unit. PMI/USAID; President Malaria Initiative/United States Agency for International Development. PPM; Pooled Procurement Mechanism. qPCR; quantitative Polymerase Chain Reaction. RBM; Roll Back Malaria. RGOZ; Revolutionary Government of Zanzibar. RSSH; Resilient and Sustainable Systems for Health. RTI; Research Triangle Institute. SBC&CE; Social behaviour change and community engagement. SME; Surveillance Monitoring and Evaluation. TBD; To be determined. TES; Therapeutic Efficacy Study. TOR; Terms of Reference. TPHPA; Tanzania Plant Health and Pesticides Authority. TWG; Technical Working Group. UHC; Universal Health Coverage. VC; Vector management. WHO; World Health Organization. ZAMEP; Zanzibar Malaria Elimination Programme. ZGFCCM; Zanzibar Global Fund Country Coordinating Mechanism. ZIHHTLP; Zanzibar Integrated HIV, Hepatitis, Tuberculosis and Leprosy Programme. ZMEAC; Zanzibar Malaria Elimination Advisory Committee. ZMEAC; Zanzibar Malaria Elimination Advisory Committee. |  |
| --- | --- |

# FOREWORD

Malaria elimination is a national developmental agenda in Zanzibar. The Revolutionary Government of Zanzibar is of the view that investments channeled towards the fight against malaria must reduce local disease transmission and manage malaria importation to the maximum. I am confident that through concerted efforts, the elimination agenda is feasible and attainable as previous cumulative experiences in implementing malaria control and elimination interventions in Zanzibar have demonstrated and pointed towards that. .

The previous National Malaria Strategic Plan (2018 – 2023) outlined the key interventions required to eliminate malaria by 2023. Though this was not achieved, some notable successes were achieved over the last five years in various thematic areas. However, there were some challenges encountered along the way such as high rate of malaria importation, inadequate multisectoral response and the malaria outbreak which occurred in 2020 among others, which certainly contributed to not achieving the malaria elimination agenda.

In view of these challenges and considering that the MSP 2018-2023 ends in June 2023, the need for the development of the 2024-2029 strategic plan is critical.

The underpinning activities in the 2024-2029 strategic plan include; a robust malaria surveillance accompanied by multisectoral response, integrated vector management (IVM) that monitors vector activities for targeted response. It also include prompt case management that provides quality diagnosis and correct treatment for all confirmed cases coupled with reactive case detection which is key for transmission reduction.

Health promotion and behaviour change communication is a cross-cutting pillar that will ensure that maximum benefits are derived from all interventions that target the communities.

Lastly, an enabling programme environment that guarantees effective partnerships through multi-sectoral engagements and sustainable financing by way of harnessing of domestic resources needed for malaria elimination is vital.

I trust that this document whose aim is to build up and accelerate the advancements realized in the previous strategic plan and formulate innovative strategies will meet the aspirations of the people of Zanzibar to ultimately reach the goal of malaria elimination.

Hon. Nassor A. Mazrui

MINISTER FOR HEALTH

ZANZIBAR

# ACKNOWLEDGMENTS

The development of this National Malaria Strategic Plan 2024-2029 was made possible through concerted and collaborative efforts from various institutional and individual stakeholders. The Zanzibar Malaria Elimination Programme (ZAMEP) extends its special gratitude to the leadership at the Ministry of Health; the Principal Secretary Dr. Fatma Mrisho and the Director of Preventive Services Dr. Salim Slim for their stewardship, guidance and unwavering support throughout the entire process.

I wish to mention that many Institutions (WHO, PMI/USAID, RBM Partnership To End Malaria, PSI, JHU, ABT, IHI, Swiss THP, PharmAccess Foundation) and individuals from both within and outside the Zanzibar Malaria Elimination Program who made substantial contributions. The Programme is indebted to the technical leads; Dr. Abdullah S. Ali (local Consultant), Fabrizio Molteni (Swiss TPH) and Dr. Anthony Yeta (RBM International Consultant) who availed invaluable technical support and guidance.

We are also very grateful to the Population Service International and PMI/USAID for providing the funding that made this malaria strategic plan conceivable.

Contributors from ZAMEP

Name				Position

Abdillahi M. Said		PSM

Ali H. Suleiman		F FP MOH

Ali O. Ali			Entomology

Ali O. Hamdu			Case Management

Bakar J. Mohammed		Head of Diagnostic

Bakar O. Khatib		Head of Integrated Malaria Vector Management

Biashara H. Hamid		SBC&CE Officer

Dr.Fadhil M. Abdalla		ZAMEP	Malaria Advisor

Fatma M. Kabole		Deputy Director for Preventive Services

Haji H. Ameir			CMT Officer

Hamis B. Kamugisha		Finance

Kali A. Omar			Head of Immunomolecular Laboratory

Majda H. Nassor		Diagnostic

Makame M. Kombo		Pemba Coordinator

Mohamed H. Ali		MnE ZAMEP

Mohamed Y. Ndee		Finance

Mvita H. Haji			MnE MOH

Mwinyi I. Khamis		Head SBC&CE

Raya A. Ibrahim		MERL

Safia M. Ali			DPM ZAMEP

Sammiha M. Ali  		Finance

Shija J. Shija			AG.Program Manager

Contributors outside ZAMEP

Name				Position

Abdullah S. Ali			Tech Advisor

Caroline Mshanga		JHU-BA

David Dadi			JHU-TVA

Dunstan Bishanga		COP IHI

Faiza B. Abass			PharmAccess Foundation

Geofrey Makenga		Epid. and Surv.

Helena Haule			PA-TL

Jovin Kitau			Malaria Technical Officer, WHO- Tanzania

Lauden George		PA-Advisor

Mubita Lifwatila		COP ABT

Mwinyi I. Msellem		MOH Researcher

Naomi Serbantez		PMI RA

Nico Govella			Entomologist

Noela Kisoka			Swiss TPH

Samson Kiware		IHI

Sigsibert Mkude 		COP PSI

Wahida S. Hassan		M&E MOH

Shija Joseph Shija

Acting Program Manager

Zanzibar Malaria Elimination Program

Ministry of Health

ZANZIBAR.

# EXECUTIVE SUMMARY

The Revolutionary Government of Zanzibar through the Ministry of Health in collaboration with her partners are dedicated to accelerate malaria elimination agenda across the Island. The Zanzibar Malaria Elimination Programme (ZAMEP) is mandated to technically guide all implementing actors and document results. Over the decades (since 2007), significant progress has been made culminating in the reduction and subsequent sustaining of malaria prevalence to less than one percent. This National Malaria Strategic Plan, covering the period 2024 to 2028, aims to accelerate the trajectory of malaria elimination to zero indigenous case and prevent re-introduction.

Demographically, the Administrative Unit’s population distribution report 2022, noted that the population of Zanzibar has increased about fivefold from 354,815 in 1967 to 1,889,773 in 2022.  The report highlighted an average annual inter-census population growth rate of 3.7 percent. These findings in reality have policy implications in rendering key basic socio-services, health inclusive.

Economic indicators reveal prevailing poverty in Zanzibar, with 30% people living below the basic need poverty line and over 48% of households experience varying levels of food insecurity. The adult illiteracy rate in 2014/15 was 16.3%. The 2014/15 Integrated Labour Force Survey reports 27% of youth aged 15-24 being unemployed (45.8% in urban areas).

ZAMEP has a comprehensive malaria database ranging from routine data to survey and study findings. Operational surveys are commonly used to offer timely information at a national level for programmatic decision making.

Despite the ZAMEP, in collaboration with partners and other key stakeholders, making significant progress in fast-tracking malaria elimination, the final goal as envisaged in the just ended MSP has not been attained due to several technical and financial challenges among others.

The Programme conducted its mid-term review in 2020 with the aim of redefining the programmes strategic direction and focus. It aimed to inform actions required to double efforts in the quest of accelerating progress towards malaria elimination targets of the current MSP by 2023.

The MTR findings 2020 noted that, progress towards epidemiological impact had stalled and was at risk of reversal. The malaria incidence target for 2019/2020 was 2.2/1000 but what was attained was 3.7/1000 population.

Overall, the number of malaria cases increased from 4,171 in 2017 to 6,736 in 2019, while the number of deaths increased from 1 in 2017 to 5 in 2019. It is against this background that practical recommendations were brought to the fore aimed at improving the situation.

The Malaria Program Review conducted in 2022 noted that, approximately 87% of the blood films between 2020 and 2022 revealed an infection caused by P. falciparum alone. Increased population movement was linked with rate of malaria importation which varied over the years and also noted that indigenous cases detected were on the upswing during seasonal peaks as well as in 2019-2020 outbreak.

With regards to implementation, 2021/2022 the MPR revealed that a total of 155 activities were planned for implementation of which 59% were fully implemented, 15% partially, 15% low implemented while 10% were not implemented at all due funding reasons.

In view of these findings, it was strongly recommended to mitigate the effect of imported cases and the consequent re-introduced transmission. Moreover, understanding better the dynamics and the determinants of population and ecological vulnerability was emphasized. Therefore, upon the expiration of the 2019/2023 MSP, this new strategic plan will incorporate the recommendations and lessons learnt that will assist in the development of technically sound scientific evidence based new interventions to halt local transmission.

The programme vision of this MSP is having a healthy population free from malaria in Zanzibar and the goal is to accelerate elimination of local malaria transmission and preventing re- introduction. The goal will supported by strategic approaches and objectives and the programme will remain steadfast and keep a vigil on the disease transmission patterns in both Islands and respond accordingly.

# CHAPTER ONE: INTRODUCTION

## BACKGROUND

Over the past two decades, the Islands of Zanzibar have made dramatic progress in reducing malaria transmission, driving the parasite prevalence down from historic levels of more than 20% in 2002 to consistently less than 1% in the last decade. Notably, the last two malaria indicators surveys (MIS) of 2017 and 2022 report zero prevalence in the sampled children. The changed malaria transmission resulted in a dramatic reduction of both morbidity and mortality attributed to malaria. As a result of this success, the Zanzibar Malaria Elimination Program (ZAMEP) is now focusing on a malaria elimination agenda following.

Zanzibar is one of the few countries in Sub-Saharan Africa that expressed its commitment to move from control towards elimination of malaria. Although elimination efforts had twice failed in the Islands: the first time in the 1960’s under the WHO led Global Malaria Elimination Programme and the second time in the 1980’s under a large initiative funded by the USAID. The ZAMEP renewed its viewpoint and re-programmed to address elimination agenda. The implementation of the planned interventions and activities in this document will be based on regional recommendations and best practices aligned to the World Health Organization (WHO) and the Southern African Development Community (SADC) malaria elimination frameworks.

The gains towards malaria elimination have been accelerated and maintained by increase in funding levels since mid-2000’s, mainly through the Global Fund to fight AIDS, Tuberculosis and Malaria (GFATM) and the U.S. President’s Malaria Initiative (PMI), coupled with the introduction of highly effective treatment, new diagnostics tools, long-lasting insecticide treated bed nets for prevention, and new insecticides for Indoor Residual Spraying.

The Zanzibar Malaria Elimination Program has set up a functional malaria surveillance able to notify and provide follow up of every single malaria confirmed case. The surveillance system reported 67% and 78% imported cases in 2021 and 2022 respectively. To facilitate tracking of the implementation of Malaria Strategic Plan of 2024 - 2029, an M&E Plan was also developed for use. The M&E Plan guides stakeholders on how to monitor and evaluate the implementation of the National Malaria Strategic plan and determine whether its goals and objectives are being achieved. Furthermore, a cross-cutting national malaria social and behavioural change strategy is currently in place in line with the Strategic Plan. The overall goal is to increase the correct use of malaria-recommended interventions to over 85 percent by 2029 through a well-coordinated SBC&CE activity.

In fostering the elimination efforts, the ZAMEP is planning to launch a national campaign for accelerating malaria elimination. The campaign will compose of a comprehensive intervention in a phased manner aiming to attempting reaching the ultimate goal of zero malaria transmission.

Accordingly, the ZAMEP is engaging stakeholders and partners to provide the required technical support to curb the challenge of malaria importation in Zanzibar through various recommended interventions. The current commitment from various stakeholders at all levels enhances the government’s efforts towards malaria elimination.

## POLICY AND PROGRAMMING ENVIRONMENT FOR MALARIA ELIMINATION

The Ministry of Health established the former Malaria Control Programme in 1988 under the Directorate of Preventive Services and Health Education. The current Malaria Elimination Programme operates based on the global and national guidance on malaria prevention and elimination. Furthermore, the implementation is also based on regional recommendations and best practices and in alignment to the World Health Organization (WHO) and the Southern African Development Community (SADC) malaria elimination frameworks.

At global level, the ZAMEP observes the WHO technical recommendations during the implementation of its operational plans. For instance, the World Health Organization’s Global Technical Strategy (GTS) for Malaria 2016-2030 is one among the fundamental guiding documents for malaria control and elimination. The strategy provides a comprehensive framework to guide countries in their efforts to accelerate progress towards malaria elimination. The strategy sets the target of reducing global malaria incidence and mortality rates by at least 90% by 2030. Targets for countries in pre-elimination stage are based on the country context.

Essentially, strategy aims at a world free of malaria. In Zanzibar context, malaria surveillance has been transformed into a key intervention as guided by the GTS. Strengthening malaria surveillance is fundamental to programme planning and implementation and is a crucial factor for accelerating progress.

### The Zanzibar Vision 2050

The Zanzibar Development Vision 2050 is a long-term national development plan formulated to guide Zanzibar’s overall development agenda. The Vision is shaped by four pillars. The malaria elimination is linked to the second pillar that is related to human capital and social services that is conducive to a healthy, competitive, innovative and productive society.

The Vision 2050 emphasizes on the provision of basic health services for all people without discrimination and priority shall be given to the most vulnerable population groups and directed at preventive services, combating epidemics, maternal and child care services.

### The Health Sector Strategic Plan IV for 2020/21 – 2024/25

The HSSP IV is focused on the goal of moving towards achieving Universal Health Coverage malaria inclusive. The Strategic Plan is fundamental to provide guidance on global and national multi-sectoral strategies as well as providing broad direction in emerging and re-emerging health conditions. The HSSP IV uses a balance score card approach, which is a strategic planning and management system that is used to align and communicate prioritized projects, products, and services. The ZAMEP is using health sector plan to align its activities accordingly.

## THE MALARIA STRATEGIC PLAN V

### Purpose of the Malaria Strategic Plan

The primary purpose of the malaria strategic plan is to articulate the programme goal, objectives and targets for the 2024-2029 period. Additionally, it lays out a plan on how the programme aims to attain the goal and objectives of the strategic plan. The MSP is also used as a resource mobilization document as it spells out the what, how and when activities need to be implemented. In this way, resources can be adequately mobilized and planned for accordingly. In addition, the MSP will be used as a tool for accountability as it provides a tracking mechanism through the performance framework.

### Process and Steps of Developing the National Malaria Strategic Plan

With the 20118-2023 MSP coming to an end, the programme alongside its stakeholders and donors were involved in the Malaria Programme Review (MPR) conducted in September 2022. The review process was diligently guided by the WHO’s 2019 Manual for developing national malaria strategic plans. A task force for the development of the MSP was established to oversee overall implementation. Similarly, the technical working group was instituted comprising of technical officers from the ZAMEP as well as development and implementing partners. Appropriate Terms of Reference were developed for the technical working groups.

The four phases, including planning, thematic desk reviews, validation (field visits, interviews) and programme strengthening were followed accordingly.

Planning: The aim of the planning phase of the MPR was to consult and secure consensus among all partners and stakeholders.

Thematic desk review: It included assembling information from reports and documents. A three-day workshop for the internal reviewer was held and the output of the workshop was a draft MPR report for sharing with the external reviewers and validation during the next phase of the MPR.

Validation: The aim of the validation phase was built upon the thematic review reports through national level consultations and sub-national field visits with the outcome of this process being a finalized MPR report. The external validation consultations were held between the ZAMEP and the WHO country office. A team of 7 senior WHO/RBM external consultants were identified to support the validation exercise. The consultants worked closely with the local consultant and ZAMEP team to form 6 external validation teams visited the selected Government Ministries, District Authorities, health facilities and malaria stakeholders at various levels.

Programme Strengthening: Following this process, the final report was developed and shared to MoH Officials, key stakeholders and partners. The MPR formed a foundation for the development of a new MSP.

### Layout of MSP 2024-2029

The MSP 2024-2029 is organized into seven chapters. Subsequent to this introduction, chapter two provides the country profile. Chapter three highlights on the Zanzibar malaria situation analysis. Chapter four runs through a progress made in achieving targets for the 2018-2023 malaria strategic plan. Chapter five provides details of the MSP 2024-2029. Finally, chapter six presents the implementation framework and work-plan and chapter seven outlines the monitoring and evaluation framework.

# CHAPTER TWO: COUNTRY PROFILE

## OVERVIEW AND ADMINISTRATIVE SET UP

### Geography and Climate

Zanzibar consists of two main densely populated islands, Unguja (1,666 km2) and Pemba (988 km2), as well as several other smaller islands, some of which are uninhabited. The entire population is closer to two million. The islands are located in the Indian Ocean, about 30 kilometers off the coast of mainland Tanzania between latitudes 5 and 7 degrees south of the Equator.

The climate of Zanzibar is equatorial and humid. The maximum temperature is around 30oC during the hot season, lasting from December to March. The minimum temperature is around 20oC during the cool season, which lasts from June to November. Zanzibar has two main rainy seasons, a long rainy period (Masika) from March to June and a short rainy period (Vuli) that starts in October and ends in December. Precipitation is high, ranging from 900 to 1000 mm during the heavy rains in April and May and 400 to 500 mm during the short rains in November-December. On average, precipitation is slightly higher in Pemba compared to Unguja. Climatic changes especially on rainfall patterns are attributed to the increased number of malaria cases on yearly basis.

### Demographic Information

The recent national population census was carried out in 2022.  Based on the 2022 population census, Zanzibar has a total population of 1,889,773 of whom 915,492 (48.4%) are male and 974,281 (51.6%) female.  About 69% of the population lives in Unguja and 31% in Pemba. Zanzibar is subdivided into five administrative regions and eleven districts, of which seven are in Unguja and four in Pemba. Each of the districts is sub-divided into several 388 Shehias which are the smallest administrative areas. A district of Mjini Magharibi is densely populated with 893,169 inhabitants, followed by Kaskazini Pemba with 272091 residents. Kusini Unguja is the lowest with a population of 195,873. The population growth is 3.7%.

### Socio-Economic Status

Economic indicators depict prevailing poverty in Zanzibar, with 30% people living below the basic need poverty line and over 48% of households experience varying levels of food insecurity. The adult illiteracy rate in 2014/15 was 16.3%. The 2014/15 Integrated Labour Force Survey reports 27% of youth aged 15-24 being unemployed (45.8% in urban areas). In 2015, agriculture contributed 19.2% of the total Gross Domestic Product of Zanzibar, also accounted for the livelihoods of over 30% of Zanzibari. Furthermore, 21% Zanzibar residents are engaged in shops, stalls, street vending and informal economic activities. Another 21% are occupied in crafts and elementary occupations while 7% are fishermen.

Tourism industry plays a major role in domestic revenues in Tanzania mainland and Zanzibar. According to National Bureau of Statistics – Press release of May 2022, the number of tourist arrivals for the period of January – April 2022 has increased significantly. A total of 367,632 tourists visited various tourism attractions compared to 275,097 tourists who entered the country during the similar period in 2021. This is an increase of 92,535 tourists, equivalent to 33.6 percent. Out of 367,632 tourist arrivals, 124,212 tourists entered the country via Zanzibar, which is equivalent to 33.8 percent of total visitors. Zanzibar is becoming an attractive destination for a large number of tourists. Low prevalence of malaria for (almost two decades is one of the possible contributing factors.

## HEALTH SYSTEM ANALYSIS AND ORGANIZATION

### The Public Sector

The Ministry of Health is overall responsible for the strategic direction of the sector. The organization of the public health care system is based on a district model consisting of a network of primary health care units (PHCU) complemented by several secondary (Primary Health Care Centers, and newly constructed District Hospitals) and tertiary referral structures. In theory there are two types of primary health care units: PHCU (basic primary health care services) and PHCU plus (same plus obstetric, laboratory and dental services). The Zanzibar health care system is comprised of 263 health facilities, 178 (68.0%) are public owned. Out of 178 public health facilities, 105(57.9%) are in Unguja island and 75 (42.1%) are in Pemba while the private health facilities, 71 (83.5%) are in Unguja and 14 (16.5%) in Pemba. All these facilities have malaria diagnostic capacity - MRDTs at the PHCU level and microscopy for Primary Health Care Centers (PHCC) and above - and dispense ACTs. According to the most recent Malaria Indicator Survey, almost 95% of the facilities have at least one staff member trained on malaria and IMCI (MIS, 2007).

Zanzibar has an impressive primary health care infrastructure that places almost all (99.1%) households in Unguja and Pemba within five kilometers of a health facility.  The provision of health care services has been further disseminated to primary, secondary, and tertiary levels that allow good access to health care. There are 161 primary health care facilities that are supported by 2 Primary Health Care Centers (Cottage Hospitals), 4 district hospitals, 1 regional hospital and 2 specialized hospitals (psychiatry and maternity). At the apex of the Zanzibar health system, Mnazi Mmoja Hospital supports all districts and regional hospitals as a referral hospital for all Islands of Zanzibar. In Zanzibar, geographical access to public health facilities is good, but the necessary human resources are not always in place to ensure access to treatment for the population. Ensuring the necessary human resource capacity, in terms of both skills and numbers, at all levels of the health care system remains a challenge.

There are various Health Professional Boards and Councils under the MoH which are responsible for the promotion of transparency, professionalism, and accountability within the professions. The Boards and Councils also have a mandate on the provision of technical advice to improve health service delivery at all levels including assuring technical standards of staff and ethics. There is also a Private Hospital Advisory Board that ensures private facilities provide quality health services by qualified and skilled health personnel.

### The private sector

Zanzibar has a flourishing private health care sector that consists of 154 private hospitals, providing outpatient care, 175 registered pharmacies and 480 over the counter (OTC) outlets selling over-the-counter drugs, excluding malaria treatments. About two-thirds of these private facilities are in and around Zanzibar town. Although the proportion of mothers seeking care through the public sector has been increasing, the private sector remains an important source of minor alignments.

Of recent, Zanzibar has made progress towards achieving the Health Sector Strategic Plan III goals with improvement in many of the health outputs, outcomes and impacts including maintaining lower HIV prevalence (0.4%) and malaria prevalence (1%). Life expectancy has improved from 63.25 years for male and 67 years for females in 2011 to 65.7 years for males and 70.8 years for females in 2021. Access and uptake of reproductive health services have improved as well. There is a reduction of maternal mortality from 228/100,000 live births in 2011 to 118/100,000 live births in 2021. Under five mortality has also declined from 75/1,000 live births in 2010 to 56/1,000 live births in 2015/16. Infant mortality has also declined from 54/1,000 live births in 2010 to 45/1,000 live births in 2015/16.

## THE ZANZIBAR MALARIA ELIMINATION PROGRAMME

The ZAMEP is responsible for the coordination of all malaria activities in Zanzibar. ZAMEP is one among the development programmes under the Directorate of Preventive Services and Health Promotion of the Ministry of Health.

The ZAMEP is relatively well staffed and has various units responsible for the coordination and implementation of different activities related to the objectives of the strategic plan. However, vector management unit requires strengthening of human resource. A data analyst with strong background in epidemiology need to be in place. Overall social behaviour change and effective community engagement necessitates for a specific knowledge and skills of which are lacking at programme level. Graphic designer is missing in the entire Ministry to the extent that all art work have to be out-sourced.

The program is financially mainly supported by the RGoZ, GF, USAID/PMI, and is also a beneficiary of technical assistance from various key stakeholders such as the WHO, Swiss TPH among others.  Furthermore, national and international research institutions play a major role in providing evidence base data for programmatic decision making.

# CHAPTER THREE: MALARIA SITUATION ANALYSIS

## HISTORY OF MALARIA CONTROL IN ZANZIBAR

Historically, malaria has been a major public health, social and economic problem in Zanzibar, except for a short period during the malaria eradication program from 1958 to 1968. In the mid-1920’s, an early document on the epidemiology of malaria in Unguja reported a parasite prevalence of 68% among children 1-6 years of age. In the 1930’s and 1950’s similar parasite prevalence was found in both Unguja and Pemba,

Before World War II; environmental management, chemical larviciding and quinine distributions to school children were the main malaria control intervention tools in Zanzibar. Larvivorous fish and mosquito nets were also used but with limited success. After World War II spraying activities with DDT and dieldrin were started. In 1961 the malaria control program was upgraded to an eradication program. The eradication program continued the bi-annual cycles of IRS with dieldrin and started mass distribution of amodiaquine and primaquine resulting in community parasite prevalence below 5%. However, the eradication program failed to interrupt transmission, which was blamed on technical, administrative and operational shortcomings. The eradication program was terminated in 1968, though malaria control activities continued, largely through the support of community volunteers. By the late 1970s, parasite prevalence had again increased to around 40% in Unguja. In 1982, a blood slide survey of symptom-free school children showed a point prevalence of 36% P. falciparum parasitemia, suggesting that falciparum malaria was highly endemic in Zanzibar.

In 1984 Zanzibar, assisted by USAID, launched a five-year project to control malaria to a level where it no longer would be a major public health problem. The main strategies included DDT spraying and chloroquine administration through dispensaries. Results, however, were poor due to inadequate coverage and operational problems like what was experienced during the eradication period. In the 1990’s funding for malaria control was limited. Nevertheless, in 1993 the new global strategy for malaria control was adopted emphasizing on prompt and effective malaria treatment rather than IRS. This strategy was, however, highly hampered by an increasing resistance to chloroquine around the time.

The Zanzibar Malaria Control Program was implemented from 1984-1989 and adopted similar strategies to the WHO elimination attempt of the 1950s focusing heavily on indoor residual spraying (IRS). The ZMCP began spraying in 1984 with two rounds of IRS, which was credited with the drop in prevalence from 54% in 1984 to 35% in 1985. However, the project was terminated in 1989.

The start of the Global Fund to Fight Aids, Tuberculosis and Malaria (GFATM) 2003 and the President’s Malaria Initiative (PMI) in 2006 marked a new era in malaria control for Zanzibar with a consistently well-funded program resulting in the above-described reduction in the malaria burden to date.

## MALARIA VECTORS

### Vector species

In both Pemba and Unguja most species detected by PCR are An. arabiensis. An. gambiae s.s. has been virtually eliminated in the islands while a few samples of An. funestus group were detected in recent years (Figure 1). Sporozoite rate in the last decade was extremely low, but in the recent years, a relative upsurge is observed from 0.1% in 2019 to 1.1% in 2021.

Figure 1: Vector species aggregated by location (upper charts) and disaggregated by year Pemba and Unguja 2010-2021 (bottom charts)

| Proportion of anopheline species analysed by PCR Zanzibar (left) and Islands (right) 2020- 2021 (see key below) |  |
| --- | --- |
| Annual anopheline species % (PCR) by island; Pemba (left) an Unguja (right) 2010-2021 (see key above) |  |

Source: ZAMEP Database 2023

Entomological surveillance is carried out in 10 sentinel sites of Unguja and Pemba. The emergence of new mosquito species An. stephensi in Africa –considered as an efficient vector of urban malaria, requires a constant watch. To date, surveillance reports indicate non-existence of the An. stephensi in Zanzibar.

### Insecticide Resistance

Resistance to pyrethroid has been progressively detected since the early 2010s, first in Pemba and then in Unguja islands. Other classes of insecticides so far do not show signs of resistance (figure 2). The high level of pyrethroid resistance is a direct threat to the effectiveness of conventional ITNs.

Figure 2: Resistance profile by type of insecticide

## MALARIA PARASITES

Approximately, 87% of the blood films between 2020 and 2022 revealed infections caused by P. falciparum, alone (77%) or mixed with other parasites (10%). Few differences were observed in the same period in Pemba and Unguja islands. Figure 3 below illustrates health facilities findings.

Figure 3: Proportion of parasite species identified in health facilities 2020-2022

## MALARIA TRANSMISSION AND ENDEMICITY

Malaria transmission has historically been holoendemic with a trend towards hyperendemicity in the 1990s and perennial with two peaks associated with seasonal rainfalls in March–June and October–November. Despite these trends from the past few years, malaria transmission remains unstable, correlating with undetermined annual rainfall levels and increased population movement and socio-economic activities.

The highly seasonal and unstable nature of malaria transmission suggests that acquired immunity by at-risk populations is undetermined, and all age groups are thus at risk of developing clinical malaria which may turn into severe if no medical consultation is sought.  In 2008 the MoH with the support from the PMI/USAID launched a Malaria Early Epidemic Detection System (MEEDS) based on weekly malaria aggregated reporting and later, in 2012, an individual Malaria Case Notification (MCN) system of all cases diagnosed at health facility level and subsequent follow up of the index cases in the respective households with active case detection of all contacts as part of improved epidemiological surveillance.

### Malaria Transmission Risk, Stratification and Mapping

Malaria transmission in Zanzibar is heterogeneous with higher malaria risk notified in Unguja island with an annual parasite incidence (API) rate, in the years 2017-2022, ranging from 2.2 (Magharibi B district in 2017) to 18.1 (Kati district in 2020) per 1000 population. The API in Pemba is remarkably lower with a minimum of 0.2 (Mkoani district 2022) to a maximum of 4.5 (Micheweni districts in 2020) per 1000 population. See table below.

Table 1: API per district per year (Source: MEEDS/IDSR)

|  |  |  | API per 1000 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Island | District |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 |
| Unguja | Kaskazini A |  | 2.8 | 4.2 | 4.8 | 7.6 | 3.3 | 1.7 |
|  | Kaskazini B |  | 3.7 | 5.2 | 4.6 | 7.2 | 3.6 | 1.8 |
|  | Kati |  | 8.8 | 9.4 | 11.9 | 18.1 | 11.6 | 5.3 |
|  | Kusini |  | 6.6 | 5.0 | 4.6 | 9.3 | 9.6 | 2.6 |
|  | Magharibi A |  | 2.2 | 3.7 | 4.8 | 6.4 | 4.1 | 1.9 |
|  | Magharibi B |  | 3.2 | 3.7 | 5.7 | 10.2 | 5.9 | 2.6 |
|  | Mjini |  | 2.9 | 4.6 | 7.4 | 16.5 | 4.4 | 1.6 |
| Pemba | Mkoani |  | 0.7 | 1.1 | 1.5 | 1.7 | 0.7 | 0.4 |
|  | Wete |  | 1.2 | 2.0 | 2.2 | 4.0 | 1.6 | 1.2 |
|  | Chakechake |  | 1.0 | 1.7 | 1.5 | 2.4 | 1.8 | 0.8 |
|  | Micheweni |  | 3.1 | 4.0 | 2.5 | 4.5 | 0.9 | 0.7 |
|  |  |  | District count by API level |  |  |  |  |  |
| API per 1000 |  |  | 2017 | 2018 | 2019 | 2020 | 2021 |  |
| <1 |  |  | 1 | - | - | - | 2 |  |
| 1-<5 |  |  | 8 | 9 | 8 | 4 | 6 |  |
| 5-<10 |  |  | 2 | 2 | 2 | 4 | 2 |  |
| 10+ |  |  | - | - | 1 | 3 | 1 |  |

Malaria is stratified according to foci, which are classified as residual, cleared and active. Comprehensive case investigation and detection is ongoing to understand the factors that contribute to repeated transmission and to halt it through targeted interventions. The former operational definition of foci was referring to the entire Shehia. In this strategic plan, the definition has changed from the Shehia to the small hamlets. In 2021 the active foci reported local cases were 296 out of 388 (76%).

Figure 4: Malaria foci classification.

The API distribution by shehia is also extremely variable with large majority of shehias reporting less than 5 cases per 1,000 population. The annual variation of endemicity is also remarkable and is summarized in the table and map below.

Table 2: Shehia count by annual level of parasite incidence (per 1000)

|  | 2017 | 2018 | 2019 | 2020 | 2021 |
| --- | --- | --- | --- | --- | --- |
| <1 | 153 | 119 | 93 | 48 | 96 |
| 1-<5 | 136 | 145 | 153 | 130 | 169 |
| 5-<10 | 59 | 77 | 74 | 85 | 67 |
| 10+ | 34 | 41 | 62 | 126 | 57 |

Figure 5: API per 1,000 population by shehia in Pemba and Unguja 2021 (source MCN)

### Current Malaria Situation In Zanzibar

The package of interventions deployed have significantly reduced malaria prevalence rates to very low over a decade; rates went down to below 1% from 2008 to date (2023). As a result of this major achievement, the ZAMEP shifted from malaria control to elimination to the extent that malaria surveillance is the nucleus of the program (ZAMEP Annual Report 2019-2020). The malaria control interventions mainly indoor house spraying and use of insecticidal treated mosquito nets together with prompt and correct treatment through the use of artemisinin combination therapy beginning in 2003/04, have proven to be efficacious malaria control strategies.

According to the ZAMEP comprehensive malaria programme review (MPR) 2022, malaria cases reported in Unguja Island have been fluctuating during the past 10 years between 500 to 1,000 annual cases. It has been noted with great concern that the number of malaria cases reported in Unguja island were constantly on the upswing from around 2,000 cases in 2012 to over 5,000 in both 2019 and 2021. However, in 2020, a malaria epidemic erupted and the cases reached slightly above 12,000. Of great note, young males between 15-29 years were disproportionally the most affected age group. This represents about ¾ of the infections compared to the females of the same age group. Older age groups maintained the same proportion of affected males and females but with a much lower incidence.

Figure 6: Malaria cases per year, by country and islands 2008-2022 (upper charts) and malaria cases per month by country (middle chart) and island (bottom chart)

### Case Classification

The establishment of malaria case notification (MCN) allowed the programme to perform case classification in order to identify where the transmission occurred. Over the past three years there has been an increase in the proportion of imported malaria cases that almost doubled from around two per every five cases in the 2020 (epidemic year) to almost four per five cases in 2022. The weekly and annual decrease of local transmission is well documented in the charts below.

Figure 7: Case classification by years and week

### Malaria Admissions and Deaths

Over the last five years the programme’s malaria case management unit has been conducting trainings and refresher trainings for health care providers at all levels of service delivery areas. These trainings are followed by supportive supervisions on a quarterly basis. The table 8 below shows a downward trend of admissions and deaths as reported by ZAMEP database.

Figure 8: Malaria admissions and deaths 2020-2022

# CHAPTER FOUR: PROGRESS MADE IN ACHIEVING 2017/18 - 2022/23 TARGETS

## OVERALL PROGRESS ON EPIDEMIOLOGICAL INDICATORS AND TARGETS

The Monitoring, Evaluation, Research and Learning Unit of ZAMEP is responsible for day-to-day programmatic monitoring of the implemented activities (outputs) and the related specific outcomes and impact. The outgoing MSP set operational indicators that were used to measure the overall impact of the malaria programme. It was noted that the programme did not reach most of the impact targets. Table 3, shows impact indicators assessing the progress towards epidemiological impact of the MSP.

Table 3: Performance of Impact Indicators

| Indicator | 2018-2019 |  | 2019-2020 |  | 2020-2021 |  | 2021-2022 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Target | Actual | Target | Actual | Target | Actual | Target | Actual |
| Reported malaria confirmed cases | 4151 | 4,869 | 3,528 | 13,611 | 9,909 | 9,290 | 2,549 | 4,849 |
| In patient malaria deaths rate (per 100,000 person per year) | 0.19 |  | 0.17 |  | 0.14 |  | 0.12 | 0.22 |
| Annual parasite incidence per 1,000 population | 2.7 | 3.0 | 2.2 | 8.3 | 1.8 | 5.3 | 1.6 | 2.9 |
| Malaria test positivity rate (%) | 1.1 | 1.2 | 1.1 | 2.6 | 0.9 | 1.5 | 0.7 | 0.3 |

Source, ZAMEP MRP Report 2020

Note: The program changed the definition of foci from village to Shehia. The target set in the strategic plan 2018/2023 was based on foci being an entire Shehia. Until March 2023, there were 216 active foci out of 388 Shehia of Zanzibar.

### Progress in MSP Morbidity and Mortality Impact Targets

The number of confirmed malaria cases recorded in 2020 was beyond 12,000 cases in both Islands compared to the subsequent years. This was due to a malaria outbreak recorded especially in Mjini Magharibi region. Across the years, imported cases have continued to rise as indicated in table 4.

On the other hand, indigenous cases as indicated above are widely spread across the districts. Kusini district in Unguja and Chakechake district for Pemba recorded the least number of confirmed cases. Case investigation is well maintained and sustained to over 85% in all districts of Zanzibar.

There has been an improvement in ensuring that all cases are investigated within 48 hours of diagnosis/notification. The main reasons for inability to investigate some of the cases were loss to follow-up due to high mobile populations and wrong household addresses and incorrect telephone numbers provided by the patients.

Table 4: Trends in Malaria Morbidity 2018/19 To 2021/22

| Year | Total number of confirmed cases | Total number of local cases (%) | Total number of cases investigated within 48 hours (%) |
| --- | --- | --- | --- |
| 2018-2019 | 4,869 | 30 | 88.5 |
| 2019-2020 | 13,611 | 56.7 | 93 |
| 2020-2021 | 9,290 | 41.4 | 96 |
| 2021-2022 | 5,356 | 20 | 92 |

Source: ZAMEP Database

Though the cases have demonstrated a reduction in 2022 local transmission still exists. As seen from the trends above, achieving malaria elimination remains a technical challenge. This therefore requires practical interventions as suggested in various fora such as MPR 2022, ZMEAC 2012, country stakeholders dialogue 2023 to allow changes and innovative approaches towards malaria elimination.

### Progress towards Entomological Impact

Although the Zanzibar NSP 2018-2023 had no entomological impact indicators, entomological activities are regularly conducted. The ZAMEP established 10 sentinel sites for vector surveillance. It is presumed that the large prevalence of An. arabiensis is probably due to a shift from more endophilic species to more opportunistic and exophilic species. The vector surveillance shall be further strengthened to comprehensively monitor entomological trends.

### Financing of Malaria Activities at Program Level

The malaria feasibility assessment conducted in 2019 indicated that malaria elimination in Zanzibar is technically feasible, though significant operational challenges will need to be overcome for malaria free status to be achieved and sustained. However, the Revolutionary Government of Zanzibar and its partners are fundamentally interested in pursuing elimination. Currently, the ZAMEP is funded by various sources including the RGoZ, PMI/USAID and GFATM. Technical assistance is also available from the research institutions and international organizations.

The GFATM and PMI financed the MSP by 56.6% and 41.6% respectively with wide variations between the allocated budget by thematic area. The MTR 2020, reported some difficulties in obtaining data on government contribution towards the malaria programme. However, significant contributions through counterpart funding, salaries of health workers, and other indirect contributions to the programme are observed on annual basis. The MTR 2020, further elaborated that RGoZ allocation from 2018/19 has been rising gradually since then. The increase in the allocation indicates the health RGoZ’s commitment to malaria elimination.

Following the financing gap (12%) of the ending MSP for the period of five years, the ZAMEP faced challenges in mobilizing additional resources to cover the identified gap and implement the planned activities. Figure 9 illustrates budget allocation and sources of funding.

Figure 9: Budget and Commitment from all Sources

Source: ZAMEP MPR 2022 Report.

## EFFECTIVENESS OF HEALTH SYSTEMS IN DELIVERING HEALTH SERVICES

### Organization of the health system

The Ministry of Health is the overall entity which guides the seamless and effective functionality of the health sector in Zanzibar through subsequent National Health Sector Strategic Plans. The current NHSSP IV (2020/21 to 2024/25) is the overarching strategy for the Zanzibar Health Sector with a vision of steering towards ensuring universal access to quality and comprehensive health and social protection services, equitable to all people in Zanzibar having a healthy population and social well-being. The HSSP IV is a key element in achieving the overall visions and development goals of Zanzibar’s Vision 2050, the Zanzibar Development Strategy as well as the Zanzibar Health Sector Policy.

The health infrastructure is distributed into primary, secondary and tertiary levels of health care services. The distribution allows good access to primary services; 95% of the population access the public or private health facility situated at less than 5km. Health facilities at this level provide preventive, treatment and care services for communicable and non-communicable diseases. At this level, health programs are being implemented in supporting targeted health interventions aimed at delivering cost effective quality primary health care services to all as defined in the essential health care package of the Ministry.

Primary level services are run by District Health Management Teams, while secondary health care services are rendered by district and regional hospitals; tertiary health services are provided by Mnazi Mmoja Hospital - a semi-autonomous institution.

The MOH has since 2017 been reviewing the performance of the health sector on a yearly basis. All departments, units, programs (ZAMEP inclusive) and management teams provide inputs for the Minister’s annual budget speech preparation to the House of Representatives. The Directorate of Planning, Policy and Research of the MoH, compiles reports into the annual performance report. The performance report is a part of on-going efforts to strengthen the planning and monitoring cycle in the Ministry.

### Malaria Services Rendered by ZAMEP

The ZAMEP is guided by the National Strategic Plan and other locally generated supporting documents (e.g. guidelines and standard operating procedures) and international publications. The primary role is to technically guide the health sector (both public and private), resource mobilization, partnership coordination, implementation and monitoring of all recommended interventions. To achieve this, at national level, the ZAMEP management collaborates with various stakeholders such as Central Medical Stores, the Health Information System, Chief Pharmacist Office, Logistic Information Management Unit, Zanzibar Health Research Unit, District and Referral Hospital.

At district, the ZAMEP collaborates with District Health Management Teams (DHMTs) for the planning and implementation of malaria activities at both health facility and community level. DHMTs have been capacitated on various interventions to technically support all health facilities in the Islands of Unguja and Pemba. District teams assist in the routine monitoring of malaria programmes activities such as national campaigns on ITNs distribution, community active case detection, indoor household spraying and others.

At Shehia level, Community Health Volunteers available in all Shehia (the lowest administrative set-up at community level), Custodian Health Committees and social groups are the most prominent traditional community-based health workers. In the previous plan, the ZAMEP interventions at this level had not factored in regular engagements of non-governmental organisations for the delivery of malaria services at community level. This oversight shall be addressed in this new strategic plan.

### Integrated Malaria Vector Management

The ZAMEP has a well-organized vector management unit with functional insectary for the monitoring insecticide resistance and other entomological indicators. The primary objective is to increase appropriate vector management measures to the population at risk of malaria to 100% by 2028. The MTR 2020 thoroughly reviewed vector management to assess the implemented vector management strategies mainly LLIN and IRS. In the past two decades, ZAMEP in collaboration with its key partners – President’s Malaria Initiative (PMI) and the Global Fund has scaled up the distribution of LLINs and IRS.

The following vector management outcome were assessed.

Long Lasting Insecticidal Nets: during the MTR 2020, it was noted that no ITNs surveys conducted during the life of National Strategic Plan. Developments on vector management indicators was captured by the Malaria Behavioural Survey 2010 and Tanzania Demographic Household Survey 2017. However, routine distribution and net replacement campaigns and distribution took place periodically. A total of 1.7 million ITN were distributed during the period between 2018 and 2021.

In this context, proportion of population that slept under an LLIN the previous night was one of the key indicators. A baseline of 47% (2017) was used. The malaria behaviour survey (MBS) of 2021 reported an increase up to 85%. Proportion of children under five who slept under an LLIN the previous night was assessed using the same year of which baseline data was 71.8% and rose up to 88% by 2020/21. Proportion of the population with access to an LLIN within their household documented 56.6% (baseline) with missing year of recording. MBS 2021 reported a significant increase of 94%.

Lastly, proportion of households with at least one LLIN for every two people was reported at 32% (MBS 2021).

Indoor Residual Spraying:  The ZAMEP shifted from blanket approach of spraying structures introduced in 2012 to focal spraying tactics in 2021 following a disease reduction at Shehia level. An assessment of this strategy indicated that percent of population protected by IRS in active foci by year was 98% (thus loosely translating that reactive IRS had a higher compliance compared to targeted or blanket spraying). As a result, the proportion of targeted households sprayed by IRS within the last 12 months was above the WHO threshold of 85%. The result is based on reactive focal IRS following entomological investigation. Additional information of IRS operations documented during the life of the strategic plan is as follows.

Figure 10: IRS Operation in Zanzibar 2017/18 to 2020/2021

| Year | Districts | Structures Sprayed | Population Protected | Insecticide |
| --- | --- | --- | --- | --- |
| 2017/2018 | Zanzibar – 8 | 67,450 | 334,715 | Pirimiphos-methyl CS |
| 2018/2019 | Zanzibar – 10 | 94,339 | 477,243 | Pirimiphos-methyl CS |
| 2019/2020 | Zanzibar – 10 | 41,231 | 499,798 | Clothianidin WG |
| 2020/2021 | Zanzibar – 10 | 46,316 | 230,708 | Clothianidin WG |

Source: ZAMEP Data base

Bio-Larviciding: It was recommended that larviciding that fight outdoor vectors may increase synergistic effect in lowering malaria cases supported with entomological surveillance with special attention to Asian malaria vector, An. stephensi. The reality on ground is that, ZAMEP identified large number of breeding sites at Shehia level with active foci. However, the larviciding is done in a very small scale; the treatment round was one per water body which is technically incorrect. This is attributed to inadequacy in funding to meet operational costs as the RGoZ is the only entity supporting this strategy.

It is worth mentioning that during the deployment of this strategy, Bio-Larviciding outcome indicators were not included hence there are no routine national framework and indicators for monitoring implementation of Bio-Larviciding. Similarly, the MPR report did not outline the effectiveness of bio-larviciding in the field due to lack of field documentation though field observations reported positive changes if breeding sites are treated as recommended by the WHO.

### Malaria Diagnosis and Treatment

The aspiration of the programme was to ensure quality assured diagnosis and appropriate case management in all health facilities and community maintained and sustained at 100% by 2023. The WHO slogan of 3Ts, (test, treat and trace) was adopted in the Zanzibar context. This was made possible due to the training of health workers and availability of malaria diagnostic commodities throughout a year.

The assessed Strategic Plan outcome target for Case Management were:

Annual blood examination rate per 100 population 28.3 in 2017 increased to 37%. The below figure illustrates.

Figure 11: Number of tests and ABER by year and location

Source: MPR 2022

Treatment: proportion of patients with confirmed malaria who received first-line antimalarial treatment according to the national policy was 100% in 2017. The results are 100% as 2022, this is attributed to the constant availability of antimalarials with no stock-outs in all health facilities.

### Procurement supply management

The continuous availability of and access to essential malaria commodities was made possible through a robust procurement, supply and logistics mechanism. The MPR report observed that the data scrutinized in 169 facilities showed no stock-outs of the essential malaria commodities.

### Malaria Surveillance and Response

The Programme purposely aimed at reinforcing malaria surveillance for elimination to actively investigate and classify all confirmed cases at 100% by 2023. In order to achieve the purpose, the programme employed key strategies including strengthening of surveillance system, improvement of data quality and strengthening of data usage and dissemination.

The programme has in its ambit a reliable and robust system for implementing surveillance system. Electronic data collection and reporting systems are in place with capabilities in prompt data entry and reporting using tablets. The following outcome indicators were assessed during the MPR 2022.

Proportion of cases investigated and classified: The baseline target was 63% (2016). In 2021/22 the achievement was 95%. This indicator was not fully achieved based on the set target due to several reasons including loss to follow up of malaria patients during the case investigation.

Proportion of foci investigated and classified: There was no baseline set for this indicator as foci investigation commenced after the development of the strategic plan. However, by 2021/22 the programme managed to identify, investigate and classify 99% of the foci especially in the malaria prominent Shehias – not the entire Island.  Based on the field experiences, the programme had to change criteria for foci investigation to suit the field context. On the other hand, the programme is missing entomological investigation and response guidelines. The review findings revealed the need to develop practical guidelines and share with the frontline workers in malaria surveillance. However, the MSP had not provided clear strategies to prevent re-introduction of malaria in the Shehia where local malaria cases have not been documented for three consecutive years.

### Malaria Advocacy

The Social Behavioural Change Communication strategy (2018-2023) provides a roadmap for advocacy activities that will support the drive of progress toward malaria elimination. The MPR noted several interventions were planned to support the SBC&CE objective. All planned activities were conducted in collaboration with DHMTs as well as Zanzibar media institutes.

The MSP clearly stated several output indicators on SBC&CE with acceptable achievements, for instance, the perception of malaria risk in the community is quite low, probably in relation to the very low burden of disease. However, this is a potential threat due to the current vulnerability to importation and re-introduction of malaria cases. This risk perception is higher in Unguja compared to Pemba. Nevertheless, the knowledge of malaria and preventive and control measures associated with it remains very high in the communities.

Figure 13: Percentage of women who reported that malaria is the most serious health problem in the community by region 2017

Source: MPR 2022

### Way Forward

Considering the findings of the MPR, several recommendations were made by thematic areas in order to strengthen and maintain programme performance. Considering that this strategic plan is a working document, it is strongly suggested to outline some of the key and practical recommendations for the implementers to take the necessary actions during the life of this plan.

Malaria Diagnosis and Treatment

- Investigate the causes of relatively low Annual blood examination rate in Pemba compared to Unguja

- Enhance and support the rehabilitation of facility infrastructure to accommodate microscope tools and ensure quality client care services

- Introduce highly sensitive tools like quantitative Polymerase Chain Reaction (qPCR) for active case detection in the community

- Develop the policy of death audit committee to provide oversight at hospital level (Public, Private and community)

- Update surveillance system to add an indicator variable on malaria deaths and PSM.

Integrated Malaria Vector Management

- ZAMEP is encouraged to ensure IRS rapid response is implemented together with other vector interventions such as larviciding

- Foci investigation should be comprehensive including both entomology and epidemiology

- There should be a budgetary increase to support focal IRS operational cost and logistics

- ZAMEP needs to revise the surveillance guidelines on malaria to enable investigation to be conducted even in a single malaria local case

- Malaria case investigation should include human behaviour that determine human and vector interaction to provide perfect target for response interventions

- Strengthening entomological surveillance even if local malaria cases is zero, targeting dominant malaria vector and anticipated new invading species such as Anopheles stephensi

- There should be a special budget to support larval source management (commodities, mapping, larvicides, monitoring and training).

- In absence of Malaria Indicator Survey findings from the field for a longer duration, ZAMEP should find an alternative approach to generate ITNs indicators.

Surveillance, Monitoring, Evaluation and Operational Research

- The MPR recommends the Programme to develop a list of operational research agenda and prioritize according to the need of the program.

- The surveillance guideline should be updated including updating the indicators to reflect the classifications which should feed into the M&E framework and the current emphasis on foci investigation and response

- The current MSR unit need to be capacitated to strengthen the M&E functions

- Foci investigation and response should be a collective effort that cuts across individual thematic units (MSR, CM, VC) at ZAMEP and need to be supported by high level of capacity in generating and interpreting surveillance data

- Coordination of the actors involved in surveillance and response activities, especially in foci investigation and its related focal response, is of paramount importance

- The programme should collaborate with other ministry of health organs such as Private Hospital Advisory Board to improve the performance private health facilities

- The programme should explore the possibility of using current introduced postal codes and registered houses number to reduce lost-to-follow up malaria cases

- The programme should continue to provide health education to general population on the importance of providing correct information for case follow-ups.

Behavioural Change Communication

- Strengthen the use of social media to reach target audiences, and increase social media budget

- Identification of risk behaviour, occupational and livelihood exposure and socio-economic vulnerability to malaria infection should be established and mitigation measures to be undertaken

- Strengthen malaria school clubs, by increasing the number of schoolteachers trained on malaria elimination key strategies, intensive monitoring and supervision of trained school teachers, distribution of IEC materials to the school clubs; the knowledge should be extended also at the level of Madras and Sunday schools

- Emphasize the use of CHV to extend interpersonal communication for malaria elimination especially in identified risk groups and occupational occasions (fishing camps, examination camps and temporary farming camps)

- Activation of community health committees to build capacity to strengthen exchange visits

- Quarterly intensive supportive supervision at Shehia level and health facilities.

Programme Management

- For better implementation of the programme, the expert group has to be established and start working appropriately as well as all technical groups should meet regularly as planned

- The programme should submit the sustainability plan to malaria stakeholders and fulfil other government requirements for it to start operation

- The programme should maintain the ZMEAC and TWGs and ensure that meetings are conducted regularly

- The programme should consider preparing clear roles and responsibilities for malaria expert group which does not contradict with malaria elimination advisory committee

- There should be specific indicators that address the outcome of the conducted meeting such as the number of proportion of recommendations that has been already implemented/cleared

- The programme to advocate for more resources from all sources including foreign institutions and private sector to move towards financial sustainability

- The set target of the malaria confirmed cases did not separate the local and imported cases, in this context the programme might has missed some useful information to make decision, the adjustment of set targets needed to separate the reported malaria cases local and imported

- There should be detailed analysis on the real cause of increased number of malaria cases for the coming MSP

- It is recommended that the rate of malaria death should be presented in line with WHO Malaria death standard.

# CHAPTER FIVE: MALARIA STRATEGIC PLAN 2024-2029

## OUTLINE TO NATIONAL MALARIA STRATEGIC PLAN 2024-2029

### Purpose of the National Malaria Strategic Plan

The whole essence of the National Malaria Strategic Plan is to offer a comprehensive technical guidance to key implementers at all levels of operation, stakeholders and development partners during the lifetime of the plan in order to achieve the set goals

### Process of Developing the Malaria Strategic Plan 2024-2029

This plan was prepared following a comprehensive Malaria Program Review, which evaluated the performance of the outgoing strategic plan 2018-2023 ending in June 2023. Prior to MPR 2022, a mid-term review was conducted in 2020. Furthermore, recommendations from the Zanzibar Malaria Elimination Advisory Committee were taken on board. The development process involved wide-ranging engagements with various key malaria stakeholders.

At Shehia level, a process of engaging Shehia leadership on behalf of the community members through Heads of Shehias representing all districts was also considered. Furthermore, administrative district officers were fully involved in the identification of operational gaps hindering achievement of the set goal of malaria elimination. Recommendations were then incorporated in this Strategic plan – 2023 to 2029.

Involvement of Civil Society Organizations and Non Health Sectors (malaria related) was also given special emphasis. Their participation in implementing various recommended interventions had already been stipulated in the existing Multisectoral Guidelines for malaria elimination. During the process of implementing this plan, a focal person for Multisectoral coordination at the Programme and relevant Ministries will be identified for better reporting and accountability.

In the spirit of sense of ownership, the leadership of ZAMEP led the process and the programme staff were fully involved in every stage of strategic plan development. Most importantly, the senior officials from the MOH were involved from the initial stages and approved the process to continue.

## VISION, MISSION AND GOAL

### Programme Vision

The vision of the programme is having a healthy population free from malaria in Zanzibar.

### Programme mission

To provide universal access to quality malaria elimination interventions through evidence-based strategies and multi-sectoral engagement.

### Goal

The Ministry of Health through the malaria programme will continue to accelerate towards malaria elimination and intensify interventions especially in Shehia with active foci and high-risk populations. The malaria program is committed to eliminate locally-acquired P. falciparum. This will require intensification and deploying to upscale of the current interventions, and also embrace the recommended activities such as proactive case detection strategies for focal screening and treatment. By 2029, Zanzibar is aiming to reach the following goal;

To accelerate elimination of local malaria transmission and preventing re-introduction

To operationalize the goal, the plan will have to establish baseline values and expected improvement in the aspects of local malaria transmission and re-introduction of malaria cases.

| Indicator | Description | Baseline (year) | Mid-term target 2026 | End-term target 2029 | Source |
| --- | --- | --- | --- | --- | --- |
| Local malaria incidence rate per 1,000 population | Number of local malaria cases detected | 0.4 per 1,000 (2022) | 0.2 per 1,000 | 0 per 1,000 | ZAMEP Surveillance database |
|  | At risk population |  |  |  |  |

## GUIDING PRINCIPLES

This strategic plan and its subsequent implementation will be guided by the following principles:

Country ownership and leadership: This strategic plan is aligned to the higher strategic directions of the country including the development goals of Zanzibar’s vision 2050, and the fourth Health Sector Strategic Plan (HSSP IV 2020/21-2024/25). The implementation of the plan will adhere to RGoZ instructions and directives of executing socio-development programmes, malaria inclusive.

Partnership and multisectoral engagement: The MoH through ZAMEP will take leadership in coordinating and engaging actors within health and non-health sectors towards malaria elimination. The plan aims at ensuring that resources and expertise are leveraged among stakeholders. This should cover both public and private sectors.

Evidence-based and adaptive management approach: This plan will prioritize globally proven strategies to respond to local malaria epidemiology. Locally generated data will be continuously used to inform decision making towards appropriate interventions.

Accountability for results: To achieve the goal of this plan, ZAMEP and stakeholders at all levels are expected to accountably deliver and/or support interventions to intended beneficiaries in an efficient and cost-effective approach.

Community-centered response: The plan intends to ensure communities are meaningfully engaged in designing, implementation, monitoring and evaluation of the malaria response activities at all levels. This principle encourages communities to participate in elimination of local transmission and preventing re-introduction.

Equity in access to quality malaria services: The plan considers equity-motivated interventions that seek to ensure allocation of resources preferentially based on malaria epidemiology.

Leaving No One behind: Everyone regardless of ethnicity, age, sex, disability and socioeconomic status should be able to receive deserved interventions timely.

Gender Sensitivity: Gender issues will continue being mainstreamed and strengthened in the planning and implementation of the malaria programme.

Sustainability: Towards malaria elimination, the RGoZ will ensure recommended malaria interventions are fully integrated into the health system with adequate resources. To sustain the malaria gains, the ZAMEP will operationalize the existing financial sustainability plan as a tool for resource mobilization. This plan advocates for adequate domestic resources.

### Strategic Focus

Essentially, the MSP 2024-2029 will continue implementing the same strategic machineries as per the previous strategic plan 2018/2023. The current strategies are found to be very effective and accepted by the general population. However, the planned activities will strictly focus on the MPR 2022 recommendations and other findings collected from different sources. Therefore, the National Malaria Strategic Plan 2024-2029 entails the strategic areas outlined below.

- Integrated Malaria Vector management

- Malaria Diagnosis, Treatment and Preventive Therapies

- Malaria Surveillance and Response

- Programme Monitoring and Evaluation

- Logistic Management System

- Social behaviour change and community engagement

- Leadership, Partnership and Resource Mobilization

### Strategic Directions for 2024-2029

The following strategic directions will be employed throughout the lifetime of this strategic plan. Technical modification of the strategic directions will be made (should the need be) based on the review findings of mid-term review of this plan.

- Going to zero local malaria transmission

The ZAMEP needs to strengthen and integrate entomological and epidemiological surveillance and response for local cases. Epidemiological foci identification, investigation and response (focal RDA/ MDA/ IRS/ LSM) are cardinal in this aspect and by doing so, local transmission is expected to be interrupted.

- Control imported malaria cases and prevent re-introduction

Since the importation of malaria cases from outside the Island is practically unfeasible, this strategy is aiming to further strengthen the detection of imported cases and by treating them and providing radical cure and clearance of parasitaemia, to mitigate the risk of re-introduction. Passive case detection in operational health facilities need to be associated with other initiatives to detect imported, especially asymptomatic cases.

- Universal access to essential malaria services

Quality curative and preventive services shall be delivered when and where needed. Prompt diagnosis of malaria accompanied by correct and effective treatment will be ensured throughout the implementation of this MSP in all health care facilities and, when applicable, communities. Personal protection of the entire population through the use of ITN will be enhanced.

- Address risk factors of malaria elimination in special situation

The ZAMEP in collaboration with the district implementers shall map and reach populations with identified occupational, behavioural and socio-economic risks to institute malaria elimination measures. Other exceptional situations, such as incumbent malaria and other emerging diseases outbreaks, need to be monitored and appropriate response to be carried out in an efficient and timely manner. The current evidence of higher incidence of malaria in urbanized areas needs to be further investigated and addressed with effective surveillance and response mechanisms.

- Strengthen multi-sectorial engagement

Coordinated efforts through the involvement of non-health sectors in the implementation of this plan is critical. The existing multisectoral guidelines developed in 2021 need to be fully operational. Therefore, it is high time for the ZAMEP to implement a common multisectoral action plan with designation of a focal person within the program to manage the linkages between the ZAMEP and selected ministries for this purpose.

## STRATEGY OUTLINE

### Core Strategic Areas: Strategic and Specific Objectives

| Strategy Outline | Description and Target | Strategic Approach/Interventions |
| --- | --- | --- |
| Core Strategic Area 1 | Integrated Malaria Vector management |  |
| Strategic Objective 1 | To protect all population with recommended vector management interventions according to epidemiological and ecological setting by 2029, to interrupt malaria transmission | 1.1. Distributing ITNs to ensure Universal Access |
|  |  | 1.2. Performing reactive focal Indoor Residual Spraying |
|  |  | 1.3. Expanding Larval Source Management by using bio-larvicides |
|  |  | 1.4. Promoting the use of topical repellents |
|  |  | 1.5. Mitigating Insecticide resistance to malaria vectors |
|  |  | 1.6. Introducing new emerging vector management tools when available |
| Core Strategic Area 2 | Malaria Diagnosis, Treatment And Preventive Therapy |  |
| Strategic Objective 2.1 | By 2029, to test all symptomatic suspected malaria infections in health facilities through passive case detection and to test at least 75% of eligible population at risk in the communities through active case detection | 2.1.1 Testing suspected malaria cases attending health facilities by using mRDT for antigen detection and malaria microscopy for malaria parasites examination |
|  |  | 2.1.2 Testing eligible population at risk in the communities by using mRDT for antigen detection for malaria parasites examination |
|  |  | 2.1.3. Providing high quality malaria diagnostic services |
| Strategic Objective 2.2 | To prevent occurrence of malaria related deaths by providing appropriate management of uncomplicated and severe malaria to 100% of confirmed malaria cases by 2029 | 2.2.1 Treating confirmed malaria cases with recommended efficacious anti – malaria therapies |
|  |  | 2.2.2 Maintaining high quality malaria management services |
|  |  | 2.2.3 Providing effective pre-referral and emergency management of severe malaria conditions |
|  |  | 2.2.4. Providing antimalarial preventive therapies to targeted high risk population and identified transmission foci to decrease morbidity |
| Core Strategic Area 3 | Malaria Surveillance and Response |  |
| Strategic Objective 3. | To intensify malaria surveillance and response in all shehias by 2029, to enhance the progress towards malaria elimination | 3.1 Reinforcing response to detected local malaria transmission foci through integrated focal entomological and epidemiological surveillance to interrupt transmission |
|  |  | 3.2. Strengthening surveillance and response to detected imported malaria cases to prevent re-introduction of transmission |
|  |  | 3.3. Operationalizing an effective malaria epidemic preparedness and control plan |
|  |  | 3.4. Expanding efficient malaria entomological surveillance, including molecular analysis, for systematic collection and use of essential vector population dynamics |
|  |  | 3.5 Introducing parasitological surveillance by using recommended molecular analysis |

### Supportive Strategic Areas, Strategic and Specific Objectives

| Strategy Outline | Description and Target | Strategic Approach/Interventions |
| --- | --- | --- |
| Supportive Strategic Area 4 | Monitoring, Evaluation, Research and Learning |  |
| Strategic Objective 4 | To improve programmatic accountability through monitoring and evaluation of all strategic objectives and interventions targets, by 2029 | 4.1. Strengthening comprehensive malaria strategic information system through appropriate data collection and reporting tools, efficient data repository, and smart data analysis and visualization |
|  |  | 4.2. Establishing proper mechanism for programmatic M&E through enhanced dissemination of data for operational and programmatic use |
|  |  | 4.3. Monitoring implementation of the strategic plan towards the achievements of set targets |
|  |  | 4.4. Conducting priority operational researches for evidence based decision making |
|  |  | 4.5. Improve data quality through continuous data audit and verification |
| Supportive Strategic Area 5 | Logistic Management System |  |
| Strategic Objective 5 | To ensure uninterrupted supply of quality and safe malaria commodities and supplies, to avail zero stock-outs at service delivery points by 2029 | 5.1. Providing adequate quantification process for all malaria commodities according to plan |
|  |  | 5.2. Maintaining an efficient procurement and supply management system |
|  |  | 5.3. Strengthening a well-organized logistics data systems to support inventory of malaria commodities |
|  |  | 5.4. Ensuring continuous quality assurance and safety vigilance of malaria commodities |
| Supportive Strategic Area 6 | Social behaviour change and community engagement |  |
| Strategic Objective 6. | To promote positive malaria behaviors through evidence-based SBC&CE strategies by ensuring that 100% of the targeted population is practicing positive malaria behaviours by 2029 | 6.1. Designing and developing using behavioral science innovative approaches |
|  |  | 6.2. Deploying community based participatory approaches to address malaria behavioral determinants and social norms |
|  |  | 6.3. Leveraging multimedia channels to promote positive malaria behaviors |
|  |  | 6.4. Advocating community, multisectoral and private sector engagement for malaria elimination |
| Supportive Strategic Area 7 | Leadership, Partnership and Resource mobilization |  |
| Strategic Objective 7.1 | To enhance effective, partnership and multisectoral engagement towards malaria elimination by assuring that 100% of annual planned activities are implemented by 2029 from the 80% level in 2022 | 7.1.1. Providing effective leadership and governance for the implementation of malaria elimination interventions at all levels |
|  |  | 7.1.2. Promoting effective multi-sectoral engagement and public-private partnership to achieve malaria elimination |
|  |  | 7.1.3. Conducting cross-border initiatives to mitigate the impact of malaria importation and reintroduction |
| Strategic Objective 7.2 | To enhance sustainable financing and accountability for the implementation of the strategic plan by increasing domestic financing up to 50% of the total malaria funding needs by 2029, from the 6% level in 2022 | 7.2.1. Enhancing sustainable financing for malaria elimination interventions |
|  |  | 7.2.2. Mobilizing adequate resources (human and financial) to support the efficient implementation of the strategic plan |
|  |  | 7.2.3. Advocating for increased malaria allocation in the overall health and other sectoral budgets |
|  |  | 7.2.4. Optimizing functional support and competency to create enabling working environment for sustainable implementation of malaria elimination strategies |
|  |  | 7.2.5. Supporting implementation of the priority areas identified in the RSSH need assessment report of 2023. |

## CORE STRATEGIC AREA 1: INTEGRATED MALARIA VECTOR MANAGEMENT

### Strategic Objective 1

To protect all population with recommended vector management interventions according to epidemiological and ecological setting by 2029, to interrupt malaria transmission

### Integrated Malaria Vector management Strategic Approaches/Interventions

Approach/Intervention 1.1: Distributing ITNs to ensure Universal Access

The proportion of persons with access to an insecticide-treated net (ITN) will be increased from 79% in 2022 to 90% by 2029

Based on the Malaria Behavioural Survey 2021 the ITNs ownership reported to be 94% while the utilization is 85%. However, Malaria Indicator Survey 2022 reported different ownership and utilization, with a coverage of 79% and 66% respectively. Essentially, both surveys show a great progress on the ITNs indicators that need to be maintained to provide optimal malaria prevention.

Insecticide Treated Nets will continue to be distributed free of charge through Reproductive and Child Health clinics in order to keep up ITN coverage and utilization country wide. Additionally, in 2024, the program is planning to conduct mass replacement distribution of LLINs across the Island. During this strategic plan a third channel will be added to establish at community level ITN delivery a mechanism to cover the identified high risk population.

Regular supervision and monitoring to the ANC and during the mass distribution to assess the efficiency of distribution mechanisms, storage and proper record keeping. Durability monitoring of ITNs will also be conducted by the entomological team as deemed necessary.

Special efforts will be put in place to assure ITNs access to specific vulnerable groups with high risk of contracting malaria infections such as army and police barracks, sober-houses, school and fishing camps, and residents living very close to rice irrigation farms. ITN distribution is not meant to be a foci response mechanism but shall compliment the foci response exercise – in Shehia continuously demonstrating high incidence of of malaria cases – as a preemptive measure. Detailed activities and timeline for all strategic areas are found in the implementation plan.

Approach/Intervention 1.2: Performing reactive focal Indoor Residual Spraying

The number of active foci receiving reactive focal IRS will be increased from 23% in 2022 to 100% by 2029

Reactive Indoor residual spraying will be performed in active malaria foci with the indigenous reported case and cover the area of a 0.05km (50mts) – 0.1 km (100m) radius from the index household (foci). The entomological survey regarding vector species composition, behaviour and mosquito breeding habitats characterization will be integral components during the focal investigation. However, adult mosquito collection will not determine the IRS decision but would rather be complementary to understanding the predominant malaria vectors and their co-existing species. The investigation and response will be within a week following case notification using a Chinese approach of 1 – 3- 7. Adult mosquito collection will only be conducted at the foci with the local transmission situated at least five kilometres from the established entomological sentinel sites or investigated location (foci).

A second targeted IRS option will be implemented, if resources will be available, to reduce receptivity in suitable operational and epidemiological areas. This IRS option will target a larger number of structures and a larger geographical area and it might be used to  mitigate/respond to seasonal malaria transmission.

Environmental compliance is a pre-requisite for IRS to ensure the safety of the environment, human and biodiversity. Refresher training, monitoring and field supervision will be a package to maximize the quality and effectiveness of the operation. Assessment of the IRS quality will be done immediately after spraying followed by periodic insecticide decay rate monitoring when the need arises.

Approach/Intervention 1.3: Expanding Larval Source Management by using bio-larvicides

The number of treated breeding habitats in Shehias with active transmission foci through LSM by using Bio-larvicides will be expanded from 20% in 2022 to 100% by 2029

Larval Source Management is a supplementary strategy to ITNs and indoor residual spraying.

ZAMEP has been conducting focal larviciding using biological larvicides in active foci. However, it hasn’t been done systematically to achieve meaningful results. In this regard, ZAMEP has planned to undertake an operational study to ascertain the effectiveness regarding local case reduction, vector density and mosquito immature stages.The LSM, larviciding in particular, will be conducted to all mosquito breeding sites in Shehia identified with active foci.  Mapping of mosquito breeding sites, characterization, counting and anopheles’ larval status is a pre-requisite for larval source management. Biological larvicides will be used for larviciding through a community-based approach with quantitative evaluation of immature stages and adult mosquito collection in selected sites/shehia. CORPS will perform a reasonable number of spray rounds of larviciding per breeding site, according to status, dimension, productivity, seasonality, to ensure the immature mosquito stages are cleared. Different approaches will be used: a) reactive larviciding after notification and investigation of transmission foci, b) universal perennial larviciding in the urbanized areas of Mjini-Magharibi region where breeding habitats are expected to be fixed, findable and few (FFF), and c) targeted larviciding in selected suitable operational, ecological and epidemiological areas. crash training programme for community and district implementers covering the essential components of larviciding will be organized. Data collection, entry, data storage and monitoring tools will be deployed to evaluate the performance and effectiveness of the program.

During the implementation of this strategic plan it will be further explored and scaled up the use of advanced technological solutions, such as drone for both mapping and larvicidal operations.

Other larval source environmental management measures such as bush clearance, earth filling and proper refuse disposal around home yards will be encouraged at community levels and other relevant authorities. Municipal authorities need to be completely aligned with the scope and the aims of environmental management and prioritize it as the most vital intervention to fight malaria in urbanized areas.

Approach/Intervention 1.4: Promoting the use of topical repellents

Worldwide, it has been observed that significant proportion of malaria vectors bite outdoors meaning that ITNs and IRS may be less effective for human protection as they mainly target mosquitos that rest and feed on human hosts indoors. In these situations, the use of topical insect repellents may reduce outdoor biting and eventual morbidity from malaria. This approach will be a complementary and not a substitute to ITNs and IRS. The target population will include the security guards, hospital staff, camping students and young adults who spend much time outdoors due to their nature of work or for social gatherings during mosquito biting hours (18.00 – 06.00hrs).

There is yet available definitive evidence on the impact of topical repellents for malaria control at the community level. Nevertheless, to achieve meaningful impact, topical repellents may require absolute individual compliance. In the existing context, social behavioural change communication and advocacy activities will be intensified alongside the promotion of topical repellents to avoid compromising the deployment and use of other primary and supplementary interventions while collecting data through programmatic surveys and/or operational research to inform and guide subsequent deployment and policy consideration.

The program using a multi-sectorial approach will hence develop an intensive advocacy program on the use of repellent and will also explore the opportunity for the subsidy of these products.

Approach/Intervention 1.5: Mitigating Insecticide resistance to malaria vectors

The mitigation of insecticide resistance to malaria vectors which is currently at 100% will be maintained and sustained throughout the lifespan of the MSP (2024-2029)

The development of insecticide resistance in malaria vectors is common, widespread and mostly inevitable. In this vein, long-term efficacy of insecticides is critical for successful and sustainability of public health interventions. Therefore, insecticide resistance management practices will be implemented in order to delay resistance and preserve the efficacy of insecticides within the programme. The main strategies will involve two years rotation of insecticide class with long residual effect and integrated vector approach.

Approach/Intervention 1.6: Introducing new emerging vector management tools when available

In addition to above mentioned strategic objectives, there are several new innovations which aim to close gaps in anti-malaria efforts by targeting the mosquitoes that spread the disease. These include; a) Attractive targeted sugar baits. (ATSBs); b) Spatial repellents; c) Improved nets; d) Endectocides; e) Gene drive: changing mosquito DNA.; and f) ivermectin for livestock

Many of these tools are still being assessed regarding the efficacy, accessibility, applicability, toxicity to human and environment. The program is waiting for the WHO guidance on its deployment.

## CORE STRATEGIC AREA 2: MALARIA DIAGNOSIS, TREATMENT AND PREVENTIVE THERAPIES

### Strategic Objective 2.1:

By 2029, to test all symptomatic suspected malaria infections in health facilities through passive case detection and to test at least 75% of eligible population at risk in the communities through active case detection

### Malaria Diagnosis Strategic Approaches/Interventions

Approach/Intervention 2.1.1: Testing suspected malaria cases attending health facilities by using mRDT for antigen detection and malaria microscopy for malaria parasites examination

The proportion of suspected malaria cases that receive a parasitological test at all health facilities (public and private) which is currently at 100% level will be maintained and sustained throughout the lifespan of the MSP (2024-2029)

Malaria case management services will continue to be provided in all health facilities and communities as planned. The detection of malaria infection will base on blood examination either by microscopy or mRDT.

Malaria diagnosis for confirmation before treatment will be continued to be offered in all health facilities to attain effective malaria case management services.

Microscopy services have the advantage of patient follow-up, gametocytes detection, speciation, and determination of parasite density and therefore in this plan, the aim is to increase the microscope service from 96 to 110 health facilities in Unguja and Pemba.

Training of health workers on the proper use diagnostic tools, procurement of malaria diagnosis commodities, and development of SOPs will be given special emphasis and shall be expanded to cater for newly recruited health workers following the construction of 11 district hospitals in Zanzibar. The programme will continue ensuring that laboratory commodities are procured, stored, and distributed to all health facilities.

Approach/Intervention 2.1.2: Testing eligible population at risk in the communities by using mRDT for antigen detection for malaria parasites examination

The proportion of eligible population at community level which is currently undetermined will be raised to at least 75% at the end of the MSP (2029)

Malaria testing services will continue to be provided in all communities as planned. The detection of malaria infection at community level will base on mRDT.

In addition, for epidemiological investigations, highly sensitive diagnostic methods including highly sensitive mRDT and PCR technique will be introduced at the ZAMEP in order to identify the low density and undetectable parasitaemia by using conventional techniques.

Approach/Intervention 2.1.3: Providing high quality malaria diagnostic services

The supervision of quality assurance and quality control (QA/QC) in all health facilities which is currently at 100% level will be maintained and sustained throughout the lifespan of the MSP (2024-2029)

In this strategic plan 2024-2029, the diagnostic unit will expand the malaria microscopic services to all public and private health facilities to 50%, compared to 20% of the previous strategic plan 2018-2023. Furthermore, re-examination of blood slides shall be strengthened to ensure the quality of services in accordance with the diagnosis and treatment guidelines with an emphasis on confirmatory diagnosis for all age groups.

Quality control services of mRDTs will be 100% upheld in all public and private health facilities and communities. An innovative, district-based malaria test quality management scheme to monitor quality mRDT performances will be maintained. Based on the second ZMEAC 2019 recommendations, it was recommended to establish a malaria profile with detection, speciation, and quantification of malaria parasites at national level. In this context, the ZAMEP will scale up a collection of mRDT positives to be confirmed by microscopy from the current 29 to 52 health facilities to cater for all of the 11 districts of Unguja and Pemba during the five years of the implementation. The ZAMEP will collaborate with DHMTs to select one or two laboratories in each district being an examination point (first reader) in a specified district and ZAMEP training laboratory as a second reader.

The accreditation and certification scheme for the laboratory staff malaria microscopists will be strengthened in collaboration with the technical partners including capacity building of staff with regards to the aspect of accreditation of malaria microscopy competence basis at AMREF, Nairobi – Kenya. This in turn will enable the ZAMEP to have competent national and international malaria microscope facilitators and validators who are key for monitoring malaria diagnosis quality management.

Participation by all malaria laboratories in external quality assessment (EQA) will be important to provide an external unbiased evaluation of laboratory performance. Regular trainings, assessments, and quality controls will be done to ensure a high standard of microscopy service is maintained.

### Strategic Objective 2.2

To prevent occurrence of malaria related deaths by providing appropriate management of uncomplicated and severe malaria to 100% of confirmed malaria cases and eligible population at risk by 2029

### Treatment and Preventive Therapies Approach/Intervention

The treatment of confirmed malaria cases that receive recommended efficacious anti – malaria therapies which is currently at 100% will be maintained and sustained throughout MSP life span (2024-2029)

Approach/Intervention 2.2.1: Treating confirmed malaria cases with recommended efficacious anti – malaria therapies

The supply chain of antimalarial commodities will be ensured following a comprehensive quantification, forecasting, timely procurement, good storage and distribution to all public health facilities. The malaria diagnosis and treatment guidelines recommended ACT and primaquine for the treatment of uncomplicated malaria shall continue to be used. Therapeutic efficacy testing, or alternative resistance marker monitoring, shall be conducted to monitor the efficacy of first line treatment. Collaboration with mainland should be emphasized.

However, the current ZAMEP guidelines for malaria diagnosis and treatment, developed in 2018, haven’t yet included the recommendations from WHO guidelines, March 2023. Hence, they shall be revised to align to global malaria policy. The program shall also develop case management job aids including pocket size guidelines and posters for clinicians and other health providers for quick references. Documents shall be printed and distributed to both public and private health facilities and also at community level.

To ensure the provision of quality case management services the programme, in collaboration with district MSDQI supervisory teams, shall continue on quarterly basis to conduct monitoring and supervision using Electronic Data System (EDS) at all point of care in order to support health facilities to provide quality case management services.

Approach/Intervention 2.2.2: Maintaining high quality malaria management services

Routine assessment of antimalarial through post marketing surveillance will be conducted in collaboration with the Zanzibar Food Drug Agency to ensure that the antimalarials circulating in the market remain efficacious in order to avert treatment failure and drug resistance.

Approach/Intervention 2.2.3: Providing effective pre-referral and emergency management of severe malaria conditions

Injectable artesunate for pre-referral and management of severe malaria conditions will be used at all levels of health care delivery in both public and private health facilities. Management of severe malaria at primary health facilities and at hospital level shall continue to be strengthened. Above all, the ZAMEP shall continue to ensure the availability of pre-referral anti-malarial drugs and essential supplies required for this intervention.

Approach/Intervention 2.2.4: Providing antimalarial preventive therapies to targeted high risk population and identified transmission foci to decrease morbidity

In response to increased malaria cases in a defined geographical areas/villages, Alternative ACT, as recommended by malaria diagnosis and treatment guidelines, shall be used for reactive focal mass drug administration (rfMDA). This will be done by district teams under the guidance of ZAMEP in close collaboration with relevant key stakeholders (CHVs and the communities at large) after the identification of population at risk. These include businessmen, fishermen, seasonal laborers, workforce in large civil construction projects, students and military recruits.

Prior to undertaking this intervention; protocols, SOPs and training packages will be revised or newly developed. Upon successful completion of the deployment of this activity, post rfMDA survey will be conducted to assess the effectiveness of the intervention as well as the safety of medicine for the people who participated in the exercise.

## CORE STRATEGIC AREA 3: MALARIA SURVEILLANCE AND RESPONSE

### Strategic Objective 3

To intensify malaria surveillance and response in all shehias by 2029, to enhance the progress towards malaria elimination

### MSR Strategic Approaches/Interventions

Approach/Intervention 3.1: Reinforcing response to detected local malaria transmission foci through integrated focal entomological and epidemiological surveillance to interrupt transmission

The timeliness of active malaria transmission foci investigated and responded within one week of notification will be increased from 16% in 2022 to 100% by 2029

The WHO through its Global Technical Strategy for Malaria (2016-2030) emphasizes the embedment and enhancement of malaria surveillance as fundamental to both malaria control and elimination. Over ten years ago, following a decline of malaria prevalence to less than one percent, the ZAMEP started case based surveillance system. The foci investigation and response mechanism to stop local transmission is well described in the Conceptual Framework for Malaria Elimination in Zanzibar. In this strategic plan, several activities related to the above will be implemented as outlined in the implementation plan.

Approach/Intervention 3.2: Strengthening surveillance and response to detected imported malaria cases to prevent re-introduction of transmission

The number of malaria cases investigated and classified will be maintained and sustained at 100% level throughout the lifespan of the MSP (2024-2029)

The program continues with its long-term goal of achieving zero local malaria cases by 2029 and therefore efforts of strengthening its surveillance system to prevent re-introduction of transmission will highly be prioritized and enhanced. This will be implemented through establishing outreach programs for malaria high risk mobile population and establishing cross district /regional collaboration. The case investigation and response interventions to mitigate importation of new cases are well described in the Conceptual Framework for Malaria Elimination in Zanzibar.

MSPApproach/Intervention 3.3: Operationalizing an effective malaria epidemic preparedness and control plan

Timely verification, investigation and response of malaria epidemics according to the standard operating procedures will be maintained at 100% level throughout the life of the MSP 2013-2029

The main thrust of malaria epidemic preparedness and response is to reduce morbidity and mortality associated with malaria epidemics among the affected populations. This is achieved through early detection of epidemics and immediate implementation of control and preventive measures. The program will continue to use its surveillance system to forecast, detect and respond with available malaria interventions. The interventions to mitigate abnormal malaria incidence in defines areas and conditions (outbreaks, urban malaria and seasonal transmission) are well described in the Conceptual Framework for Malaria Elimination in Zanzibar.

Epidemic preparedness will be undertaken at all levels of the health system.

Table 5: Epidemic Preparedness Roles by Level

| National level | District level | Health facility level |
| --- | --- | --- |
| - Use long range forecasting (information) for preparedness in epidemic-prone areas - Coordinate and ensure inter-sectoral collaboration - Strengthen the capacity of health workers to analyze and verify data - Ensure that emergency stocks of medicines are available and can be transported to the epidemic area - Develop standard operating procedure for epidemic preparedness - Support DRTs to conduct malaria epidemic response. | - Compile data and establish or update thresholds - Conduct entomological assessment, correlate epidemiological data with other relevant indicators, such as meteorological data, population movement or socioeconomic activities | - Conduct simple analysis and graphing of weekly data, including notification to the district management team - Conduct quick verification with either microscopy or RDTs. |

MSPApproach/Intervention 3.4: Expanding efficient malaria entomological surveillance, including molecular analysis, for systematic collection and use of essential vector population dynamics

Sentinel sites collecting entomological parameters for malaria elimination will be expanded from 10 in 2022 to 13 sites by 2024

Vector surveillance will be maintained at sentinel sites to evaluate the impact of vector management interventions including IRS and ITNs. In an effort to strengthen the surveillance, sites will be expanded from 10 to 13 sites to cater for Anopheles stephensi monitoring. In addition to entomological monitoring sites, focal investigation will also be conducted to complement malaria vector information in shehia with active malaria transmission.

Anopheles stephensi will be monitored in two sites, Stone town in Unguja and Wete town in Pemba. Unlike other African malaria vectors that are often sampled using adult collection methods, larval surveillance is the best tool for An. Stephensi. Larvae and pupae of Anopheles will be dipped from potential larval breeding habitats including man-made water containers, freshwater pools, stream margins, discarded tires, plastic containers, flowerpots and irrigation ditches. Water storage containers used such as metal and plastic tanks, cisterns, barrels and plastic sheets will also be searched for the presence of larvae and pupae. This exercise will enable the programme to come up with recommendations on the best strategies for Anopheles stephensi control.

A functional digitalized solution for data collection, repository system and visualization will be completely developed and integrated into the malaria surveillance and response information system.

Human behaviour data through observation will be collected to understand the time and man/vector interaction to inform the correct interventions, timing and where to intervene. Mosquito larval habitats and larval density will be characterized once per month per site in routine sentinel sites regarding size, larval status, density and vegetation/ site to supplement entomological information with attention to new invasive species, An stephensi and co-existing vectors.

Insecticide resistance of malaria vectors will be done at 11 sentinel sites at least once a year to maintain IRS programme efficacy and assess the susceptibility of local vectors against common insecticides, thus guiding the IRS campaign on the kind of insecticides to be deployed.

This MSP envisages to expand efficient malaria entomological surveillance, including molecular analysis, for systematic collection and use of essential vector population dynamics by way of intensifying malaria molecular surveillance (MMS) such as vector speciation, resistance marker analysis and determination of feeding preference of the malaria vector.

The generated molecular information will be used by the ZAMEP to develop targeted vector management strategies, such as proper selection of insecticide-treated bed nets, LSM and indoor residual spraying and also providing alarming information if there is any biological threat to malaria elimination like presence of Anopheles stephensi.

Approach/Intervention 3.5: Introducing parasitological surveillance by using recommended molecular analysis

Parasitological molecular and genomics parameters for malaria elimination will be introduced in 2024 and will be fully operational at the end of phase 1 in 2026

To complement above mentioned strategies, molecular parasitology shall be regularly used for confirming the species of malaria parasites after the diagnosis has been established by either smear microscopy or mRDT. The most common method is the PCR, which amplifies the parasite's DNA, making it easier to detect. PCR-based tests are more sensitive and specific than traditional microscopy, which can be time-consuming and require skilled personnel.

At program level, molecular parasitology shall be used to identify drug-resistant strains of the malaria parasites, during the therapeutic efficacy studies of antimalarial to inform treatment decisions. Monitoring the prevalence of the parasite with the HRPT2/3 gene deletion, which makes them undetectable using conventional mRDT. The MMS will provide critical information to the malaria programme, allowing them to begin planning for the potential alternative for routine mRDT. If the prevalence of false negative RDTs due to pfhrp2 deletion is ≥5% among symptomatic patients, the WHO recommends switching to an RDT that is not solely based on HRP2 for P. falciparum detection (e.g. pf-pLDH).

MMS will also facilitate determination of malaria cases distribution patterns by identifying specific/respective strains of the malaria parasite, which will assist in knowing whether a particular outbreak is due to local transmission or imported malaria cases. Overall, malaria molecular technology will play a crucial role in malaria elimination efforts, by improving diagnosis, treatment, and prevention strategies.

## SUPPORTIVE STRATEGIC AREA 4: MONITORING, EVALUATION, RESEARCH AND LEARNING

Strategic Objective 4

To improve programmatic accountability through monitoring and evaluation of all strategic objectives and interventions targets, by 2029

### M&E Objectives

The proportion of outcome and output indicators achieved according to set MSP targets will be increased from 75% in 2022 to 100% by 2029.

Approach/Intervention 4.1: Strengthening comprehensive malaria strategic information system (MSIS) through appropriate data collection and reporting tools, efficient data repository, and smart data analysis and visualization.

A well-functioning MSIS at the ZAMEP, will ensure storage, organization and integration of malaria data collected through relevant data collection systems. Through this approach, ZAMEP malaria composite electronic database (repository) will be designed to systematically organize and integrate malaria related data collected inside and outside routine information system. The integration will support the production (availability and accessibility), smart data analysis, and visualization of comprehensive reliable evidence-based malaria information from reliable sources.

Approach/Intervention 4.2: Establishing proper mechanism for programmatic M&E through enhanced dissemination of data for operational and programmatic use

Monitoring and evaluation is a powerful management tool that can be used by the program for tracking progress towards the outcome and impact of malaria interventions and thus improve the effectiveness of activities implementation. It is in line with this that all existing monitoring tools under the ZAMEP will be reviewed and deployed by 2025 in order to attain a proper mechanism for programmatic assessment and hence it will be cardinal that M&E operates at its maximum potential..

Approach/Intervention 4.3: Monitoring implementation of the strategic plan towards the achievements of set targets

A detailed monitoring and implementation plan will be developed in line with the MSP, this plan will be key for the monitoring of the implementation of the planned activities by ZAMEP.

Approach/Intervention 4.4: Conducting priority operational researches for evidence-based decision making

In collaboration with the technical implementing partners, ZAMEP will prepare a research agenda for operational research highlighting priority topics which will be useful to generate evidence-based information for programmatic decision-making. It is against this background that, the ZAMEP will establish a systematic innovative system to ensure implementation and operational research are conducted and results are shared through the existing structures and used to inform programme activities.

Approach/Intervention 4.5: Improve data quality through continuous data audit and verification

Malaria elimination efforts demand high quality data, to ensure that the data used by the stakeholders and program decision making are accurate, reliable and of high integrity. This will be achieved by conducting verification of the quality of programme reported data for key indicators and assessing the ability of ZAMEP systems to effectively collect and report quality data.

## SUPPORTIVE STRATEGIC AREA 5: MALARIA LOGISTIC MANAGEMENT SYSTEM

### Strategic Objective 5

To ensure uninterrupted supply of quality and safe malaria commodities and supplies to avail Zero stock-outs at service delivery points by 2029

### MLMS Strategic Approaches/Interventions

It is anticipated that during the implementation of this MSP, all essential quality assured commodities will be adequately quantified, timely procured, stored, supplied and accounted for up to delivery point.

Approach/Intervention 5.1: Providing adequate quantification process for all malaria commodities according to plan

This is an important component of the programme that links information on services delivery and commodities from the national to facility level. Quantification for all the required commodities shall be done jointly with Central Medical Store, Logistics Management Unit and the Office of Chief Pharmacist. Technical assistance will be sought from the relevant partners supporting logistics management system in the ministry of health.

Approach/Intervention 5.2: Maintaining an efficient procurement and supply management system.

In malaria elimination settings, zero tolerance for stock-outs of antimalarials and accompanied supplies is of essence. In this regard, the programme shall strive to ensure availability of products for routine use and other eventualities such as epidemic outbreaks. The programme shall continue with the existing integrated supply chain system which is a seamless linkage that connects demand and supply throughout the supply chain to in order to obtain maximum benefit.

Approach/Intervention 5.3: Strengthening logistics data system to support inventory of malaria commodities.

The primary purpose of the logistics management data system is to manage the logistics by ensuring a smooth operation of supply chain whereby the data is generated for monitoring key indicators of health system performance. The programme shall therefore endeavor to continuously invest in the national logistics management and electronic logistics management information system thus resulting into better data use.

Approach/Intervention 5.4: Ensuring continuous quality assurance and safety vigilance of malaria commodities.

The aim of the QA programme is to ensure that the results obtained are accurate, reliable and reproducible. This is an outcome of pre-analytical, analytical and post-analytical procedures to all commodities associated with malaria case management. Strong logistic management performance is a determinant of national performance in fighting against the elimination of malaria. Effective case management for malaria requires that quality products be available and used appropriately in the correct formulations, amounts, and appropriate regimens (dose, frequency, duration). In line with this, the program closely works with Zanzibar Food Drug Agency to ensure quality and safety is maintained.

The programme shall also continue to strengthen the aspect of logistics management with the aim of ensuring that resources are available when and where needed (this consists of order processing, warehousing, and transportation).

## SUPPORTIVE STRATEGIC AREA 6: SOCIAL BEHAVIOUR CHANGE AND COMMUNITY ENGAGEMENT

### Strategic Approach 6

To promote positive malaria behaviors through evidence-based SBC&CE strategies by ensuring that 100% of the targeted population is practicing positive malaria behaviours by 2029

### SBC&CE Strategic Approaches/Interventions

Approach/Intervention 6.1: To design and develop interventions using behavioral science approaches by end of 2025

It is anticipated that by the end of 2025 behavioral science approaches will be used to design and develop interventions

The concept of utilizing behavioral sciences to address challenges for malaria elimination will be highly considered. To support this approach, the program will communicate with several targeted audiences through different innovative communication channels and ensure that right information and facts about malaria elimination are known by the general population. Riding upon the advances in information technology, community members will receive malaria educative information timely and be able to take necessary healthy actions in supporting the elimination agenda in their respective areas of dwellings.

Zanzibar has very good coverage of media institutions (both public and private) and at community level with supporting infrastructure that allows smooth implementation of innovative communication approaches thus making the possibility of achieving good outcomes. The use of artificial intelligence, cellphones/smart phones, cartoon and animation messages shall also be taken on board.

Segmentation of the targeted audiences shall be done with the aim of covering large social media and reduce production cost. Furthermore, ZAMEP will engage photographers and designers to organize educational edutainment events through local influencers such as musicians, religious and political leaders etc. to propel malaria messages.

Approach/Intervention 6.2: Deploying community Based participatory approaches to address malaria behavioral determinants and social norms

Community active social norms attributed to low performance in attaining malaria elimination agenda will be identified by end of 2024 and then community based participatory approaches will be deployed throughout the lifespan of MSP (2024-2029)

Understanding malaria determinants and social norms that hinder the malaria elimination movement in the population is of great essence. Through community based participatory approaches, ZAMEP will identify active social norms hindering the attainment of the elimination agenda at community level. Implementation of malaria community based interventions shall include inter-personal communication (IPC) of which community dialogues shall be conducted, involvement of CHVs and strengthening of community health committees through shehia leaderships. Community empowerment for malaria elimination interventions shall be given outmost priority.

Approach/Intervention 6.3: Leveraging multimedia channels to promote positive malaria behaviors

Scripts via multimedia campaigns will be continuously deploy to reach targeted population with appropriate malaria messages throughout the lifespan of this MSP (2024-2029).

Multimedia channels shall be used at large to ensure that appropriate information regarding the malaria elimination strategies is conveyed to all targeted community members. During the implementation of this approach the program will engage and actively involve journalists from different media to disseminate malaria education messages to the general population. In so doing, the use of YouTube, WhatsApp, ZAMEP Web, SMS, Instagram live radio and television program shall all be embraced.

Approach/Intervention 6.4: Advocating community, multisectoral and private sector engagement for malaria elimination

Multisectoral (public and private) entities will be engaged through advocacy meetings on malaria elimination throughout the life span of this MSP

The development of multi-sectoral guidelines will enable the ZAMEP to map all health-related sectors in all spheres including the private sector space in advocating for the malaria elimination agenda. These will include agriculture, education, environment, national planning, social development, housing, tourist, transport and military.

## SUPPORTIVE STRATEGIC AREA 7: LEADERSHIP, PARTNERSHIP AND RESOURCE MOBILISATION

### Strategic Objective 7.1

To enhance effective, partnership and multisectoral engagement towards malaria elimination by assuring that 100% of annual planned activities are implemented by 2029

### Malaria Leadership & Partnership Strategic Approaches/Interventions

Approach/Intervention 7.1.1: Providing effective leadership and governance for the implementation of malaria elimination interventions at all levels

During this strategic plan, the level of fully implemented planned activities will be increased from 60% in 2022 to 95% by 2029.

The ZAMEP is the main overseer and coordinator of all efforts toward malaria elimination. The programme is responsible for providing support and monitoring all malaria elimination interventions in the Islands. In this regard, the programme shall relentlessly endeavor to ensure the required resources (HR, financing, expertise etc.) are harnessed coupled with creating a conducive environment for every stakeholder to play part in achieving malaria elimination goal within the specified period.

Approach/Intervention 7.1.2: Promoting effective multi-sectoral engagement and public-private partnership to achieve malaria elimination

The number of multisectoral entities actively engaged in malaria elimination will be increased from 2 in 2022 to 15 by 2029.

Multi-sectorial engagement particularly among non-health sectors has been identified by the MPR 2022 as one of the areas that need to be strengthened if sustainable malaria elimination is to be attained. In this strategic plan, regular engagement and consultation with the different Ministries, Departments and Agencies will be harnessed to ensure relevant malaria prevention activities are mainstreamed in respective sectorial developmental plans. Moreover, private companies and autonomous agencies together with local and international NGO and CBOs will be actively engaged to support malaria elimination efforts.

Approach/Intervention 7.1.3: Conducting cross-border initiatives to mitigate the impact of malaria importation and reintroduction

In addition to the above strategic approaches, several interventions have been earmarked to enhance cross-border collaboration and partnership with the neighboring regions and countries aiming at preventing malaria importation and re-introduction. The program in collaboration with the bordering countries will need to implement several interventions addressing malaria importation.

### Strategic Objective 7.2

To enhance sustainable financing and accountability for the implementation of the strategic plan by increasing domestic financing up to 50% of the total malaria funding needs by 2029 from the 6% level of 2022

### Malaria Financing and Resource Mobilization Strategic Approaches/Interventions:

Approach/Intervention 7.2.1: Enhancing sustainable financing for malaria elimination interventions

The ZAMEP management has developed the sustainability plan though not in operation to guide the program on the effective implementation of malaria elimination strategies using the domestic resources and the support from the external funding inputs. This plan will be updated and operationalized to maximize mobilization and effective use of resources. In addition, the programme will seek the assistance of the African Leaders Malaria Alliance (ALMA) to establish the End Malaria Council (EMC) and subsequently the End Malaria Fund (EMF). The EMC will be a high-level and profile entity to greatly assist the programme in resource mobilization and advocacy.

Approach/Intervention 7.2.2: Mobilizing adequate resources (human and financial) to support the efficient implementation of the strategic plan

Recognizing the challenges and complexities of sustaining malaria elimination, particular arrangements will be set for mobilization of adequate domestic resources as stated above. Furthermore, the ZAMEP management will continue advocating for resources from the interested malaria stakeholders and the traditional partners currently supporting the Programme.

Approach/Intervention 7.2.3: Advocating for increased malaria allocation in the overall health and other sectoral budgets

Stable availability and effective use of domestic resources is a key requirement for sustainable malaria elimination. Apart from the health sector, activities from other non-health sectors shall be mobilized to contribute to realizing the achievement of reducing malaria transmission chain in the population. Therefore, investments through these sectors are expected to contribute to malaria prevention in the population as well.

Approach/Intervention 7.2.4: Optimizing functional support and competency to create enabling working environment for sustainable implementation of malaria elimination strategies

The ZAMEP will continue deploying innovative approaches in implementing the laid down strategic approaches. For instance, use of geographical information systems shall be extended in order to improve surveillance of mobile populations and identify high transmission areas for better targeted interventions. Such initiative and others within the technical thematic areas will be utilized and regularly monitored to understand its impact to the programme.

Approach/Intervention 7.2.5: Supporting implementation of the priority areas identified in the RSSH need assessment report of 2023

Following a comprehensive RSSH need assessment conducted in 2023, the ZAMEP management will continue supporting an enabling working environment for sustainable implementation of malaria elimination strategies based on the gaps identified in the key priority areas selected. In this context, strengthening national health systems for example, community based interventions, health information management and others shall continue to be given most attention in order to accelerate malaria elimination agenda.

# CHAPTER SIX: IMPLEMENTATION FRAMEWORK

## ACCELERATING TOWARDS MALARIA ELIMINATION: MSP PHASES AND MODALITIES

The implementation of the MSP is divided into two phases of three years each. In between the two phases a mid-term review (MTR) will be performed. A final malaria program review will be conducted towards the end of the second phase. See diagram below.

Figure 14: MSP phases and reviews

| 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| --- | --- | --- | --- | --- | --- |
| Phase 1 |  |  | Phase 2 |  |  |
| MPR |  | MTR |  | MPR |  |

Country level context and universal interventions:

Within the first phase (2024-2026) of NSP implementation it is needed to set up an enable environment to reach and sustain malaria elimination in Zanzibar through more a) political engagement that will enact the necessary legislation and regulations; b) multisectoral engagement to promote non-health initiatives to fight malaria; c) promotion of public private partnership; d) district engagement to enhance the response to local situations and, finally, e) community engagement to promote better utilization and compliance of malaria services.

ZAMEP leadership and technical capability to guide malaria elimination need to be enhanced as well by a) re-orienting and empowering the national team; b) implementing a malaria elimination human resource development plan; c) strengthening programmatic monitoring and evaluation; d) enhancing advanced digital solutions; e) setting up capacity of Lab for next-gen malaria molecular surveillance; f) upgrading essential infrastructures; and g) conducting operational researches.

In this phase it is needed to maintain universal coverage of ITN as the main vector management initiative and universal access to diagnosis and treatment in all health facilities.

Innovative approaches will complement the operations through: a) strengthening advanced digital solution; b) using extensively parasite genomics and malaria molecular surveillance; c) introducing evidence based innovative initiatives for both prevention and care; and d) creating capacity and conducting operational researches.

The set of interventions described above intend to strengthen the national capacity to achieve elimination by the end of this MSP and will form a first strategic initiative named: MAlaria eLImination in ZAnzibar (MALIZA - Swahili for finish it).

Specific Pemba and Unguja islands context and targeted interventions

The current epidemiological situation in Pemba island is characterized by consistent very low malaria incidence (0.9 cases per 1,000 population in 2021). This is a strong indication to aspire for a complete end of local transmission in relatively short period, by end of phase 1. Furthermore, the burden of malaria importation in Pemba is much lower and, therefore manageable, compared to the sister Island of Unguja. During phase 1 a set of interventions will be supported in Pemba to: a) stop local transmission and b) increase detection and mitigation of imported cases. The second phase in Pemba will be dedicated to the prevention of malaria re-introduction. This intensified efforts to eliminate quickly malaria in Pemba and satellite islands, are included under MAnaging Pemba Elimination of MAlaria (MAPEMA – Swahili for soon) initiative.

Malaria epidemiology in Unguja island is more complex compared to Pemba. Malaria in Unguja has a relatively high incidence (5 per 1,000 population in 2021) and is characterized by a) seasonal transmission peaks, b) high rate of imported cases (up to 80% of cases detected) and c) perennial sustained malaria transmission in Zanzibar metropolitan area. In the first phase of the implementation of this MSP a set of dedicated interventions will target the above situation to mitigate importation of malaria cases, seasonal transmission and urban malaria. In phase 2, after learning from the intensive elimination practices introduced by MAPEMA initiative, the knowledge and skills will be shared to Unguja Island. The above interventions will be consolidated in the third initiative, ELImination of Malaria in Unguja (ELIMU - Swahili for education) that aims to achieve malaria elimination in Unguja and satellite islands in a relatively longer time with complete end of local transmission by 2029.

Across Tanzania Mainland and Zanzibar context:

A last initiative TAnzania mainland & ZAnzibar MAlaria (TAZAMA – Swahili for lookup) aims to: a) control the imported cases from Tanzania Mainland (and other malaria endemic countries) to Zanzibar, and b) to prevent the re-introduction of the infection in the islands; and c) strengthen operational research, molecular surveillance and insecticide/medicines resistance. The two malaria programmes of Tanzania Mainland and Zanzibar, NMCP and ZAMEP respectively, will be jointly working on improved travelers’ surveillance, operational research to detect determinants of parasite movements and joint operations to track parasite genomics.

## MSP WORKPLAN

On yearly basis, the programme and partners will jointly develop and implement annual work-plans derived from the MSP ensuring that activities planned for that particular year are undertaken accordingly. The implementation of these plans will be monitored closely through the year across all thematic areas by the M&E Unit in order to ensure that desired traction is maintained.

## IMPLEMENTATION ARRANGEMENTS

Implementation of the Programme services and activities will be carried out using the existing health service delivery system involving primary health care units (at community level), district, regional and Mnazi Mmoja Tertiary Hospital located in Unguja. District level is the functional unit solely responsible for coordinating all district and community based activities. Administratively, district authorities remain a link within the district and at community level through the existing structures – Shehia leadership. Technically, the District Health Management Teams will continue to provide directives and guidance in the provision of services.

Civil Society Organizations, Community Health Volunteers and Custodian Health Committees shall be fully engaged to accelerate community-based malaria activities such as Indoor Residual Spraying, LLINs distribution, Active Malaria Case Detection and health promotions sessions.

At Programme level, heads of each technical thematic area will oversee implementation of interventions at all levels and report to the Programme manager. These are Socio Behavioural Change Communication, Integrated Vector management, Diagnostics and Case Management, Surveillance Monitoring and Response, Finance and Procurement and Supply.

The heads are responsible and accountable for implementation of strategies and activities entailed in the programme’s strategic plan under the guidance of the Programme Manager. They will ensure that coordination, accountability, implementation and management of malaria activities at all levels is realized in order to improve service delivery, achieve greater intervention coverage of malaria services, improved quality, cost effectiveness and ownership of interventions.

## OVERALL PROGRAMME MANAGEMENT

The Programme Management shall ensure the use of strategic documents to guide operations and reporting systems. These documents include procurement plan, annual work plan, training, business and M&E plans.

### The Zanzibar Malaria Elimination Program (ZAMEP)

ZAMEP is responsible for the development of strategic plans concerning malaria elimination, implementation, monitoring and evaluation of malaria elimination interventions and coordination of stakeholders at all levels of the health care delivery system including formulating strategies, preparing guidelines, working tools and mobilizing resources.

ZAMEP implements its activities in both Unguja and Pemba islands and is technically supporting malaria implementation activities in the districts through the District Health Management Teams (DHMTs) headed by a District Medical Officer who is the overall in charge of health services, including malaria.

The malaria implementing partners comprise of the District Health Management Teams (DHMT), Research institutions, the non-governmental organizations, the Zanzibar Private Hospital Board, Central Medical Store, Health Information Management Unit and Zanzibar Food Drug Agency.  Public awareness is being carried out by media, community groups and volunteers.

The ZAMEP is also mandated and encouraged to mobilize resources through the development of funding proposals and operational plans to be submitted to development partners and RGoZ. Additional functions of ZAMEP are as follows:

- Technically advise and make practical recommendations to the MoH on all issues related to policies and strategies of national malaria elimination

- Receive and discuss reports from technical working groups on malaria elimination policies, strategies and interventions

- Develop technical and scientifically sound guidelines for the implementation of malaria elimination in line with WHO recommendations

- Provide technical guidance for monitoring outcomes and processes and evaluate impact of the interventions

- Identify critical strategic and programmatic issues arising from implementation of malaria interventions and activities and assign responsibilities to working groups for follow up

- Identify emerging programmatic and implementation research questions and bring these to the attention of relevant partners.

### ZAMEP Structure and Functional Technical Units

### ZAMEP Management

Leadership and program management

Under the leadership of Program Manager (PM) will be working five dedicated units and sections responsible for cross cutting tasks. The units are: Monitoring, Evaluation, Research and Learning (MERL), Accounts and Finance, Procurement and Supply Chain, Information, Communication Technology and Administration. Each section will have a focal person reporting directly to the PM. The functions and composition of each section will be as follows.

Figure 15: the ZAMEP organograms

Monitoring, Evaluation, Research and Learning

The MERL Unit has the overall function of strengthening the program M&E capacity and its organizational culture in ensuring the program activities are getting implemented as planned, and to assess whether desired results are being achieved.

The M&E Unit will also strive to reinforce the malaria information system by ensuring collection of quality data (routine & non-routine), analysis, dissemination and use of evidence-based information.

In addition, the Unit will institute proper M&E mechanisms to track changes from baseline conditions to the desired outcome and impact, and understanding why change is or is not taking place thus implore for improvement of the malaria interventions and strategies.

The above are of great importance as they make the MoH, ZAMEP, health service providers (public & private), beneficiaries and other stakeholders accountable for attributing to the achievement of malaria elimination in Zanzibar.

Accounts and Finance

The key functions of this Unit will focus on strengthening strategic financial management by meeting financial compliance of funds disbursed to the programme. Preparation of budgets, managing records and receipts following the daily expenditures, reconciliation of funds and preparation of financial reports are fundamental in this unit. Financial audits and responding to management letters from the funders are critical for transparency purposes.

Procurement and Supply Chain (Logistics Management)

This Unit acts a link between the ZAMEP and Procurement Management Unit of the Ministry of Health (PMU) in order to adhere with the public procurement act. The Unit is responsible for the procurement of commodities and supplies locally at a particular set financial threshold whilst those which fall above this will be referred to the PMU.

Information, Communication Technology

The ICT Unit at ZAMEP plays a vital role in ensuring smooth and effective functioning of the program. It is responsible for planning, design, development, implementation, management, maintenance, of digital health interventions for ZAMEP in line with the Zanzibar Digital Health Strategy. The Unit works closely with other departments with regards to design and development (digital tools, applications and platforms) in order to identify areas where digital health interventions can enhance the programme's effectiveness.

Once digital health interventions are developed and implemented, the ICT Unit oversees the ongoing management and maintenance thus ensuring seamless functionality and staying up-to-date with technological advancements.

Furthermore, the ICT section ensures that all digital health interventions align with the broader goals and objectives outlined in the Zanzibar Digital Health Strategy. This ensures that ZAMEP's digital health initiatives are well-coordinated and contribute to the larger goal of improving health outcomes in Zanzibar.

Administration and Human Resource

The Programme Management Unit’s primary role is to ensure smooth operations of ZAMEP as a whole to enable that the planned activities in MSP are undertaken. The Programme Manager (PM) is the link person to the MoH including the other health related sectors and to the broad partnership. In this plan, a newly proposed position (Head of Thematic Units) shall be established whose responsibility will be to technically overseeing the implementation progress and provide relevant feedback to the Programme Manager for possible action. For effective delivery of the planned activities, the presence of required human resource in terms of quantity and professional knowledge and skills remain a task of the PM who makes the necessary official engagements with the MOH pertaining to any relevant situation that may arise.

### Partnership:

The PM is also responsible for coordinating the broader partnership including MoH intra-sectoral collaboration, multi-sectoral framework, developmental partners, and research institutions. ZAMEP will continue to strengthen coordination with the partners and key stakeholders by way of the already set regular meetings and if/when the need arises.

### Technical Thematic Units

The successful implementation of this MSP depends on technically sound performances of the thematic units. Four thematic units, namely Malaria Surveillance and Response, Integrated Malaria Vector management, Malaria Case Management, and Social behaviour change and community engagement, are envisaged to conduct the planned proven malaria elimination initiatives. Each unit will be coordinated by a focal person who will report to the Head of Technical Units who in turn will be supervised by the Programme Manager. The proposed functions and composition of the Technical Units is as follows:

Malaria Surveillance and Response (MSR) Unit: the main functions of the MSR are to coordinate and conduct three major surveillance tasks: a) epidemiological; b) entomological and c) molecular surveillance. All the above tasks are closely linked with dedicated response actions aimed at blocking local transmission and mitigating possible re-introduction. The units need to be fully equipped with qualified and skilled personnel under the supervision of the Unit focal person. The desire of the programme is that the ZAMEP offices (Unguja and Pemba) should have at least an epidemiologist, a data analyst/statistician, and enough field officers to provide support to Surveillance and Response operations.

Integrated Malaria Vector management (IMVM) Unit: the main function of the IMVM unit is to plan and implement the identified core strategies to limit the human-vector contacts aimed at achieving the goal of elimination of local malaria transmission. The IMVM unit should be able to calibrate and integrate universal coverage of ITNs and targeted/focal application of IRS and LSM. The programme will work towards ensuring that both ZAMEP offices (Unguja and Pemba) have an IMVM unit with at least a qualified entomologist/vector management specialist, and a team of competent environmental field officers to support routine and response operations.

Malaria Case Management (MCM) Unit: the main function of the MCM unit is to provide competent and quality universal diagnosis and treatment services to the population and to prevent mortality by promoting improved referral services and appropriate emergency management for severe malaria. Lastly, the unit will continue to support the focal and targeted response approach in the quest of contributing towards halting local transmission and limiting the risk of reintroduction by using preventive therapies. Each ZAMEP office (Unguja and Pemba) should have a MCM unit with at least a medical doctor, a laboratory technologist, a pharmacist to support routine and response operations.

Social behaviour change and community engagement (SBC&CE) Unit: the main function of the SBC&CE unit is to provide appropriate and informative guidance on malaria elimination to the general population using various channels of communication. Both ZAMEP office (Unguja and Pemba) are envisaged to have a SBC&CE unit with at least a Social Science Specialist, a communication expert and enough field staff to support routine and response operations.

## ROLES AND RESPONSIBILITIES OF DISTRICT HEALTH MANAGEMENT TEAMS, HEALTH FACILITIES AND COMMUNITIES

### District Management Teams

This structure was developed to facilitate the management and implementation of primary healthcare. The management teams’ responsibilities include planning and budgeting, human resource management, monitoring service quality, and ideally allocating resources to most effectively meet local population needs.

The District Medical Officer (DMO) is a link person to the MOH programmes such as ZAMEP, ZIHHTLP, NCD and others. Similarly, the programmes have a direct communication with the districts in order to carry out the planned activities. There are eleven district health management teams headed by the DMOs. The teams are responsible for coordinating and monitoring health services at district level. Each team consists of 2-8 mixed skilled staff including District Malaria Surveillance officers who have dual roles, within the DHMT and at ZAMEP.

All ZAMEP activities conducted at district level such as surveillance, training and community based activities are also reported at district level for follow up and reference.

### Health Facilities

The Health Facilities at primary care level (dispensaries and health centres) are responsible for diagnosis and treatment of malaria patients including pre-referral management of severe cases. Furthermore, they are providing essential preventive services (ITN) for biological risk population such children under five years of age and pregnant women. Primary health care is also providing health education and promotion for all attendees.

Secondary level of health care facilities (district hospitals) are providing all the above services and additionally are managing patients referred with sever malaria from primary care level.

The tertiary level of health care facilities (regional and referral hospitals) are providing more specialized interventions in the case referred from secondary level, in intensive care units and management of most severe complications (such as dialysis).

### Communities

Community-based services are a critical component of high-quality primary healthcare services. The community health volunteers (CHV) scheme provide a platform for the community engagement in health services. The aim of establishing the CHV scheme is to empower the communities to take in the decisions that affect their communities; mobilize communities for health programs and strengthen the delivery of health services through referral and linkage at household level. Initially, the CHV were dealing with reproductive health services only. However, their boundaries are gradually expanding following the observed impacts. In this plan, CHV will be used to hasten malaria interventions such as ITNs distribution, health promotion activities and malaria surveillance.

## PROGRAM GOVERNANCE

### Independent National Malaria Elimination Advisory Committee

In 2018, the RGoZ through the Ministry of Health established the Zanzibar Malaria Elimination Advisory Committee (ZAMEAC), comprising local and international experts whose mandate is to provide an external view of progress and gaps in Zanzibar malaria elimination programme, assist in adapting WHO guidance to the Zanzibar context, and review malaria trends and progress towards elimination. ZAMEAC is an independent entity from ZAMEP and meets once a year to technically assist the programme in achieving evidence based strategic direction.

ZAMEP acts as the secretariat for the ZMEAC and facilitates its work, including the preparation of meeting and teleconference agenda, background documents and presentations, and meeting minutes and reports, in consultation with the Chairperson.  All ZMEAC reports and recommendations are advisory to the MOH and ZAMEP and in order to ensure transparency, recommendations of the ZMEAC are published on the Zanzibar Ministry of Health website.

### ZAMEP Management Committee (ZAMC)

The key purpose of the ZAMEP management committee is to: a) oversee development and implementation of malaria elimination; b) monitor and evaluate the effectiveness of malaria programs; c) ensure coordination and collaboration among various stakeholders involved in the fight against malaria both national and international; d) advise on policy matters related to malaria prevention and elimination in Zanzibar.

Moreover, ZAMC will guide ZAMEP on resource mobilization and partnership coordination in the fight against malaria in Zanzibar. Aiming to advocate for increased funding for malaria elimination from governments as well as raising the profile of the disease internationally.

The ZAMC will discusses policies and researches that are proven to work on the ground in the fight against malaria and seeks to resolve malaria implementation bottlenecks in Zanzibar.

Composition

The ZAMC will comprise a group of key personnel to include individuals with diverse skills, expertise, and relevant stakeholder representation

- ZAMEP core management

- Director of preventive serves (secretariate)

- Implementing partners

- Developing partners/donors

- Health policy advisor

- Zanzibar Malaria epidemiologist

- Research Institution representative

- Ex-ZAMEP Program management representative

- ZAMEP advisor

### Malaria Technical Working Groups

The ZAMEP Management has a good track history of working with the thematic technical working groups especially on SMR, Diagnosis and treatment. Over time the TWGs did not perform to the full expectations as they did not regularly meet. Due to its importance, all malaria technical working groups will be energized during the lifespan of this MSP implementation:

- TWG on Malaria Surveillance and Response

- TWG on Integrated Malaria Vector Management

- TWG on Malaria Diagnosis Treatment and Preventive therapies

- TWG on SBC&CE

- TWG on Malaria Monitoring, Evaluation, Research and Learning

TWGs operational modality: All technical implementation and programmatic issues related to malaria behaviour will be discussed at respective technical working groups and their resolutions be submitted to ZAMEP management and shared with Executive Committee of the MoH -should need be, through the DPS. The TWGs will meet twice a year, and extra-ordinary meetings can be convened if necessary. The respective ZAMEP Head of Units function as the secretariat.

#### Malaria Surveillance and Response Working Group

In 2014, the TWG was established to provide technical advice to ZAMEP on the development and implementation of appropriate surveillance system for malaria elimination. The TWG will be responsible to synthesize the recommendations provided by ZMEAC on matters related to   surveillance and response. Therefore, there is need to reinforce and achieve a strong surveillance system based on existing platform such as the Integrated Disease Surveillance and Response(IDSR)and the Malaria Case Notification System (MCN). This will enable ZAMEP to track progress through stronger demand and use of data generated through IDSR and MCN, so as to enable decision making at Programme level and beyond. The term of reference of the SMR TWG are:

- The responsibilities of the SMR TWG will be to: provide technical advice to ZAMEP on surveillance, monitoring and response and is not limited to:

- Review ZAMEP indicators (impact, outcome and coverage) in order to monitor program performance. Review findings to be shared to the Program Management for action

- Review the existing surveillance systems and recommend innovative approaches to ensure robust surveillance system for malaria elimination

- Assess data use at all levels (National, Districts, HFs) for better decision making and design useful and effective methods to promote data use where necessary

- Review and recommend additional indicators for monitoring the impact of malaria interventions at all levels when the need arises

- Suggest priority research areas in the field of SMR and other areas as need arises

- TWG should have access to ZMEAC reports and monitor implementation of all SMR recommendations

The TWG will be comprised of up to 10 members. Member of TWG should represent different areas of expertise and experience on malaria surveillance and response. The following is a list of TWG members:

- ZAMEP staff - 4 (Head SMR, SMR staff Pemba, 2 TBD by management)

- Development partners 1 - 2 (Dar es Salaam and Zanzibar)

- USAID Tanzania - 1

- Research Institute (TBD) - 1

- MOH Zanzibar (Head M&E unit) - 1

- MOH Mainland (Malaria Surveillance).  1

Other individuals with different or additional areas of expertise could be added to the TWG as needed, to assist with specific issues or problem areas. To ensure continuity of TWG oversight, no more than half of the members should be replaced during any six-month period. ZAMEP SMR Unit will serve as secretariat for the TWG. A TWG Chairperson and an alternate will be selected by the members of the TWG during the first meeting. The function of the Chairperson will be to work with SMR Unit to develop agenda for each meeting and to facilitate the meetings. ZAMEP SMR staff will be responsible for recording the minutes of the meeting, including decisions, recommendations and action items and preparing reports of each meeting.

#### Integrated Malaria Vector Management Technical Working Group

In 2021, all ZAMEP technical thematic areas, including vector management, revived the technical working groups with the responsibilities of advising the programme on the methods that could be deployed in controlling malaria mosquitoes (such as IRS, ITNs & LSM) and showing the way for vector management operational research areas for effective malaria elimination.Therefore, the Integrated Malaria Vector management TWG will work based on the following TOR:

- To advise on implementation plans and progress reports related to Malaria Vector management

- To review vector management interventions (e.g. LSM, IRS, LLINs) in Zanzibar and advice the MOH/ZAMEP timely and accordingly

- To review policies, legislation, regulations and procedures and advise the MOH on their enforcement and application

- To review various malaria vector management activities carried out by other stakeholders and give on-the-spot advice on the appropriate technical aspect

- To identify potential areas for research and suggest ways and mechanisms towards obtaining appropriate solutions

- To review and advise on the best modalities of publicizing policies, policy guidelines and communication strategies on IEC related to malaria vector management

- To advise on the appropriateness of IEC materials that would disseminate correct and effective information in regard to malaria vector prevention and control

- To advise the best mechanisms to track progress of vector management program interventions

The Malaria Vector management TWG has a multi-sectoral composition. Members are selected by the respective institutions based on their expected contributions to the specific vector management matters within their areas of expertise. The Working Group membership includes the following:

- Director of Preventive Services (chairperson)

- Programme Manager, ZAMEP

- Head of Integrated Vector management Unit (secretary) and Members of the Unit

- Head of SMR Unit of ZAMEP

- Head of SBC&CE unit of ZAMEP

- Head of Case management unit of ZAMEP

- Head of diagnostic unit of ZAMEP

- Head of Immuno-molecular Laboratory

- Representative from research institution working with ZAMEP (IHI, NIMR, SUZA)

- Representative from anzania Plant Health and Pesticides Authority (TPHPA) former Tropical Pesticides Research Institute (TPRI)

- Representative from the Environmental Management section (ZEMA)

- Representative from the Ministry of Agriculture e.g. Plant/Animal protection

- Representative from Ministry of state in Presidential office, Regional Administration, Local Government and special SMZ department

- Implementing Partner Group representative (interested in malaria vectors)

- USAID-PMI Malaria Technical advisor

- WHO representative

- Representative from ZFDA

- Representative Member from Tanzania Meteorological Agency.

#### Malaria Case Management Technical Working Group

In 2016, the Malaria Diagnostic TWG was established to provide technical advice to ZAMEP on the development and implementation of appropriate malaria diagnostics for malaria elimination in Zanzibar. In this phase of implementation it is suggested to include therapeutics and preventive therapies into a comprehensive malaria case management working group. The followings are the terms of reference for the MCM-TWG

- Advise and provide technical support to the ZAMEP case management unit

- Review and give inputs on developed guidelines and SOPs for malaria diagnosis and treatment

- Advise on diagnostic and treatment operational interventions

- Assess training needs and provide selection criteria for the facilitators and trainees

- Establish a network of actors to share information and harmonize Mosquitoes and Parasite interventions at National, International, and District levels including medical health alliances

- Coordinate and provide technical assistance on matters related to malaria diagnosis

- Coordinate preparation and review of malaria policy guidelines for malaria diagnosis, treatment and preventive therapies

- Advise on the training of health workers plans on all issues related to malaria diagnosis and treatment

- Review the implementation of malaria diagnostics (mRDT, Microscope, etc.) use

- Review therapeutical efficacy of antimalarials

- Review the malaria case management studies proposed to be conducted by various partners

- MCM-TWG should have access to ZMEAC and other groups' reports and monitor the implementation of case management recommendations

Membership Malaria Diagnosis TWG

The mMCM-WG will be comprised of up to 10 - 15 members. Members of TWG should represent different areas of expertise and experience in malaria diagnosis

- ZAMEP staff - 6

- Development partners  - 4

- Research Institutions (TBD) - 1

- MOH (Diagnostic and quality) - 2

- Medical alliances University (School of medical laboratory) -2

#### Monitoring, Evaluation Research and Learning technical working group

The technical working group of ZAMEP - MERL shall be compose by representatives from HMIS, ICT unit of the MOH, M&E unit of the MoH, Malaria Sub-recipient focal person, representative from the M&E of the Zanzibar Planning Commission, M&E expert from malaria supporting Partners, ZAMEP manager/DPM, head of ZAMEP M&E unit, and the MEL focal person of the ZAMEP thematic sections. The ZEMEP –MEL technical working group among other roles will to provide technical guidance in the followings:

- Ensure effective monitoring and evaluation of the malaria program.

- Enhance data-driven decision-making, assess program effectiveness, and foster continuous improvement in malaria prevention and control efforts, including analysis and interpret data to assess the effectiveness of malaria prevention and control strategies.

- Ensure the integration of health information systems to facilitate data-driven decision-making and facilitate community engagement and feedback mechanisms to enhance program responsiveness

- Effective coordination of MEL activities within ZAMEP

- Technically advice the ZAMEP M&E system on various MEL actions to facilitate its effectiveness

- Stay as a consultation level for ZAMEP MEL related issues.

- Socio-behaviours Communication technical working group

### Partnerships and co-ordination

The ZAMEP Management attributes its achievement of reducing malaria burden to a no longer public and socio-economic health problem to a collaborative effort, and will over the years continue to partner with multi-sectoral stakeholders and development partners. These partnerships cut across national and international platforms. They are aimed at synergistic and collective efforts towards malaria elimination through technical skills exchange and bridging gaps in resources necessary for achieving malaria elimination. The Programme will also continue to work closely with existing partners and stakeholders and further identify new partnerships relevant with the current strategy. A mapping exercise for all Programme partnerships will be conducted in this current strategy for coordination and harmonization.

### National fiscal planning cycle and alignment with malaria programme

The ZAMEP sources of financial support is mainly from the RGoZ, WHO, GFATM and the PMI/USAID. Different financial management and reporting systems from these institutions are used which the programme adheres to. For Government funds, the programme produces its annual budget using the Government mandated medium term expenditure framework. This is then submitted to the Ministry of Health which consolidates all budgets before forwarding them to the Ministry of Finance. The Governments fiscal cycle commences 1st July and ends on 30th June of the following year.

Funds from the Global Fund are controlled at MoH which is the Principal Recipient (PR). Planning and absorption of these funds are guided by the Global Fund approved grant budget and implementation plan. Each year, the programme together with the PR develop an annual forecast that informs the year’s expenditure and required disbursement

### Cross‐border malaria initiatives

There is no formal framework strategy for malaria elimination between the ZAMEP and neighbouring coastal areas of Tanzania Mainland and also Kenya. However, elimination efforts are underway with Mainland Tanzania. Exchange learning tours have been conducted to look into the possibilities of executing mitigation measures following the imported malaria cases.

In this plan, the ZAMEP Management supported by the MoH shall approach RBM Secretariat Southern and Eastern Region to technically assist in establishing collaborative cross-border malaria initiatives.

## MULTISECTORAL ENGAGEMENT

It is widely recognised that controlling and eliminating malaria is an essential part of a comprehensive development framework for the multisectoral collaboration.

Achieving malaria elimination requires a well-coordinated and concerted multisectoral effort and integrated approach which as a resultant, will directly impact on enhanced economic growth. For this strategy to succeed and eventually realize the set goal it will require multiple actions at several levels implemented by various actors from different ministries. As stated by the World Health Organization, the Multisectoral Action Framework for Malaria is a stimulant to inspiration and guidance-for-action for policy and executive decision makers as well as for practitioners in all sectors, including public and private. The Framework considers priority determinants to be addressed by different sectors as applied to the Zanzibar situation.

This MSP 2024-2029 emphasizes the importance of multisectoral action on malaria elimination. ZAMEP needs to improve planning, coordination and collaboration, and to identify interactions between different sectors and actors to yield malaria smart interventions. Malaria interventions are now faced with a system challenge. In most settings the root causes of malaria lay beyond the health sector’s reach – social and economic inequities; poor housing and living conditions; the climate crisis and environmental degradation; agricultural practices and water and waste management .

A successful multi-sectoral programme must be relevant to the situation. Therefore, this MSP presents an overall picture of how the MSA should be used and its main components, applying the guidance to detailed strategies and programme shall remain flexible and adapted to local capacity and institutions. The first step in a collaboration based on the MSA must be a detailed inventory and evaluation of national, regional/district and Shehias’ organizational structures, activities and resources in strong advocacy and national work on infectious diseases, including VBD. The health sector itself is not well placed to advocate for policies promoting multisectoral action; such policies should be formulated at a higher, over- arching level.

ZAMEP developed multisectoral guideline since 2020, however interventions from this document have not been implemented, except for work at Ministry of education and vocation training (MoEVET) that established malaria school clubs at public secondary school (30%).

The followings are the gaps identified to establish a functional multisectoral framework:

- Lack of a solid and compelling evidence to convince other sectors’ decision makers of the links between their sectoral actions and malaria incidence and of the mutual benefit of multisectoral action on malaria

- Lack of coordination across sectors due to difficult and bureaucratic structures based on strong organizational silos

- Lack of non-health sectors ownership towards malaria elimination, which can limit their enthusiasm and commitment to achieve commun goals.

- Agreed upon activities are unfunded within the national or sectoral ministries budget

In this context, the ZAMEP Management will re-organize itself in order to set up some strong operational mechanisms to execute the existing multi-sectoral guidelines. At program level, there is a need of appointing a dedicated programme officer to establish strong linkages with relevant sectors to kick-start this important agenda. On the other hand, awareness creation on the role of the multisectoral collaboration as stipulated in the current guidelines will be implemented. Roles and responsibilities for other sectors including accountability shall then be determined.

During the implementation of this MSP, ZAMEP will emphasize the followings

- To identify non-health sectors associated with the determinants of VBDs to assist them in deciding on sectoral objectives, partners and actions (see provisional list below)

- To establish a comprehensive conceptual framework for an multi-sectoral approach (MSA) to the prevention and proactively control of vector-borne diseases (VBDs)

- To standardize and guide the implementation of malaria control and prevention in all sectors

- To integrate malaria elimination in respective non-health sectors plans and budgets

- To establish an effective coordination mechanism through secretariat at second VPO

- To develop a multisectoral operational plan, where roles and responsibilities of all sectors activities and M&E framework will be outlined

- Conduct awareness and advocacy meetings to be malaria -smart on elimination strategies at different level of stakeholders

- Establish end malaria council (National and District)

- Identify malaria champion

- Document and disseminate multisectoral investment case for malaria elimination in Zanzibar

Provisional list of sectors

- Agriculture

- Defense And Security

- Civil works & Construction company

- Infrastructure

- National Environment Commission

- Education

- Tourism

- Housing

- Transport

- Politician

- Communication

- Hoteliers

- Fisheries

- Ministry of work and social welfare

- Metrology Department

- Media Institution

- Universities (Health and non- health)

- Telephone companies

- Collaboration of Private Sectors

- Local Government Authorities

- Community

- Others etc.

## MANAGEMENT PROCEDURES

## Data Management Arrangements

The Zanzibar Malaria Elimination Program obtains malaria data through routine systems. All health facilities collect data on malaria as part of the general health services at outpatient department (OPD), in-patient admissions and antenatal care using weekly disease surveillance forms and entered into a web-based DHIS2 system. Malaria suspects, diagnosed and treated patients in health facilities are recorded and summarized each day on paper-based tally sheets, which are then used to compile Weekly disease surveillance form [electronic integrated disease surveillance and response (eIDSR)]. The data is submitted in the DHIS2 monthly and is then accessible to users nationally and sub-nationally for analysis and decision-making.

Additionally, passive malaria cases are collected and reported through Malaria Case Notification (MCN). The MCN data of individually diagnosed malaria cases is collected at health facilities and entered using Android gadgets (mobile phones and tablets) into a central database. The index case is notified to a District Malaria Surveillance Officer (DMSO), who then collects surveillance data as part of a reactive case follow-up and detection at households of index cases.

The system links the malaria case notification and the reactive case follow-up data. Coconut Surveillance is an open-source case-based surveillance and response system designed for malaria elimination. It is a mobile application system modified from Malaria Early Epidemic Detection System (MEEDS) to support individual case reporting. In 2012 the Research Triangle Institute (RTI) in collaboration with the ZAMEP developed the Coconut Surveillance System. Coconut Surveillance provides near real-time case identification, geo-located data for finely targeting interventions, and management information about field staff progress. Coconut Surveillance uses the Geographical Positioning System (GPS) capability of the tablet to record the location of the household. Each household member is tested, and the confirmed cases are treated immediately. The data are synchronized at least daily with a e-government database. Routinely, data validation is done every 6 months.

## Procurement and Supply Management Systems

ZAMEP conducts in-house procurement for all malaria commodities below the set threshold stipulated by the Financial and Procurement Manual 2018. The Ministerial Tender Board is used for all procurements beyond the threshold. The Pooled Procurement Mechanism using Pooled Procurement Mechanism (PPM) system through the GFATM is used to procure donor-funded health and non-health commodities. The USAID/PMI uses its own procurement mechanisms.

The programme shall submit an annual procurement plan to Procurement Management Unit, which provides a forecast and timelines for all procurement needs. This plan will reflect the products that are required by all thematic areas of the programme.

## Financial Resources Management And Audits

Financial resources from the RGoZ, the Global Fund and PMI/USAID are managed and accessed differently using their own individual financial management system which are also audited intensely. For instance, with regards to the Global Fund resources, an annual forecast for all activities and procurements for the year is submitted, and then funds are released against the forecast. Financial audits are done at the Principal Recipient (MoH) where finances are held by Local Funding Agent. Government finances are managed within the MoH but governed by the Ministry of Finance.  The Auditor General conducts audits on all financials for Ministries and any discrepancies noted are forwarded to the Principal Secretary of the relevant Ministry for management responses.

Key Assumptions

There are number of factors which might positively favour the programme with a likelihood of meeting the set targets by 2029 subject to the following assumptions by the ZAMEP and partners being true:

- Financial and technical support from the RGoZ and partners will continue.

- Harnessing of domestic resources to fulfill the noted gap

- Uninterrupted commodities and supplies will constantly be available to meet the country’s needs

- Strong coordination among all key malaria stakeholders will continue

- Full implementation of all planned activities

- Maintain and sustain the current low prevalence of malaria

## RISK ANALYSIS AND MITIGATION

Implementation of this strategic plan will mostly likely be subjected to several risks which will require timely and appropriate mitigation to avoid derailing of its implementation.

Table 6: risk outline and proposed mitigation:

| Risk | Mitigation |
| --- | --- |
| Inadequate or gaps in financing may lead the Programme not fully implementing all planned activities which are key for malaria elimination. | Enhance the harnessing of domestic resources through: 1) Operationalization of the sustainability plan 2) Establishment of the End Malaria Council (EMC) and End Malaria Fund (EMF) 3) Enhancement and expansion of Multi-sectorial engagements |
| Global pandemics such as COVID-19 which may lead to disruptions in implementation and also supply chain management | With regards to; 1) Implementation: adapt to prescribed guidelines during field work and use of new technologies (Zoom, Microsoft Teams etc) when there is need to conduct trainings and meetings. 2) Supply chain management: Consider front loading of procurements of commodities especially those sourced from overseas and internally factor in buffer stocks. |
| High incidences of imported cases | 1) Establish Cross-border Malaria Initiatives with nneighbouring countries 2)Enhance surveillance at all points of entry (both official and non-official) |
| Malaria Outbreaks | Finalize and deploy the Epidemic and Response Plan |
| Increasing resistance of insecticides notably pyrethroids | -Update the Insecticide Resistance Mitigation Management Plan -Rotation of insecticides every two years -Consider usage of Next Generation ITNs |
| Emerging resistance of ACTs in Lake Zone regions of Mainland Tanzania and neighboring countries poses potential threat to Zanzibar as well | Conduct regular Therapeutic Efficacy Studies and if need be, switch to another first line Anti-malarial |

## COSTS OF NSP, ANTICIPATED FUNDS AND GAPS

The total cost of the NSP 2024-2029 is estimated in USD 45,757,833 (see Annex 2). Vector management has the larger share of the budget (27%) followed by the other two core strategy, surveillance and response (22%) and case management (14%), see Figure 15. The total annual budget and its proportion by intervention is represented in Figure 16.

Figure 16: Proportion of NSP costs by strategic area

Figure 17: Total and proportion of budget costs by year and strategic area

PMI and GF are the two major contributors to the malaria financing with an aggregated share of 59% (Figure 17). The total annual budget and its proportion by funding initiative is represented in Figure 18. The expected total budget gap however is at the level of 40%.

Figure 18: Proportion of NSP costs by partner and funding gap (Year 1- year 4)

Figure 19: Total and Proportion of NSP costs by partner and funding gap by year and development partner and the remaining gap

# CHAPTER SEVEN: MONITORING AND EVALUATION FRAMEWORK

## COMPREHENSIVE MALARIA STRATEGIC INFORMATION SYSTEM

A well-managed malaria strategic plan for Zanzibar needs the followings steps: a) generate routine and periodic quality data (data collection); b) transfer the data into information (data analysis); c) transform information into knowledge (interpretation); d) translate knowledge into evidence-based policy; e) develop effective interventions plan; f) implement the activities efficiently; and lastly g) monitor and evaluate the implementation by generating routine and periodic quality data. To perform the above tasks, ZAMEP needs to integrate and streamline the current information systems into a unique comprehensive malaria strategic information system (CMSIS) within the existing settings of the MoH.

Due to the complexity of malaria epidemiology and its elimination intervention  there are several set of information that are needed to monitor a) transmission determinants such as parasite and vector dynamics and environmental conditions; b) disease incidence, including severe morbidity and mortality; c) biological indicators of programmatic importance such as insecticide resistance and therapeutics efficacy; d) elimination interventions, e.g. outcome and outputs of preventive and treatment measures including commodities accountability; e) socio-economic factors influencing receptivity and vulnerability to infection, e.g. population movements, urbanization, population wealth, occupational exposure; behavioural aspects in relation to night activities; and f) health services access and quality.

A functional comprehensive malaria strategic information system (CMSIS) should take into consideration all the above factors and the relative complexity to link them to efficient and effective actions to eliminate malaria in Zanzibar through a) stop local malaria transmission; b) control unavoidable imported cases and lastly c) prevent resurgence.

In the current elimination phase the ZAMEP-CMSIS needs an interactive and well linked system that is able to: a) collect real time information from a number of different places (health care facilities, community, and reference laboratories); b) transmit the information to, possibly, a unique data repository; c) provide a visualization platform for the information users at different levels.

The essential data collection tools are in place, yet not well integrated, and using a number of different systems using paper and electronic based data collection tools, manual and digitalized transfer of data and different data repository facilities (from staff laptops to central MoH server).

To facilitate the planning, monitoring and evaluation of this MSP, a CMSIS will be set up and managed according to the regulatory framework of the RGoZ and MoH.

The core element of the CMIS that is essential to generate short, medium and long-term responses is the integrated malaria surveillance system with essential epidemiological, entomological and environmental information. The second element is provided by the routine health management information system with more performance-based indicators from health facilities. The third element of the CMSIS is the commodity tracking system that allow a functional and accountable management of commodities procured by the state or by development partners. A programmatic monitoring and evaluation system is also crucial to document the field activities related to malaria control interventions at community level and to track the efficacy of antimalarials and insecticide susceptibility.

Figure 19: Elements of the comprehensive Zanzibar Malaria Elimination Information System

Key: OPD = Out Patient Department; IPD = In Patient Department; RCH = Reproductive and Child Health; QA/QC = Quality assurance and Quality Control

### Integrated Malaria Surveillance System

For the past two decades ZAMEP initiated and supported a number of original and advanced entomological surveillance initiatives starting from the establishment of entomological sentinel sites. More recently, this activity has been expanded to include entomological foci investigations. Entomological surveillance system completed insecticide resistance monitoring, ZAMEP has also been in the forefront of the establishment of an innovative epidemiological surveillance through the introduction in 2008 of a digitalized weekly malaria case monitoring (MEEDS) and in 2012 of malaria case notification (MCN).

For the implementation of the new MSP the two system need to be interlinked and well-coordinated to generate indications for immediate MCM, MVC and SBC&CE response.

Figure 20: Malaria Surveillance and Response Information System

Key: frDA = focal reactive Drug Administration; frIRS = focal reactive Indoor Residual Spraying; frLSM = focal reactive Larval Source Management; fTAT = focal Test and Treatment; fRC = focal Risy Communication;

### Health Management Information System

The HMIS is a national system which routinely captures inpatient and outpatient information for all diseases, including malaria which is reported monthly by health facilities. The ZAMEP shall continue to work with the HMIS in all aspects of data management.

Figure 21: Malaria HMIS and Response Information System

Key: DHIS2 = District Health Information Software; HMIS = Health Management Information System; IDSR = Integrated Disease Surveillance and Response

### Tracking Implementation Progress

The MSP describes all M&E processes, indicators and targets that will track progress toward elimination. To monitor progress, data will be regularly collected, analyzed, reviewed and used to inform programme management. In addition to routine data collection through the passive and active surveillance system, detailed and standardized facility reporting will enable tracking of progress. Several specific indicators have been chosen to demonstrate commitment from national and community level in line with the malaria elimination.

Monitoring of the elimination targets is undertaken annually through national malaria programme reports compiled by a team from the programme together with district and national implementers consisting of experts in epidemiology, case management, vector management, surveillance, health promotion, programme management and other relevant areas. The 2024-2029 Strategic Plan will be reviewed at its midpoint in 2026 to assess progress against the targets set within the plan, as well as the efficacy and efficiency of its strategies and activities.

Figure 22: Malaria programmatic M&E info system

### Commodity Tracking System

To monitor consumption of all malaria commodities at health facilities, the Logistic Management Unit using an electronic system is in place under the Central Medical Store. Periodically, all heath facilities submit order form (report and request) which include consumption for previous months to CMS. The data is entered into the system for a quick analysis before a new order is released. The ZAMEP management has access to the system to do a commodity tracking of rapid diagnostic test kits and anti-malarial. The purpose is largely mirroring existing inventory management tools to capture consumptions of malaria commodities at all health facilities. Some operational challenges have been observed by ZAMEP especially in the accuracy of the stock presented. In most cases, the system provides information on stock status at National level only and not the consumption and stock status at peripheral level.

### Programmatic Monitoring and Evaluation System

The outputs and outcomes of malaria control interventions need to be consistently monitored and evaluated through routine and continuous collection and analysis of data for delivery of vector management interventions at community level LLIN, LSM and IRS). In the current MSP special efforts should also be dedicated to case management interventions at community level such as TAT and MDA. Surveillance and its response also need a dedicated system to monitor its efficiency and to report on response interventions.

Figure 23

## DATA QUALITY

Routine supervisions are carried out by ZAMEP, HMIS and District implementers with the aim of assessing and guiding health care providers to ensure data quality from the sources. To guarantee high data quality, there are efforts underway of quality assurance mechanisms implemented by HMIS and other stakeholders to promote accurate collection, aggregation, and reporting of data in addition to routine activities performed by the ZAMEP officers from the Surveillance Unit.

Consolidation of parallel data collection and reporting to ensure that all systems are interoperable is ongoing under the umbrella of Information Communication Technology Unit of the MoH. Currently, health sector programs have several electronic systems for data management and reporting with lack of integration.

It is impressive to note that when a household data collection is done constant data verification during data collection is carried out. During the household survey, a data collection team will consist of data collectors and a supervisor whose primary responsibility is to verify data quality. There are validation rules which ensure that correct data is captured at time of case investigation. Data collected on electronic tablets is automatically backed up to an external storage card daily.  This data is updated on real time cleaned and quality checks are conducted weekly to ensure data completeness.

During the life-span of this plan, therapeutic efficacy testing and the insecticide resistance testing will be conducted as planned. Report and raw data will be cross-checked and verified internally by ZAMEP staff and Principal Officer is involved in this exercise. For instance, data aggregated by a field officer will be confirmed by a second person in the team. Similarly, reports will go through as drafts and shared among implementing partners to ensure accuracy of the data.

The Surveillance Monitoring, Evaluation, Research and Learning Unit managed to maintain a culture of conducting feedback meetings with health facility staff and district malaria surveillance officers to allow for health facility data verification. If a data entry error has occurred, the data will be properly reconciled once the root of the data irregularity has been determined. In this context, data irregularities are subject for rectification. This culture will be continued in the coming five years of implementation.

## PERFORMANCE FRAMEWORK

The success of the malaria elimination programme will be gauged by a series of impact, outcome, output, and process indicators, which measure the results of programmatic implementation at different levels. The impact indicators measure the long-term effect of all the interventions, specifically malaria morbidity and mortality. The outcome indicators are measurements of the effect of each intervention area. For example, the outcome of the case management intervention is to increase the number of confirmed malaria diagnosis and to ensure confirmation and treatment of all cases. Output indicators measure the effects of the service delivery areas. Active case investigation outputs include the number of cases followed-up at household level. All these indicators at the different levels of implementation are   key   measurements   of   the   planned   strategic interventions over the 5-year period, 2024-2029. Performance framework is available in Annex 3.

# APPENDIX

# ANNEX 1: WORKPLAN

| Strategy Outline | Description | Year | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 | 2028 | 2029 | Resp. Unit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1-4 | 1-4 | 1-4 |  |
| Goal | To accelerate elimination of local malaria transmission and preventing re-introduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Area 1 | Integrated Malaria Vector management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 1 | To protect all population with recommended vector management interventions according to epidemiological and ecological setting by 2029, to interrupt malaria transmission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 1.1 | 1.1. Distributing ITNs to ensure Universal Access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1 Quantify and Procure recommended ITNs |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | MVC |
|  | 1.1.2 Planning and implementation of ITNs |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  | MVC |
|  | 1.1.3 Conduct coordination meetings |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | MVC |
|  | 1.1.4 Conduct operational research |  | x |  |  |  | x |  |  |  | x |  |  |  |  |  |  | MVC & RI |
| Strategic Approach / Intervention 1.2 | 1.2. Performing reactive focal Indoor Residual Spraying |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.1 Reactive Focal Indoor Residual Spray |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | MVCU |
|  | 1.2.2 Update the Reactive Rapid Response guidelines. |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MVCU |
|  | 1.2.3 Ensure Environment Compliance |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.4 Implement Reactive IRS in targeted Areas |  | x |  |  |  |  |  |  |  | x |  |  |  |  |  |  | MVCU |
|  | 1.2.5 Monitoring and Evaluation |  | x |  |  |  | x |  |  |  | x |  |  |  | x | x | X | MVCU |
| Strategic Approach / Intervention 1.3 | 1.3. Expanding Larval Source Management by using bio-larvicides |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.3.1. LSM implementation |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | MVCU |
|  | 1.3.2 Conduct community engagement and relevant authorities and advocacy |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | X | SBC&CEC & MVCU |
| Strategic Approach / Intervention 1.4 | 1.4. Promoting the use of topical repellents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.4.1 Implementation of repellents initiatives |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  | MVCU |
|  | 1.4.3 Promote the use of repellents continuously through engaging and sensitizing targeted population (e.g. fisheries and others) |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | SBC&CE & MVCU |
|  | 1.4.2 Conduct Operational Research (e.g., acceptability and usage). |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  | MVCU |
| Strategic Approach / Intervention 1.5 | 1.5. Mitigating Insecticide resistance to malaria vectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.5.1 Conduct susceptibility test, intensity and mechanism of resistance, of malaria vectors, KDR & molecular analysis |  |  |  | x |  |  |  |  |  |  |  |  |  | x | x | X | MVCU |
|  | 1.5.2 Update insecticide mitigation plan |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  | MVCU |
| Strategic Approach / Intervention 1.6 | 1.6. Introducing new emerging vector management tools when available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MVCU |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.6.1 In most part, implemented based on activities described either for ITN, LSM, Repellents |  |  |  |  |  | x | x | x | x | x | x | x | x | X | x | x | MVCU |
| Strategy Outline | Description | Year | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 | 5 |  | Resp. Unit |
|  |  | Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1-4 | 1-4 |  |  |
| Strategic Area 2 | Malaria diagnosis, treatment and preventive therapy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 2.1: | 2.1 By 2029, to test all symptomatic suspected malaria infections in health facilities through passive case detection and to test at least 75% of eligible population at risk in the communities through active case detection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 2.1.1 | 2.1.1 Testing suspected malaria cases attending health facilities by using mRDT for antigen detection and malaria microscopy for malaria parasites examination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.1 Quantify and procure malaria commodities, equipment’s and consumables for passive case detection |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | ZAMEP PSM & DU |
| Strategic Approach / Intervention 2.1. | 2.1.2 Testing eligible population at risk in the communities by using mRDT for antigen detection for malaria parasites examination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.2.1 Quantify and procure malaria commodities, equipment’s and consumables for active case detection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 2.1. | 2.1.3. Providing high quality malaria diagnostic services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.3.1 Conduct quality control of malaria diagnostics |  |  |  |  | x | x |  |  | x | x |  |  | x | X | x | x | DU |
|  | 2.1.3.2. Capacity building for malaria diagnosis |  |  |  | x |  |  |  |  |  |  |  |  |  |  | X |  | DU & DHMT |
|  | 2.1.3.3. Conduct malaria case management technical working group meetings |  |  |  |  | x |  | x |  | x |  | x |  | x | x | X | X | DU & DHMT |
| Strategic Objective 2.2 | 2.2. To prevent occurrence of malaria related deaths by providing appropriate management of uncomplicated and severe malaria to 100% of confirmed malaria cases and eligible population at risk by 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 2.2.1 | 2.2.1 Treating confirmed malaria cases with recommended efficacious anti – malaria therapies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.1.1 Quantify and procure antimalarial commodities |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  | x | MCM & PSM |
|  | 2.2.1.2. Therapeutic efficacy study to monitor drug resistance |  |  |  |  | x |  |  |  |  |  |  |  |  | x | X |  | MCM |
| Strategic Approach / Intervention 2.2.2 | 2.2.2 Maintaining high quality malaria management services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.2.1 Capacity building for malaria treatment |  |  |  |  | x |  |  |  |  |  |  |  | x |  | X |  | MCM & PSM |
|  | 2.2.2.2 Conduct supportive supervision |  |  |  | x |  | x |  | x |  | x |  | x |  |  |  | X | MCM |
|  | 2.2.2.3 Improve malaria case management initiatives including services for marginalized at risk population and severe malaria management |  |  |  | x |  | x |  | x |  | x |  | x |  | x | x |  | MCM & DHMT |
| Strategic Approach / Intervention 2.2.3 | 2.2.3 Providing effective pre-referral and emergency management of severe malaria conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.3.1 Improve severe malaria management |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  | MCM & DHMT |
| Strategic Approach / Intervention 2.2.4 | 2.2.4. Providing antimalarial preventive therapies to targeted high risk population and identified transmission foci to decrease morbidity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.4.1. Contributing to Interrupt malaria transmission in identified foci |  |  |  |  | x |  | x |  | x |  | x |  | x | x | x | X | MCM & DHMT |
|  | 2.2.4.2 Improve malaria case management initiatives including services for marginalized at risk population and severe malaria management |  |  |  | x |  | x |  | x |  | x |  | x |  | X | X | X | MCM & DHMT |
| Strategy Outline | Description | Year | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 | 5 |  | Resp. Unit |
|  |  | Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1-4 | 1-4 |  |  |
| Strategic Area: 3 | Malaria Surveillance and Response |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 3 | 3. To intensify malaria surveillance and response in all shehias by 2029, to enhance the progress towards malaria elimination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 3.1. | 3.1 Reinforcing response to detected local malaria transmission foci through integrated focal entomological and epidemiological surveillance to interrupt transmission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.1 Integrate epidemiological and entomological surveillance |  | x | x | x | x |  |  | x |  |  | x |  |  | x |  |  | MSR |
|  | 3.1.2. Provide foci characterization and response (Identification, notification and investigation of active foci) |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | X | MSR |
|  | 3.1.3 Establish effective, targeted, specific and innovative response mechanisms for identified population at risk of local transmission |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  | MSR |
|  | 3.1.4. Strengthen MCN ICT architecture and sustainability |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  | MSR |
|  | 3.1.5. MSR Capacity building |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  | MSR |
| Strategic Approach / Intervention 3.2 | 3.2. Strengthening surveillance and response to detected imported malaria cases to prevent re-introduction of transmission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.1 Maintain case based surveillance for imported cases |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | MSR |
|  | 3.2.2 Establish targeted and innovative surveillance and response mechanisms for population identified to be at risk for imported malaria |  | x | x | x | X | x | x | x | x | x | x | x | x | x | x | X | MSR |
| Strategic Approach / Intervention 3.3 | 3.3. Operationalizing an effective malaria epidemic preparedness and control plan |  |  | x | x | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  | x | x | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3.1 Update a functional malaria epidemic preparedness plan |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  | X | MSR |
|  | 3.3.2. Set up and maintain an epidemic response |  |  | x |  | x |  | x |  | x |  | x |  | x | X | x | X | MSR |
| Strategic Approach / Intervention3.4 | 3.4. Expanding efficient malaria entomological surveillance, including molecular analysis, for systematic collection and use of essential vector population dynamics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  | x |  |  |  | x |  |  |  |  |  |  |  |  |
|  | 3.4.1. Maintain and expand entomological surveillance in sentinel sites |  | x | x | x | x | x | x | x | x | x | x |  |  |  |  | X | IMVMU |
|  | 3.4.2 Conduct insecticide resistance monitoring |  | x |  |  |  | x |  |  |  | x |  |  |  | x | x | X | IMVMU |
|  | 3.4.3. Quality assessment of IRS and insecticide decay rate |  | x | x | x | x | x | x | x | x | x | x |  |  |  |  | X | IMVMU |
|  | 3.4.4. Use of PCR technique for monitoring of malaria vectors |  |  |  |  |  | x |  |  |  | x |  |  |  |  |  | X | IML & PSM |
| Strategic Area: 4 | Monitoring, Evaluation, Research and Learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 4 | 4. To improve programmatic accountability through monitoring and evaluation of all strategic objectives and interventions targets, by 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 4.1 | 4.1. Strengthening comprehensive malaria strategic information system through appropriate data collection and reporting tools, efficient data repository, and smart data analysis and visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1.1. Develop comprehensive ZAMEP information system database |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  | M&E |
|  | 4.1.2. Conduct program data review |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | M&E |
|  | 4.1.3. Malaria data use workshop |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | M&E |
|  | 4.1.4. Enhance data dissemination to appropriate audience |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | X | M&E |
| Strategic Approach / Intervention 4.2 | 4.2. Establishing proper mechanism for programmatic M&E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.2.1. Develop M&E plan of the malaria strategic plan |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  | M&E |
|  | 4.2.2.Develop ZAMEP data management plan |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  | M&E |
| Strategic Approach / Intervention 4.3 | 4.3. Monitoring implementation of the strategic plan towards the achievements of set targets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.3.1. Conduct programmatic review |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  | X | M&E |
|  | 4.3.2. Review performance of thematic technical working group |  |  | x |  | x |  | x |  | x |  | x |  | x |  |  | X | x |
|  | 4.3.3. Review program/thematic monitoring tools (data collection tools, supervision tools in thematic areas). |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | M&E |
|  | 4.3.4. Review performance of multisectoral engagement |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | X | M&E |
|  | 4.3.4. Review performance of sub recipient |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  | X |  |
| Strategic Approach / Intervention 4.4 | 4.4. To conducting priority operational researches for evidence-based decision making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.4.1. Conductive operational researches relevant to improving implementation of the MSP |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | MCM |
| Strategic Approach / Intervention 4.5 | 4.5. Ensuring data quality audit and verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.5.1.Conduct verification of the quality of Program reported data for key indicators |  |  |  | x |  | x |  | x |  | x |  | x |  | x |  | X | M&E |
|  | 4.5.2.Assess the ability of ZAMEP systems to collect, report quality data and effective use of the data |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | X | M&E |
|  | 4.5.3. Strengthening MSR technical working group |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  | X | M&E |
| Strategy Outline | Description | Year | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 | 5 |  | Resp. Unit |
| Strategic Area 5: | Logistic management system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 5 | 5. To ensure uninterrupted supply of quality and safe malaria commodities and supplies, to avail zero stock-outs at service delivery points by 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 5.1 | 5.1. Providing adequate quantification process for all malaria commodities according to plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.1.1. Perform annual quantification |  | X |  |  |  | x |  |  |  | x |  |  |  | x | x | x |  |
| Strategic Approach / Intervention 5.2 | 5.2. Maintaining an efficient procurement and supply management system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.2.1. Strengthen the supply chain system from National to health facilities level |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X | ZAMEP - PSM |
| Strategic Approach / Intervention 5.3 | 5.3. Strengthening a well-organized logistics data systems to support inventory of malaria commodities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.3.1 Capacity building |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | ZAMEP - PSM |
| Strategic Approach / Intervention 5.4 | 5.4. Ensuring continuous quality assurance and safety vigilance of malaria commodities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.4.1. Provide QA and QC |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X |  |
|  | 5.4.2. Promote ADR reporting |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X |  |
| Strategy Outline | Description | Year | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 | 5 |  | Resp. Unit |
| Strategic Area: 6 | Social behaviour change and community engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 6 | 6. To promote positive malaria behaviors through evidence-based SBC&CE strategies by ensuring that 100% of the targeted population is practicing positive malaria behaviours by 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 6.1 | 6.1. Designing and developing using behavioral science innovative approaches |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.1.1. Conduct qualitative research by employing innovative methodologies to uncover barriers and facilitators on malaria behavioral determinant with the purpose of informing message prioritization among high-risk population |  | x |  |  |  | x |  |  |  | x |  |  |  | x | x |  | SBC&CEU & MSR |
|  | 6.1.2. Utilize artificial intelligence and advanced cell phone and social media targeting to disseminate targeted reminders among target population |  |  | x |  |  |  | x |  |  |  | x |  |  | x | x | X | SBC&CEU |
|  | 6.1.3. Develop Provider Behavior Change (PBC) Initiative to address provider SBC&CE challenges and bias across all malaria behaviours |  |  | x |  |  |  | x |  |  | x |  |  |  | x | x |  | SBC&CEU |
|  | 6.1.4. Digitalize SBC&CE supportive supervision tool to have real time monitoring of community-based SBC&CE activities and thereby inform immediately corrective actions |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  | X | SBC&CEU |
| Strategic Approach / Intervention 6.2 | 6.2. Deploying community Based participatory approaches to address malaria behavioral determinants and social norms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.2.1. Co-design interactive community toolkit and subsequently orient CHVs on usage of the toolkit |  | x |  |  |  |  |  |  |  |  | x |  |  |  |  | X | SBC&CEU & HPU |
|  | 6.2.2. Implement participatory community dialogue sessions through CHVs for both clear foci & hotspot areas |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | X | SBC&CEU |
|  | 6.2.3. Reinforce CHVs and mass media work with targeted community wider events i.e., community theater, community health days (shehia) |  |  | x |  | x |  | x |  | x |  | x |  | x | x | x | X | SBC&CEU |
|  | 6.2.4. Develop and implement SBC&CE outreach programs for marginalized and disadvantaged vulnerable groups in all malaria transmission areas |  |  | x |  |  |  | x |  | x |  |  |  | x | x | x | X | SBC&CEU |
|  | 6.2.5. Design SBC&CE activities and message package that will be ready to deploy as emergence response for malaria outbreak (i.e., Artemisinin Partial Resistance, Anopheles Stephensi) |  |  |  | x |  |  |  |  |  |  | x |  |  | x |  | X | SBC&CEU |
| Strategic Approach / Intervention 6.3 | 6.3. Leveraging multimedia channels to promote positive malaria behaviors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.3.1. Use human centered and co design methodologies to develop multimedia campaign and co deliver through channels that combines greater reach, access and trust among target audience. (channels such as radio, TV and Print media) |  |  | x |  |  |  | x |  |  |  | x |  |  | x | x | X | SBC&CEU |
|  | 6.3.2. Develop social media plan and use it on engagement of social media influencers who will intensify social media presence and increase malaria messages relevance among target population |  | x |  |  |  | x |  |  |  | x |  |  |  | x | x | X | SBC&CEU |
|  | 6.3.3. Use alternative channels such as animation to reach strategic audience such as travelers through airports and marine point of entry |  |  |  |  | x |  |  |  | x |  |  |  | x | x | x | X | SBC&CEU |
|  | 6.3.4. Implement multi-media-based Provider Behavior Change campaign to echo and provide focused initiative being designed and implemented under Strategic Objective 1. The campaign will promote professional providers and address provider SBC&CE challenges and bias across all malaria behaviors |  |  | x |  |  |  | x |  |  |  | x |  |  | x | x | X | SBC&CEU |
| Strategic Approach / Intervention 6.4 | 6.4. Advocating multisectoral and private sector engagement for malaria elimination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.4.1. Review school malaria communication and advocacy plan and use it to orient and guide all school-based malaria activities such as development of teachers and students’ tool |  | x |  |  |  |  |  |  | x |  |  |  |  | x |  | X | SBC&CEU |
|  | 6.4.2: Implement school- based malaria activities such as strengthening existing school clubs, clubs malaria sessions and exchange visits between school to enhance their skills in facilitating malaria elimination in their clubs and discussions with parents |  |  | x |  |  |  |  |  |  | x |  |  |  | x |  | X | SBC&CEU & DHMT |
|  | 6.4.3. Develop multisectoral and private sectors malaria elimination planned implement activities suggested in the plan to ensure activate engagement of all sectors to eliminate malaria in Zanzibar |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SBC&CEU & DHMT |
|  | 6.4.4. Conduct advocacy activities to raise the profile of malaria and seek active involvement of high-level leaders/politicians in the malaria elimination agenda. |  |  |  | x |  |  |  | x |  |  |  |  |  |  |  |  | SBC&CEU & DHMT |
|  | 6.4.5: Engage and orient influencers from other sectors as sheikh, influential leaders and traditional healers |  |  | x |  |  |  | x |  |  |  | x |  |  | x | x | X | SBC&CEU & DHMT |
| Strategy Outline | Description | Year | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 | 5 |  | Resp. Unit |
|  |  | Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1-4 | 1-4 |  |  |
| Strategic Area: 7 | Leadership, Partnership and Resource mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 7.1 | 7.1 To enhance effective, partnership and multisectoral engagement towards malaria elimination by assuring that 100% of annual planned activities are implemented by 2029 from the 80% level in 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 7.1.1 | 7.1.1. Providing effective leadership and governance for the implementation of malaria elimination interventions at all levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.1.1.1 Conduct technical working groups meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PM |
|  | 7.1.1.2 Conduct programmatic reviews |  |  |  | x |  | x |  |  | x |  | x |  | x | x | x | X | PM |
|  | 7.1.1.3 Support Programmatic over sight and regular managerial activities |  |  |  | x |  |  |  | x |  |  |  | x |  | x | x | X |  |
|  | 7.1.1.4 Support Program for develop new Strategic plan VI |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | X |  |
|  | 7.1.1.5 Support program for Grant Applications |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  | X |  |
|  | 7.1.1.6 Support Programmatic Administrative costs |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X |  |
| Strategic Approach / Intervention 7.1.2 | 7.1.2. Promoting effective multi-sectoral engagement and public-private partnership to achieve malaria elimination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.1.2.1 Establish effective collaboration and partnership with relevant health and non-health institutions |  |  |  | x |  | x |  |  | x |  | x |  | x | x | x | X |  |
| Strategic Approach / Intervention 7.1.3 | 7.1.3. Conducting cross-border initiatives to mitigate the impact of malaria importation and reintroduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.1.3.1. Operationalize implementation of Regional strategic framework for cross border collaboration in malaria elimination. |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X |  |
| Strategic Area | Leadership, Partnership and Resource mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective 7.2: | 7.2 To enhance sustainable financing and accountability for the implementation of the strategic plan by increasing domestic financing up to 50% of the total malaria funding needs by 2029, from the 6% level in 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 7.2.1 | 7.2.1. Enhancing sustainable financing for malaria elimination interventions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2.1.1. Finalize Malaria Sustainability Plan |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 7.2.2 | 7.2.2. Mobilizing adequate resources (human and financial) to support the efficient implementation of the strategic plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2.2.1. Establish multisectoral resource mobilization mechanism for malaria elimination interventions |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Approach / Intervention 7.2.3 | 7.2.3. Advocating for increased malaria allocation in the overall health and other sectoral budgets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2.3.1. Advocate meeting with official ministries and other sectoral budget |  |  |  | x |  |  |  | x |  |  |  | x |  | x | x | X |  |
| Strategic Approach / Intervention 7.2.4 | 7.2.4. Optimizing functional support and competency to create enabling working environment for sustainable implementation of malaria elimination strategies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Main Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2.4.1. Create enable working environment for the program to perform interventions effectively |  |  |  | x |  | x |  | x |  | x |  | x |  | x | x | X |  |
| Strategic Approach / Intervention 7.2.5 | 7.2.5. Supporting implementation of the priority areas identified in the RSSH need assessment report of 2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2.5.1 Support MoH units through policy, planning and research department in line with strengthening MoH system |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  | X | PM |

# ANNEX 2: BUDGET

|  |  | Phase 1 2024-2026 |  |  | Phase 2 2027-2029 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy | Approach | Needs | Available/ anticipated | Gap | Needs | Available/ anticipated | Gap |
| IMVM | IRS | $ 1,190,431 | $ 350,117 | $ 840,314 | $ 1,290,385 | $ 350,117 | $ 940,268 |
|  | ITN | $ 2,226,707 | $ 2,226,707 | $ | $ 2,226,707 | $ 2,226,707 | $ |
|  | LSM-BL | $ 3,297,923 | $ 244,223 | $ 3,053,700 | $ 2,303,867 | $ 244,223 | $ 2,059,644 |
|  | LSM-EM | $ 50,000 | $ 50,000 | $ | $ 50,000 | $ 50,000 | $ |
| M&E | MSIS | $ 32,654 | $ 32,654 | $ | $ 32,654 | $ 32,654 | $ |
|  | OR | $ 326,703 | $ | $ 326,703 | $ 640,167 | $ | $ 640,167 |
| MCM | Diagnosis | $ 1,912,204 | $ 1,912,204 | $ | $ 1,912,204 | $ 1,912,204 | $ |
|  | MDA | $ 111,578 | $ 10,348 | $ 101,229 | $ 21,682 | $ 10,348 | $ 11,333 |
|  | Treatment | $ 1,306,511 | $ 1,306,511 | $ | $ 1,306,511 | $ 1,306,511 | $ |
| MSR | ACD | $ 157,461 | $ 52,997 | $ 104,464 | $ 87,917 | $ 52,997 | $ 34,920 |
|  | Epi Surv | $ 2,275,663 | $ 2,275,663 | $ | $ 2,275,663 | $ 2,275,663 | $ |
|  | HRP | $ 253,535 | $ 68,947 | $ 184,589 | $ 170,518 | $ 68,947 | $ 101,571 |
|  | MMS | $ 1,675,195 | $ 148,293 | $ 1,526,902 | $ 885,140 | $ 148,293 | $ 736,847 |
|  | MVS | $ 1,050,980 | $ 1,050,980 | $ | $ 1,050,980 | $ 1,050,980 | $ |
|  | RCCE | $ 98,665 | $ | $ 98,665 | $ 64,607 | $ | $ 64,607 |
| PM | District Engagement | $ 1,733,008 | $ | $ 1,733,008 | $ 1,231,908 | $ | $ 1,231,908 |
|  | Human Resource Development | $ 1,488,680 | $ 512,629 | $ 976,051 | $ 566,629 | $ 512,629 | $ 54,000 |
|  | ICT | $ 596,458 | $ 99,058 | $ 497,400 | $ 366,358 | $ 99,058 | $ 267,300 |
|  | Infrastructure Dvl | $ 677,000 | $ | $ 677,000 | $ | $ | $ |
|  | Management | $ 1,068,809 | $ 1,068,809 | $ | $ 1,068,809 | $ 1,068,809 | $ |
|  | Mutisectoral | $ 506,000 | $ | $ 506,000 | $ 486,000 | $ | $ 486,000 |
|  | Policy Engagement | $ 138,954 | $ 64,782 | $ 74,172 | $ 120,704 | $ 64,782 | $ 55,922 |
|  | PPP | $ 54,620 | $ | $ 54,620 | $ 36,120 | $ | $ 36,120 |
|  | Technical Assistance | $ 981,000 | $ 900,000 | $ 81,000 | $ 981,000 | $ 900,000 | $ 81,000 |
| SBC&CE | RCCE | $ 1,558,866 | $ 1,558,866 | $ | $ 2,336,466 | $ 1,558,866 | $ 777,600 |
| Total |  | $ 24,769,604 | $ 13,933,786 | $ 10,835,818 | $ 21,512,994 | $ 13,933,786 | $ 7,579,207 |

# ANNEX 3: PERFORMANCE FRAMEWORK

| Strategy Outline | Description | Indicator | Description | Baseline (year) | Mid-term target 2026 | End-term target 2029 | Source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Area 1 | Integrated Malaria Vector management |  |  |  |  |  |  |
| Strategic Objective 1 | To protect all population with recommended vector management interventions according to epidemiological and ecological setting by 2029, to interrupt malaria transmission | Proportion of malaria vectors with confirmed Sporozoite rate | Number of malaria vectors with confirmed plasmodium infection | 0.75% | 0.35% | 0% | ZAMEP entomology database |
|  |  |  | Number of malaria vectors screened for sporozoite |  |  |  |  |
| Strategic approaches/ Interventions | 1.1. Distributing ITNs to ensure Universal Access | Proportion of persons with access to an insecticide-treated mosquito net (ITN) | Population that could sleep under an ITN if each ITN in the household were used by 2 people | 62.1% | 80% | 90% | DHIS |
|  |  |  | Household population visited in the survey |  |  |  |  |
|  | 1.2. Performing reactive focal Indoor Residual Spraying | Proportion of active foci received focal IRS | Active foci that have received focal IRS | 23% | 80% | 100% | ZAMEP database |
|  |  |  | Active foci identified |  |  |  |  |
|  | 1.3. Expanding Larval Source Management by using bio-larvicides | Proportional of treated breeding habitats in shehia with active transmission foci | Number of treated breeding habitats in shehia with active transmission foci | 20% | 85% | 100% | ZAMEP database |
|  |  |  | Total breeding habitats in shehia with active transmission foci identified |  |  |  |  |
|  | 1.4. Promoting the use of topical repellents | Proportion HRP reached with repellent promotion | Identified HRP groups reached with repellant promotion initiatives | NA | 40% | 80% | ZAMEP SBC&CE report |
|  |  |  | Identified HRP groups |  |  |  |  |
|  | 1.5. Mitigating Insecticide resistance to malaria vectors | Proportion of sentinel sites conducting susceptibility test, intensity and mechanism of resistance | Sentinel sites conducting susceptibility test | 100% | 100% | 100% | ZAMEP database |
|  |  |  | Sentinel sites eligible |  |  |  |  |
|  | 1.6. Introducing new emerging vector management tools when available | New tools introduced | NA | NA | 1 | 2 | ZAMEP report |
| Strategic Area 2 | Malaria diagnosis, treatment and preventive therapy |  |  |  |  |  |  |
| Strategic Objective 2.1 | By 2029, to test all symptomatic suspected malaria infections in health facilities through passive case detection and to test at least 75% of eligible population at risk in the communities through active case detection | Annual blood examination rate (%) | Number of persons receiving parasitological test for malaria (Microscope or mRDT) by island | 37% | 42% | 45% | HMIS Routine Surveillance System |
|  |  |  | Population at risk of malaria |  |  |  |  |
| Strategic approaches/ Interventions | 2.1.1 Testing suspected malaria cases attending health facilities by using mRDT for antigen detection and malaria microscopy for malaria parasites examination | Proportion of suspected malaria cases that receive a parasitological test in public health facilities. | Suspected malaria cases that received a parasitological test in public health facilities | 100% | 100% | 100% | HMIS/DHIS2Malaria surveillance system |
|  |  |  | All suspected malaria cases presenting in public health facilities |  |  |  |  |
|  |  | Proportion of suspected malaria cases that receive a parasitological test in Private health facilities. | Suspected malaria cases that received a parasitological test in Private health facilities | 100% | 100% | 100% | HMIS/DHIS2Malaria surveillance system |
|  |  |  | All suspected malaria cases presenting in Private health facilities |  |  |  |  |
|  | 2.1.2 Testing eligible population at risk in the communities by using mRDT for antigen detection for malaria parasites examination | Proportion of eligible population that received a parasitological test at community. | Number of populations received a parasitological test in community | NA | 60% | 75% | Malaria surveillance system |
|  |  |  | Number of targeted populations received parasitological test in community |  |  |  |  |
|  | 2.1.3. Providing high quality malaria diagnostic services | Proportion of supervision QAQC | Number of health facilities conduct QAQC | 100% | 100% | 100% | Malaria Microscope /mRDT database |
|  |  |  | Total number of health facilitiessupervised |  |  |  |  |
| Strategic Objective 2.2 | To prevent occurrence of malaria related deaths by providing appropriate management of uncomplicated and severe malaria to 100% of confirmed malaria cases and eligible population at risk by 2029 | 100% of confirmed malaria cases and eligible population at risk received appropriate treatment by 2029 | Confirmed malaria cases detected in HFs and eligible targeted population receiving an antimalarial therapy | NA | 80% | 100% |  |
|  |  |  | Confirmed malaria cases detected in HFs and eligible population targeted for antimalarial therapy |  |  |  |  |
| Strategic approaches/ Interventions | 2.2.1 Treating confirmed malaria cases with recommended efficacious anti – malaria therapies | Proportion of confirmed malaria cases that received recommended anti- malaria treatment at all health facilities | Confirmed malaria cases at all facilities who received recommended antimalarial treatment according to national policy in all health facilities | 100% | 100% | 100% | HMIS |
|  |  |  | Confirmed malaria cases detected |  |  |  |  |
|  | 2.2.2 Maintaining high quality malaria management services | Proportion of health facilities with an overall MSDQI score over 75% in management of malaria cases | Health facilities with an overall MSDQI score over 75% in management of malaria cases | 70 | 100% | 100% | ZAMEP annual report |
|  |  |  | Health facilities assessed with MSDQI in the period |  |  |  |  |
|  | 2.2.3 Providing effective pre-referral and emergency management of severe malaria conditions | Malaria case fatality rate | Deaths reported with confirmed malaria | 1.8% | 0.9% | 0% | HMIS |
|  |  |  | Confirmed malaria admissions |  |  |  |  |
|  | 2.2.4. Providing antimalarial preventive therapies to targeted high risk population and identified transmission foci to decrease morbidity | Proportion of people receiving antimalarial drugs as preventive therapy | People receiving antimalarial drugs as preventive therapy | NA | 80% | 95% | ZAMEP annual report |
|  |  |  | People eligible for receiving antimalarial drugs as preventive therapy |  |  |  |  |
| Strategic Area 3 | Malaria Surveillance and Response |  |  |  |  |  |  |
| Strategic Objective 3. | To intensify malaria surveillance and response in all shehias by 2029, to enhance the progress towards malaria elimination | Proportion of Districts not reporting zero local cases | Number of Districts not reporting local cases in annual basis | 0 | 50% | 100% | Surveillance system |
|  |  |  | Total number of Districts |  |  |  |  |
|  |  | Proportion of shehias not reporting active foci | Number of shehias not reporting active foci | 44% | 72% | 100% | Malaria surveillance system |
|  |  |  | Total number of shehias |  |  |  |  |
|  |  | Proportion of shehias reporting cleared foci | Number of shehias reporting cleared foci | 5% | 25% | 50% | Malaria surveillance system |
|  |  |  | Total number of shehias |  |  |  |  |
| Strategic approaches/ Interventions | 3.1 Reinforcing response to detected local malaria transmission foci through integrated focal entomological and epidemiological surveillance to interrupt transmission | Completeness of health facility report (zero case report) in weekly basis | Number of health facility reports in weekly basis | 70T% | 100% | 100% | Surveillance system |
|  |  |  | Number of health facility expected reports in weekly basis |  |  |  |  |
|  |  | Timeliness of malaria case notification at health facility | Number of Malaria cases notified within 24 hrs. | 65% | 90% | 100% | Surveillance system |
|  |  |  | Total number of malaria cases detected at heath facilities |  |  |  |  |
|  |  | Timeliness of malaria case investigated and classified at household | Number of malaria cases investigated and classified within 48hrs of notification | 80% | 100% | 100% | Surveillance system |
|  |  |  | Total number of malaria cases notified |  |  |  |  |
|  |  | Timeliness of active foci investigated | Number of active foci investigated within a week from notification | 16% | 56% | 100% | Surveillance system |
|  |  |  | Total number of active foci notified |  |  |  |  |
|  |  | Proportion of malaria cases investigated and classified at household level | Number of Malaria cases investigated and classified | 100% | 100% | 100% | Surveillance system |
|  |  |  | Total number of malaria cases notified |  |  |  |  |
|  |  | Proportion of active foci investigated and respond | Number of active foci investigated and respond | 50% | 75% | 100% | Malaria surveillance system |
|  |  |  | Total number of active foci transmission |  |  |  |  |
|  | 3.2. Strengthening surveillance and response to detected imported malaria cases to prevent re-introduction of transmission | Proportion of malaria imported high-risk mobile people screened | Number of people with imported high-risk malaria transmission screened | 0% | 50% | 100% | Malaria surveillance system |
|  |  |  | Total number of high-risk groups reported |  |  |  |  |
|  |  | Proportion of cross district/regional agreements implemented according to work plan | Number of agreements implemented | 0% | 100% | 100% | ZAMEP annual report |
|  |  |  | Total number of agreements in work plan |  |  |  |  |
|  | 3.3. Operationalizing an effective malaria epidemic preparedness and control plan | Timeliness of malaria epidemics verification according to the standard operation procedures | Number of Outbreaks verified within two weeks (per guideline) | 100% | 100% | 100% | Malaria surveillance system |
|  |  |  | Total number of Outbreaks notified |  |  |  |  |
|  |  | Proportion of malaria epidermic responded | Number of malaria epidemics responded | 100% | 100% | 100% | Malaria surveillance system |
|  |  |  | Total number of epidemics notified |  |  |  |  |
|  | 3.4. Expanding efficient malaria entomological surveillance, including molecular analysis, for systematic collection and use of essential vector population dynamics | Proportion Anopheles mosquitoes collected in sentinel sites and in transmission foci analyzed by PCR | Anopheles mosquitoes collected in sentinel sites and transmission foci analyzed by PCR | 100% | 100% | 100% | ZAMEP entomology database |
|  |  |  | Anopheles mosquitoes collected in sentinel sites and in transmission foci |  |  |  |  |
|  | 3.5 Introducing parasitological surveillance by using recommended molecular analysis | Proportion of malaria parasite collected in transmission foci genotypically analyzed by 2029 | Malaria parasite collected in foci analyzed by PCR | NA | 50% | 100% | ZAMEP surveillance |
|  |  |  | Malaria parasite collected in foci |  |  |  |  |
| strategy Outline | Description | Target (outcomes) | Strategic Objective |  |  |  |  |
| Strategic Area 4 | Monitoring, Evaluation, Research and Learning |  |  |  |  |  |  |
| Strategic Objective 4 | To improve programmatic accountability through monitoring and evaluation of all strategic objectives and interventions targets, by 2029 | Proportion of impact indicators achieved the target | Number of impact indicators that achieved the annual target | 70% | 80% | 100% | ZAMEP annual report |
|  |  |  | Total number of impact indicators planned to be achieved |  |  |  |  |
|  |  |  | Total number of outcome indicators planned to be achieved |  |  |  |  |
| Strategic approaches/ Interventions | 4.1. Strengthening comprehensive malaria strategic information system through appropriate data collection and reporting tools, efficient data repository, and smart data analysis and visualization | Functional comprehensive malaria Management information system (MIS) in place |  | NA | In place | In place | ZAMEP annual report |
|  | 4.2. Establishing proper mechanism for programmatic M&E through enhanced dissemination of data for operational and programmatic use | Proportion of recommendation implemented (Technical meeting, ZAMEAC meeting, Evaluation, assessment etc) | Total number of recommendations | 70% | 100% | 100% | ZAMEP annual report |
|  |  |  | Total number of programmatic decisions made |  |  |  |  |
|  |  | Number of abstracts presented at international conference per thematic area |  | 0 | 8 | 8 | Abstract report |
|  | 4.3. Monitoring implementation of the strategic plan towards the achievements of set targets | Proportion of annual targets achieved per MSP | Number of targets achieved the annual target | 80% | 100% | 100% | ZAMEP Annual report |
|  |  |  | Total numbers of annual target planned to be achieved |  |  |  |  |
|  | 4.4. To conduct priority operational researches for evidence-based decision making | Number of Operational researches implemented | Operational researches implemented | 0 | 2 | 4 | ZAMEP annual report |
|  |  |  | Planned operational researches |  |  |  |  |
|  | 4.5. Improve data quality through continuous data audit and verification | proportion of Health facilities with accuracy/consistency malaria data for the key indicators (suspected, tested, confirmed, species, treatment etc) in surveillance system | Number of health facility with accurate malaria data | 70% | 80 | 100% | ZAMEP annual report |
|  |  |  | Total number of health facilities |  |  |  |  |
| Strategic Area 5 | Logistic management system |  |  |  |  |  |  |
| Strategic Objective 5 | To ensure uninterrupted supply of quality and safe malaria commodities and supplies, to avail zero stock-outs at service delivery points by 2029 | Zero stock-outs of malaria commodities at service delivery points by 2029 | Proportional of HF with the improved logistics management | 100% | 100% | 100% | From the guidelines and annual reports. |
|  |  |  | Number of eligible HF |  |  |  |  |
| Strategic approaches/ Interventions | 5.1. Providing adequate quantification process for all malaria commodities according to plan | Proportion of updated malaria commodities quantified by type (insecticides, larvicides, bed-nets, diagnostics and therapeutics) according to implementation plan | Updated malaria commodities quantified by type | NA | 100% | 100% | 100% |
|  |  |  | Malaria commodities by type |  |  |  |  |
|  | 5.2. Maintaining an efficient procurement and supply management system | Proportion of needed commodities procured according to implementation plan | Proportional of procured commodities | 100% | 75% | 100% | Annual Reports |
|  |  |  | Quantified commodities per category |  |  |  |  |
|  | 5.3. Strengthening a well-organized logistics data system to support inventory of malaria commodities | Functional and comprehensive improved electronic logistic information system in place at all levels of service delivery | Functional elements of the logistic information system | NA | 75% | 95% | Reports |
|  |  |  | Planned elements of the logistic information system |  |  |  |  |
|  | 5.4. Ensuring continuous quality assurance and safety vigilance of malaria commodities | Proportion of quality assured (internal and external) malaria commodities | Quality assured (internal and external) malaria commodities by category | 100% | 90% | 100% | Reports |
|  |  |  | Procured malaria commodities by category |  |  |  |  |
| Strategic Area 6 | Social behaviour change and community engagement |  |  |  |  |  |  |
| Strategic Objective 6. | To promote positive malaria behaviors through evidence-based SBC&CE strategies by ensuring that 100% of the targeted population is practicing positive malaria behaviours by 2029 | Proportion of the targeted population who practice positive malaria behaviors | Targeted populations who practice positive malaria behaviors | Not available | 70 | 99 | Survey |
|  |  |  | Targeted populations |  |  |  |  |
| Strategic approaches/ Interventions | 6.1. Designing and developing using behavioral science innovative approaches | Proportion of interventions designed and implemented using behavioral science approaches | Interventions designed and implemented | Not available | 70 | 99 | Annual Report |
|  |  |  | Interventions planned to be designed and implemented annually |  |  |  |  |
|  | 6.2. Deploying community Based participatory approaches to address malaria behavioral determinants and social norms | Proportion of targeted audiences with positive attitude towards malaria behaviors | Targeted audiences reached to positive malaria behaviors/number of audiences targeted for positive attitudes towards malaria behavior | Not available | 70 | 100 | Survey report |
|  | 6.3. Leveraging multimedia channels to promote positive malaria behaviors | Proportion of targeted population reached with appropriate malaria messages through multi media | Targeted population reached with appropriate malaria messages through multi media | Not available | 70 | 99 | Survey report |
|  |  |  | Targeted population planned to be reached with appropriate malaria messages |  |  |  |  |
|  | 6.4. Advocating community, multisectoral and private sector engagement for malaria elimination | Proportion of advocacy meetings conducted to engage multisectoral and private sectors. | Advocacy meetings conducted | Not available | 6 | 10 | Activity report |
|  |  |  | Advocacy meeting planned to be conducted |  |  |  |  |
| Strategic Area 7 | Leadership, Partnership and Resource mobilization |  |  |  |  |  |  |
| Strategic Objective 7.1 | To enhance effective, partnership and multisectoral engagement towards malaria elimination by assuring that 100% of annual planned activities are implemented by 2029 from the 80% level in 2022 | Proportion of recommendations/issue from multi-sectorial action plan implemented/solved | Recommendations from multi-sectorial action plan implemented | 0 | 80% | 100% | Annual activity reports |
|  |  |  | Recommendations from multi-sectorial action plan implemented |  |  |  |  |
| Strategic approaches/ Interventions | 7.1.1. Providing effective leadership and governance for the implementation of malaria elimination interventions at all levels | Proportion of malaria interventions conducted by the program at all level | Activities fully implemented as planned | 90% | 90% | 95% | Annual Activity reports |
|  |  |  | Planned activities |  |  |  |  |
|  | 7.1.2. Promoting effective multi-sectoral engagement and public-private partnership to achieve malaria elimination | Proportion of multisectoral entities actively engaged in malaria elimination through a common action plan | Multisectoral entities actively engaged in malaria elimination | 2 | 10 | 15 | Multisectoral action plan |
|  |  |  | Multisectoral entities endorsed malaria elimination action plan |  |  |  |  |
|  | 7.1.3. Conducting cross-border initiatives to mitigate the impact of malaria importation and reintroduction | Proportion of agreed cross border action plan implemented | Agreed interventions implemented according to cross border action plan | NA | 50% | 80% | Meeting reports / Annual implementation Reports |
|  |  |  | Agreed interventions in cross border action plan |  |  |  |  |
| Strategic Objective 7.2 | To enhance sustainable financing and accountability for the implementation of the strategic plan by increasing domestic financing up to 50% of the total malaria funding needs by 2029, from the 6% level in 2022 | Proportion of the total malaria annual funding contributed by the RGoZ | Malaria annual funding contributed by the RGoZ | 6 | 25% | 50% | ZAMEP financial report |
|  |  |  | Anticipated malaria annual funding |  |  |  |  |
| Strategic approaches/ Interventions | 7.2.1. Enhancing sustainable financing for malaria elimination interventions | Updated malaria financing and resource mobilization plan available and endorsed | NA | NA | 1 | 1 | Resource mobilization plan |
|  | 7.2.2. Mobilizing adequate resources (human and financial) to support the efficient implementation of the strategic plan | Number of review meetings to monitor implementation of the sustainability plan conducted | Number of Review Meetings conducted | NA | 3 | 8 | Meeting reports |
|  | 7.2.3. Advocating for increased malaria allocation in the overall health and other sectoral budgets | Proportion of the total MoH annual funding targeting malaria elimination | Annual malaria elimination budget | NA | 5% | 5% | ZAMEP financial report |
|  |  |  | Annual MoH budget |  |  |  |  |
|  | 7.2.4. Optimizing functional support and competency to create enabling working environment for sustainable implementation of malaria elimination strategies | Proportion of malaria funds allocated for health system strengthening (RSSH) | Malaria funds allocated for health system strengthening | NA | 13% | 13% | Annual Financial Report |
|  |  |  | Malaria funding envelop |  |  |  |  |
|  | 7.2.5. Supporting implementation of the priority areas identified in the RSSH need assessment report of 2023 | Priority areas identified in the RSSH need assessment | Priority areas identified in the RSSH need assessment funded through malaria envelop | NA | 33% | 33% | Annual Financial Report |
|  |  |  | Priority areas identified in the RSSH need assessment |  |  |  |  |

# ANNEX 5. SWOT ANALYSIS

| PROGRAMME MANAGEMENT |  |  |
| --- | --- | --- |
| Strengths |  | Opportunities |
| - Existence of functional and well-defined program and organized structure for malaria elimination - Existence of Strategic Plan and various operational guidelines/documents for implementation of malaria elimination programs - Well experienced and committed team of program officers in each thematic area - Strong and well-established partnership among key malaria stakeholders (GF, PMI/USAID & Other donors) to support both technically and financial the malaria elimination agenda - Functional platforms for regular coordination, monitoring and evaluation of the program. These include weekly meetings, annual and quarterly reports and regular program performance reviews - Functional and effective platforms for technical contributions and advice for malaria elimination agenda such as Malaria Advisory Committee, Malaria TWGs - Capacity to implement majority of planned activities as per workplan (full implementation 60 %, partial implemented 15 %, low implementation 15% and 10% not implemented) - Presence of different Research and higher learning institutions working and supporting the Program in malaria research activities (e.g. MUHAS, IFAKARA, SUZA, SWISS TPH, UCSF and others) - High acceptance and recognition of malaria prevention interventions in general community - Managed to sustain very low prevalence (less than 1%) of local malaria transmission in the Islands |  | - Existence of collaborative ministries, departments and other potential stakeholders for malaria elimination interventions - Political stability and willingness to support malaria elimination interventions. - Conducive geographical environment and manageable population of Zanzibar favor implementation of malaria elimination strategies - Availability of different forums for potential harnessing of knowledge and information pertinent to the malaria elimination agenda (WHO, AU, EAC, SADC, THS, NMRI, ASTMH) - Availability of several digital technologies and social media that can facilitate easy communication, advocacy and information sharing to the general population |
| Weaknesses |  | Threats |
| - Inadequate multi-sectoral engagement for implementation of malaria elimination strategies, particularly with private partners and non-health sectors - Limited capacity in undertaking operational research based on program research agenda - Insufficient strategies and clear guidelines to address importation of malaria cases - In adequate number of technical experts in some of the thematic areas like Entomologist, parasitologist, IT specialists - Lack of some technical experts in some of the thematic areas like epidemiologist, biostatisticians, data scientist, some SBC&CE specialist like designers, photographers, documentarists and animators, and programmers, developers and system analysts - Lack of independent M&E unit/section for overall monitoring of program performance - Inadequate enforcement of environmental health and malaria related laws and regulations in the community - No influential leaders actively working as malaria ambassadors to advocate for malaria elimination at national and subnational levels - Inadequate strategies that enhance cross border collaboration with neighboring regions for effective malaria elimination (vector management and human behaviour) - Insufficient use of climatic information and seasonal forecast for preparedness and early warning strategies against malaria - Delay in adopting some new technologies and innovations to fight malaria - Lack of strategic use of low-level stratification data targeting malaria elimination intervention. (One size fit for all) - Inadequate interventions that target outdoor biting mosquitoes which found to be predominant in recent years - Inadequate targeted interventions for special populations like fishermen, students, seasonal workers and unofficial port of entries, etc. - Lack of an integrated approach on foci investigation comprising all respective thematic areas, namely entomology, epidemiology, surveillance, case management, etc. |  | - High donor dependency for the implementation of most activities - Inadequate financial support to cover all planned activities as per Strategic Plan. ~10% of planned activities could not be implemented - Global pandemics such as COVID-19 lead to the disruption of implementation of some planned activities and supply chain of malaria commodities. - Lack of donor support to some key interventions identified by the program necessary for malaria elimination such as larviciding and other LSM based interventions - High incidence of imported malaria cases - Global warming and weather change influencing abnormal seasonal rains that contribute to potential temporary mosquito breeding sites - High movement of population in and out of Zanzibar due to various reasons particularly through official and un-official points of entry in both Unguja and Pemba - Staff relocation who have been trained in malaria aspects to other stations and department thus creatingfrequent gaps in health facilities - High staff attrition and low commitment of staff in private health facilties who have been capacitated by the program - Possibilities of Malaria resurgence in case donors withdraws their support to the program due to various reasons - Poor infrastructure and low living standards among the communities contributing to inadequate protection against malaria |
| Identified Strategic issues |  |  |
| - Needs for effective multi-sectorial engagement with all related sectors in malaria elimination strategies - The program and the ministry should find effective financing strategies to sustain the gain without even with minimal donor support - How to technically address the imported malaria cases in Zanzibar. - More collaboration and support is required from institutional authorities to support malaria control strategies at the Port of Entries (POE) - Needs for effective use of available platforms and experts for learning and technical input within the program |  |  |
| CASE MANAGEMENT - Diagnostic |  |  |
| Strengths |  | Opportunities |
| - All Public Health Facilities in Zanzibar can provide malaria diagnosis and treatment services throughout a year, either by microscope or mRDT - Malaria parasite species are identified, differentiated and quantified at primary health facility levels in all health facilities that have microscope - Revised universal malaria diagnosis guidelines (2021) are available and used in all public and private health facilities, Unguja and Pemba - Strong Collaboration with other technical institution to support External Quality Assurance for Malaria diagnosis - Regular bi-annual integrated supportive supervisions conducted through MSDQI system (DHMT & National) - Regular trainings and updates on malaria diagnosis from different partners. These includes seminars, short course and competence basis recertification trainings - All health facilities (Public and Private) are regularly involved in QA /QC of malaria diagnosis either by Microscope or mRDT - The program has got functional teaching laboratory services at its headquarter, Unguja |  | - The existing good collaboration between ZAMEP and private health facilities provides a platform to address the failure to adhere the malaria diagnosis guideline in most of the private health facilities, through regular trainings, supportive supervisions, mentorship and feedback meeting - The willingness of developing partners to support the elimination agenda, to establish the teaching laboratory in Pemba and also molecular parasitology at ZAMEP - Existence of relevant authorities in Zanzibar regarding to policy enactment gives the opportunity for the program to advocate for standardized usage of only multiple detection mRDT in both public and private health facilities. |
| Weaknesses |  | Threats) |
| - Failure to adhere to revised malaria diagnosis guideline in most of the private health facilities. This leads to wrong patient management due to false positive from mRDT - Malaria species confirmation are conducted from only 52 out of 172 (30%) public health facilities using mRDT, from only (4 out 11 districts) - Lack of facilities to conduct malaria parasite molecular analysis in ZAMEP - Lack of teaching laboratory to support malaria diagnosis and training in Pemba - Use of single species detection mRDTs in most private health facilities - Lack of qPCR machine and consumables to conduct molecular /genomic parasitology |  | - Presence of HRP2/3 deletion in plasmodium observed in neighboring countries - Poor health facilities infrastructure and shortage of laboratory technicians to place microscopy services in some health facilities |
| Identified Strategic issues |  |  |
| - Accessibility of molecular analysis in parasitology analysis in ZAMEP - Universal access of malaria quality diagnosis at PoC - Scale up of malaria confirmed cases by detection speciation and quantification in the country |  |  |
| CASE MANAGEMENT – Treatment |  |  |
| Strengths |  | Opportunities |
| - High level of adherence to malaria treatment guidelines with adequate knowledge and skills on malaria case management among all public health facilities - Availability of supportive supervision software (EDS - Electronic Data System) for malaria data collection and regular performance monitoring among health care providers - Sustained support from the Government (RGoZ), GF, PMI, WHO and others for procurement of malaria commoditiesresulting to uninterrupted supply of, Antimalarials, mRDTs and other malaria supplies throughout a year - Well established systems for malaria death audits in all secondary and tertiary health facilities - Continued collaboration and support from several local and international partners on case management activities - Good collaboration with private health sector in malaria case management. These include regular trainings, supportive supervisions and distribution of job aids and primaquine |  | - The threat of emerging resistance of ACTs in Lake Zone regions of Mainland Tanzania and neighboring countries presents the timely opportunity by ZAMEP and partners to regularly conduct TES which was last done in 2017 - The seasonal variation of malaria incidence in Zanzibar and some other emerging issues, gives the impetus to the ZAMEP and partners to conduct operational research |
| Weaknesses |  | threats |
| - Shortage of core health care providers with adequate knowledge and skills for management of severe and complicated malaria cases in some health facilities - Failure to conduct Therapeutic Efficacy Study for antimalarial since 2017 - Lack of electronic system to capture consumption data for antimalarial at PHCU level (PHCU-eLMIS). Data are still collected using paper based system - Irrational prescription of antimalarial in some private health facilities - Incorrectly filling of Reporting & Request (R&R) form resulting to under/ over stocking of medicine and other medical supplies in some facilities - Failure by some Local Government Authorities (LGAs) and District Health Management Teams (DHMTs) to make appropriate follow up and actualizing of recommendations by the program with respect to some malaria case management activities - Missing primaquine consumption data from private health facilities |  | - Emerging resistance of ACTs in Lake Zone regions of Mainland Tanzania and neighboring countries poses potential threat to Zanzibar as well - Self-diagnosis and medication of antimalarial drugs remains a big challenge in the community might end up leading to the antimalarials drug resistance - Occasional overstocking of antimalarials due to annual seasonal variation of malaria incidences - Delayed referrals of severe malaria patients from community to HFs can lead to unnecessary preventable deaths |
| Identified Strategic issues |  |  |
| - Skilled Case Management officers to support case management interventions - Capacity of health care providers to manage uncomplicated and severe malaria diagnosis and treatment - Accurate antimalarial consumption data records to inform the program on decision making - Ensure efficacy and safety of antimalarials to minimize resistance and safeguard the health of patients - Mass drug administration to cut down malaria transmission in hotspot areas |  |  |
| SURVEILLANCE, MONITORING AND EVALUATION) |  |  |
| Strengths | Opportunities |  |
| - Presence of national malaria surveillance guidelines and other working manuals for notification, preparedness and response at all levels. These includes National malaria surveillance guideline, DRTs Manuals and DMSOs working manuals - Availability of knowledgeable, skilled and competent health officers for malaria surveillance at all levels - Presence of Integrated, robust malaria surveillance system (Malaria case notification – MCN/DHIS2) that allows tracking of individual case, classification and stratification up to the shehia level - Maintained malaria reporting completeness and timeliness of more than 90% through MCN & DHS2 though out a year - Strong collaboration with partners and other stakeholders working in malaria surveillance (Academic and research institutions MoH departments, District authorities and community and implementing partners etc.) - Availability and access to multiple streams for malaria information sharing. These include: HMIS, IDSR, LMIS, KAP survey, THIS survey, MIS, TSDI survey etc. - Presence of functional MSR technical working group for regular technical guidance |  | - High donor interest and willingness to support Zanzibar malaria surveillance |
| Weaknesses |  | Threats |
| - Shortage of some of the key professional staff at MSR unit like data analyst and biostatistician - Lack of ZAMEP data management plan to guide data management and ownership - Lack of proper feedback mechanism to share malaria surveillance data at community (e.g. case detection, investigation and classification - Inadequate capacity for data management and analysis at the district and health facility level - Outdated malaria surveillance guidelines (latest 2015) - Malaria preparedness and response plan is still in draft and not operating. Still awaiting for updated thematic guidelines - Lack of data electronically integration between entomological, vector management and epidemiological surveillance data - Lack of Malaria data repository with collated strategic information (including researches, publications and regular implementation reports) |  | - Unstable MoH server hosting MCN system (system requires to run 24hrs for immediate malaria case notification , investigation and response) - Presence of parallel health facility information system (HMIS, EMR and eIDSR) which do not favour seamless implementation of malaria elimination agenda |
| Identified Strategic issues |  |  |
| - Imported case-based Surveillance - Strengthen MSR capacity on data management and analysis - Fulfill Human capacity requirement at MSR unit (e.g. biostatistics, data scientist /analysist) - Establish/implement malaria strategies to minimize risk of importation - Effective monitoring and evaluation of RDA to yield maximum benefits - Establish ZAMEP Monitoring and evaluation system. - Establish malaria commodities stock status at health facilities - Enhance ZAMEP Health information system & data repository (managing existing malaria rich information) - Use of low-level stratification for targeting malaria intervention. |  |  |
| ENTOMOLOGY AND VECTOR MANAGEMENT |  |  |
| Strengths | Opportunities |  |
| - Availability of various guidelines to guide entomology and vector management interventions (e.g. vector management, foci entomological investigation, resistance mitigation , Larval source Management and IRS rapid response) - Availability of essential working tools for vector and entomological control activities, e.g. molecular entomological laboratory, mosquito insectary, transport facilities, etc - Presence of trained and dedicated human resources at both laboratory and implementation/field areas - Availability of financial and technological support for molecular and Immunological analysis of mosquitoes - Strong collaboration with several technical institutions and partners supporting entomology and vector management intervention (e.g. SIS, CDC, IHI, PSI, PMI, Universities) |  | - Presence of several new technologies which can be used in the field of larviciding such as drones for mapping potential areas etc. - Presence of Bio larvicides plant within Tanzania - High acceptance and positive attitude towards LSM (92%) and IRS (86%) among Zanzibar population (MBS, 2021) |
| Weaknesses |  | Threats |
| - Use of outdated guidelines for foci investigations that requires 3 or more local cases to initiate investigations while, updated WHO guidelines require investigations for only a single local case - Lack of electronicdata system for capturing vector and entomological data from the field - Improper conducting of Larval Source Management (LSM) whereby only a single round is done without prior mapping and no monitoring is done after the exercise - No sentinel site for entomological surveillance in Magharibi B District, Unguja - Inadequate skilled/trained human resource on entomology and vector management at ZAMEP - Lack of sequencing machine for identification of An. Stephensi - Lack of insectary at Pemba Island |  | - Shortage of funds for operationalization of foci response and other LSM activities - Increased risk of malaria transmission due to increased outdoor biting of malaria vectors as documented in most entomological surveillance areas - Increasing Pyrethroid insecticide resistance to malaria vector - Potential risk of invasion of new vector species (An. stephensi) from neighbouring regions - Early washing of PBO in LLINs than expected 3 years period |
| Identified Strategic issues |  |  |
| - Indoor vector management methods should be supplemented with outdoor vector interventions - Strategies for Larval Source Management needs to be prioritized if sustainable malaria elimination to be attained - The program stands ready to embrace the use of new technologies and innovations as they become available - More vigilant surveillance system is required to address a current risk of invasion of An. stephensi and other new vector species - Issue of Pyrethroid insecticide resistance need to be addressed timely in collaboration with other respective sectors |  |  |
| SOCIAL AND BEHAVIOUR CHANGE AND COMMUNITY ENGAGEMENT(SBC&CE) |  |  |
| Strengths |  | Opportunities |
| - Good Capacity of the unit to implement almost all planned activities. - About 90% of the activities have been implemented as planned in the current MSP leading to high level of community awareness and acceptance (>85%) of malaria prevention, diagnosis and treatments across entire Zanzibar community members Uninterrupted distribution of ITNs to the targeted populations through mass campaigns and health facility channels (for <5 children & pregnant women. - High level of LLINs ownership (94%) and utilization (85%) among Zanzibar population as found in MBS, 2021) - Good collaboration and support from district authorities, ministries and other stakeholders in SBC&CE activities - Financial and technical support from several local and international partners interested in SBC&CEC, namely USAID (JHUCCP, FHI360, Tulonge Afya) - Strong collaboration and partnership with both public and private media institutions |  | - High coverage and ownership (>80) of mobile phone among Zanzibar community members |
| Weaknesses |  | Threats |
| - Limited funds to cover all SBC&CEC activities as planned - Lack of some essential tools for effective SBC&CEC interventions such as mobile van equipped with PA facility, speakers, advance printers, moving cameras etc.) - Inadequate corporation and support from some marine vessel companies on malaria prevention strategies at Ports of Entry |  | - Low pace of behavioral change despite the intensiveinterventions and high level of awareness and acceptance in the community does not favor the malaria elimination agenda |
| Identified Strategic issues |  |  |
| - Increasing community understanding and perception on importance of malaria elimination rather than control (MALARIA-FREE ZANZIBAR) - Enhancing use of new technologies based on targeted group of society. |  |  |

WHO.2015. The Global Technical Strategy for Malaria – 2016-2030. Geneva, Switzerland. WHA68/2015/REC/1

Source: 2019/20 Household Budget Survey

Zanzibar Planning Commission, Evaluation of Zanzibar Vision 2020, September 2020

Ministry of Health, Health Sector Progress Report, 58 years after Zanzibar Revolution, January 2022

Ministry of Health, Community Development, Gender, Elderly and Children (MoHCDGEC),

(Tanzania Mainland), Ministry of Health (MoH Zanzibar), National Bureau of Statistics (NBS),

Office of the Chief Government Statistician (OCGS) and ICF. 2016. 2015-16 TDHS-MIS.

Manfield-Aders, 1927

Delfini, 1969

Matola, 1984

Minjas et al., 1989

Schwartz E, Pener H, Issa SM, Golenser J. An overview of the malaria situation in Zanzibar. J Community Health. 1997; 22(1):33–44.

Bhattarai A, Ali AS, Kachur SP, et al. Impact of artemisinin-based combination therapy and insecticide-treated nets on malaria burden in Zanzibar. PLoS Med. 2007;4(11):e309.

Smith DL, Hay SI. Endemicity response timelines for Plasmodium falciparum elimination. Mal J. 2009;8:87.

ZAMEP: Conceptual Framework for Malaria Elimination in Zanzibar, (2023)

ZAMEP: Conceptual framework for accelerating malaria elimination in Zanzibar, 2023

WHO, The Health and Environment Linkages Initiative (HELI); Malaria control: the power of integrated action. Accessed on August 19, 2020 from: https://www.who.int/heli/risks/vectors/malariacontrol/en/

ibid

RBM Partnership to End Malaria:  Multisectoral Action Guide to End Malaria (2020)

ZAMEP: ZAMEP Multisectoral Guidelines (2022)